## Sheet1 (hidden)
Technology Stream - Progress as at 31st May 2016
(Rs .Mn)
Funding Position (Capital) | Total Allocation |  |  | Fund Realesed by |  |  | Total Expenditure | Progress % |  | Remarks
| NBD | UGC | Total | NBD (Recommended) | UGC | Total |  | Financial | Physical
University of Colombo | 0 | 150 | 150 | 0 | 0 | 0 | 0 | 0% | 0%
University of Sri Jayewardenapura | 75 | 700 | 775 | 10 | 0 | 10 | 4.33 | 0.5587% | 4.1%
University of Kelaniya | 50 | 170 | 220 | 30 | 0 | 30 | 3.7 | 1.682% | 12%
Univeristy of Jaffna | 50 | 300 | 350 | 5 | 0 | 5 | 0 | 0% | 0%
Vavuniya Campus | 25 | 100 | 125 | 0 | 0 | 0 | 0 | 0% | 0%
University of Ruhuna | 50 | 260 | 310 | 0 | 0 | 0 | 13.6 | 4.387% | 5%
Eastern University , Sri Lanka | 25 | 100 | 125 | 10 | 0 | 10 | 0 | 0% | 30%
South Eatern University of Sri Lanka | 25 | 135 | 160 | 0 | 0 | 0 | 0 | 0% | 0%
Rajarata University of Sri Lanka | 50 | 280 | 330 | 0 | 0 | 0 | 10.3 | 3.121% | 10.5%
Sabaragamuwa University of Sri lanka | 50 | 225 | 275 | 10 | 0 | 10 | 0.06 | 0.02182% | 0.02%
Wayamba University of sri lanka | 50 | 380 | 430 | 0 | 0 | 0 | 0 | 0% | 0%
Uva Wellassa University | 50 | 200 | 250 | 4 | 0 | 4 | 0.07 | 0.028% | 5%
Total | 500 | 3000 | 3500 | 69 | 0 | 69 | 32.06

## CMB (hidden)
University of Colombo- As at 7/7/2016
Name of the Project | Original/Amended TCE (Rs.Mn) | Allocation 2016 (Rs.Mn) | Cabinet Approved Date | Implementation Period |  | Cumulative Expenditure as at 31/06/2016 | Financial progress (%) | Physiacal progress (%) | Remarks
|  |  |  | Date of Start | Expected date of completion
Construction of Buildings | 813 | 139 |  | 2016-01-01 | 2016-12-31 |  |  |  | Pending UGC approval
Rehabilitation Works | - | -
Acquisitions (Equipment, Furniture, Library Books & Vehicles) | 1573 | [6 empty] | 5% | Consultant and TEC appointed , started the procument process
Curriculum Development | 2 | 2 |  |  |  | 0.6Mn | 30% | 50% | Work in progress
Human Capital Development / Training | 162 | 2 |  |  |  | 0.5Mn | 25% | 40% | Work in progress
Recurrent Cost | 100 | 7 |  |  |  | 2Mn | 28% | 28%
Total | 2650 | 150

## Technology
Annex I
Progress Report on Technology Stream Projects
As At 30th June 2016
Name of the Project | Original/Amended TCE (Rs.Mn) | Allocation 2016 (Rs.Mn) | Cabinet Approved Date | Implementation Period |  | Cumulative Expenditure as at 30/06/2016 | Financial progress (%) | Physiacal progress (%) | Remarks
|  |  |  | Date of Start | Expected date of completion
Construction of Technology Building
Construction of Buildings - II
Rehabilitation Works
Acquisitions (Equipment, Furniture, Library Books & Vehicles)
Curriculum Development
Human Capital Development / Training
Recurrent Cost
Total
Note : Applicable only Universities financed under Technology Stream

## Capital projects
Annex II
Progress Report on Other Capital Projects
As At 30th June 2016
Name of the Project | Original/Amended TCE (Rs.Mn) | Allocation 2016 (Rs.Mn) | Cabinet Approved Date | Implementation Period |  | Cumulative Expenditure as at 30/06/2016 | Financial progress (%) | Physiacal progress (%) | Remarks
|  |  |  | Date of Start | Expected date of completion
Rehabilitation & Improvement of Capital Assets
Acquisition of Fixed Assets
Capacity Building
Strengthening Research
Total