## Budget 2016 (hidden)
Head No: 214 - UNIVERSITY GRANTS COMMISSION
Objective 1: Widen participation & equitable access to higher education
Objective 2: Improve physical & aesthetic environment & stakeholder satisfaction
| Programme: Construction Projects | [11 empty] | Rs. Million
| Name of the University & Construction Project | Original / Amended TCE | Implementation Period |  | Progress as at 31.05.2016 |  | Cumulative upto 31.05.2016 | Allocation 2016 | Estimated Value |  |  | Remarks | Project KPI
|  |  | Date of Start | Expected date of Completion | Financial (%) | Physical (%) |  |  | 2017 | 2018 | 2019
University of Peradeniya
Construction / Development Projects - Continuation
| Faculty of Medicine - Stage I | 280 | 2005.08.31 | 2013.04.30 | 86.38% | 100% | 241.86 | 15 | 30.6 | 0 | - |  | 0
| Building for the Dept. of Management Studies | 78.5 | 2009.12.16 | 2014.02.11 | 57% | 100 | 44.5 | 5 | 36 | 0 | - |  | 0
| Building for the Faculty of Allied Health Science - P I , P II | 157 | 2016.01.06 | 2017.07.05 | 26.22% | 20% | 41.17 | 50 | 100 | 0.6 | - |  | 0
| Construction of Para Clinical Building - Stage II | 794.58 | 2011.12.15 | 2013.06.14 | 26.8% | 60% | 213.23 | 50 | 300 | 256.4 | - |  | 0
| Expansion of Student Hostel at Sarasavi Uyana | 89.53 | 2013.10.28 | 2014.10.27 | 67.16% | 100% | 60.13 | 15 | 21.9 | 0 | - |  | 0
| Construction of Chemical Engineering Building - Stage II | 85.71 | 2014.07.11 | 2015.07.10 | 47% | 70% | 41.12 | 25 | 20.5 | 9.6 | - |  | 0
| Proposed Extension to the Surgical Ward Faculty of Medicine | 81.25 | 2014.07.25 | 2016.07.24 | 39% | 28% | 31.55 | 30 | 26.7 | 8 | - |  | 0
| Building for the Dept. of Management Studies | [9 empty] | - |  | 0
| Stage I Phase III | 93.1 | 2014.07.15 | 2015.07.14 | 50% | 100% |  | 0 |  | 0 | - |  | 0
| Stage II |  |  |  | 82% | 100% | 76.3 | 40 |  | 0 | - |  | 0
| Construction of Five storied Building for Faculty of Dental Science | 209.59 | 2014.08.13 | 2016.02.19 | 41% | 48% | 84.24 | 38 | 86.4 | 20 | - |  | 0
| Master plan development Faculty of Agriculture - Phase I | 930.4 | 2014.08.29 | 2017.02.28 | 66% | 68% | 590.43 | 200 | 146 | 94 | - |  | 0
| Building for the Dept. of Statistical and Computer Science | 179 | - | - | 0 | 0 | 0 | 20 | 71 | 70 | 18 |  | 0
| Construction of Faculty Center - Faculty of Engineering | 36 | [5 empty] | 5 | 27 | 4 | - |  | 0
| Construction of Upper Floor & Completion of Balance Work of the Drawing Office II (DO II), Faculty of Engineering | 32.1 | 2015.11.02 | 2016.08.01 | 32% | 40% | 10.23 | 20 | 12 | 0 | - |  | 0
| Master Plan development for the Faculty of Agriculture - Phase II | 383.8 | 2015.12.07 | 2017.12.06 | 18% | - | 68.46 | 65 | 243.3 | 39 | - |  | 0
| No. of Projects 14 | 3430.56 |  |  |  |  | 1503.22 | 578 | 1121.4 | 501.6 | 18 |  |  | #REF! | 2150.12
#REF!
Cabinet Approved Projects to be Implemented
| Geology Building - Stage II | 165.75 | - | - | - | - | 0 | 51 | 97.8 | 17 | - |  | 0
| Construction of Hockey & athletic pavilion for physical Education Dpt. | 30.6 | - | - | - | - | 0 | 0 | 26 | 4 | - |  | 0
| Construction of Convocation Hall | 328 | - | - | - | - | 0 | 15 | 280 | 33 | - |  | 0
| Postgraduate school of Advanced Medical Science | 4144.9 | - | - | - | - | 0 | - | 124.3 | 2486.9 | 415 | Cabinet approved on 2015.01.05 | -
| Construction of a Building for the Department of Geography Faculty of Arts | 95.23 | - | - | - | - |  |  | 29 | 56.2 | 10 | Cabinet approved on 2016.06.22 | -
| Extension to the Mechanical Engineering | 144.48 | - | - | - | - | - | 5 | 81.2 | 9 | - | Cabinet approved on 2016.06.22 | -
| Building for the Computing Centre, Engineering Mathematics. Postgraduate & Engineering | 353.2 | - | - | - | - | - | 5 | 106 | 207.2 | 35 | Cabinet approved on 2016.06.22 | -
| Improvement of Student Quality/ Services, Employability,Student Centered Learning & Librarary Facilities & Strengthening Research Facilities at the Postgraduate Institute of Science | 140.1 | - | - | - | - | - | 3 | 42 | 81 | 14 | Cabinet approved on 2016.06.22 | -
| No. of Projects 08 | 4764.48 |  |  |  |  | 0 | 66 | 786.3 | 2894.3 | 425 |  | 0
Pending Cabinet Approval/ NPD Approved
| Rehabilitation of the water supply system | 212.03 | - | - | - | - | - | - | - | 63.609 | 84.812 |  | -
| Clinical Research & Service Lab., Faculty of Medicine | 50.8 | - | - | - | - | - | - | - | 15.24 | 20.32 |  | -
| Construction of New Building Complex for Faculty of Arts | 488.78 | - | - | - | - | - | - | - | 146.634 | 195.512 |  | -
| Proposed Extension to Farm Animal Production and Health Faculty of Vet Medicine & Animal Science | 126 | - | - | - | - | - | - | - | 37.8 | 50.4 |  | -
| Proposed Building Extension to the Dept. of Production Engineering, Faculty of Engineering | 41.8 | - | - | - | - | - | - | - | 12.54 | 16.72 |  | -
| Reactivating the unfinished section of the New Building of the Dept. of Electrical & Electronic Engineering | 82 | - | - | - | - | - | - | - | 24.6 | 32.8 |  | -
| Construction of New Building for the Centre for research in oral cancer , Faculty of Dental Science | 48.78 | - | - | - | - | - | - | - | 14.634 | 19.512 | NPD Approved on 2016.05.27 | -
| Proposed extension to the MainLibrary | 302.43 | - | - | - | - | - | - | - | 90.729 | 120.972 | NPD Approved on 2016.05.31 | -
| No. of Projects 08 | 6610.4 | 0 | 0 | 0 | 0 | 0 | 74 | 934.3 | 3588.286 | 1015.048 |  | 0
| Total Allocation | 14805.44 | 0 | 0 | 0 | 0 | 1503.22 | 718 | 2842 | 6984.186 | 1458.048 |  |  | 13610.12 | 16587.926 | 3693.048
#REF!
University of Colombo
Construction / Development Projects - Continuation
Building complex at Maradana road (Pre Clinical Building)
| - S II | 840 | 2014.02.07 | 2016.04.29 | 57% | 79% | 478.6 | 219 | 21 | - | 0 |  | 0
| Extension to the Existing Building of Faculty of Education | 128.3 | 2015.01.28 | 2016.04.09 | 96% | 100% | 123.22 | 48 | 3.2 | - | 0 |  | 0
| Extension to the East Wing Building, Faculty of Management & Finance | 130 | 2015.11.17 | 2017.05.16 | 38% | 33% | 49 | 50 | 3.3 | - | 0 |  | -
| 25% of the cost of th e Project of Construction of Proposes Building for Faculty of Graduate Studies | 253 | 2014.07.21 | 2015.07.21 | 63% | 75% | 160 | 45 | - | - | - |  | -
| No. of Projects 04 | 1351.3 |  |  |  |  | 810.82 | 267 | 24.2 |  | 0 |  | 0
Cabinet Approved Projects to be Implemented
| Establishment of a Student service center at the faculty of Science | 468.4 | - | - | - | - | - | 27.72 | 308 | 132.68 | - | Cabinet approved on 2016.06.22
| Information and Learning Center at the Faculty of Science | 850 | - | - | - | - | - | 47.12 | 562 | 240.88 | - | Cabinet approved on 2016.06.22
| Six Stories Building for the Department of Stastices , Faculty of Science | 485.8 | - | - | - | - | - | 19.11 | 326.7 | 140 | - | Cabinet approved on 2016.06.22
| Construction and completion of remaining stage of Pre - Clinical Department, Library and Canteen for Faculty of Medicine | 5688.44 | - | - | - | - | - | - | - | - | - | Cabinet approved on 2016.06.28
| No. of Projects 04 | 7492.64 | - | - | - | - | - | 93.95 | 1196.7 | 513.56 | 0
Pending Cabinet Approval/ NPD Approved
| Student service centre at faculty of Science Premises | [10 empty] | NPD Approved on 06/04/2016
| Stage I | 277.2 | - | - | - | - | - | 0 | 270.2 | - | - |  | 0
| Stage II | 191.1 | - | - | - | - | - | 0 | - | 186.1 | -
| Information & learning centre for the faculty of Science Premises |  | - | - | - | - | - | 0 | - |  | - | NPD Approved on 06/04/2016
| Stage I | 471.2 | - | - | - | - | - | 0 | - | 459.2 | - |  | -
| Stage II | 378.8 | - | - | - | - | - | 0 | - | - | - |  | -
| Six Stories Bilding for the Cepartment of Statistics Faculty of Science | 191.118 | - | - | - | - | - | 0 | - | - | - | NPD Approved on 6/4/2016 | -
| Extension to the west wing building of the faculty of management and Finance | 290 | - | - | - | - | - | 0 | - | - | - | NPD Approved on 27/5/2016 | -
| No. of Projects 04 | 1799.418 | 0 | 0 | 0 | 0 | 0 | 0 | 270.2 | 645.3 | 0 |  | 0
Pending NPD Approval / UGC Approved
| Project Proposal for Establishment of A Faculty of Technology | 4173.77 | [9 empty] | UGC Approved on 08.07.2016
| No. of Projects 01 | 20953.686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Allocation | 31597.044 |  |  |  |  | 810.82 | 360.95 | 1491.1 | 1158.86 | 0 | 0 | 0
University of Sri Jayewardenepura
Construction / Development Projects - Continuation
Building Programme - Faculty of Applied Sciences - Phase I
| Stage I | 363.5 |  |  | 100% | 100% | 0 | 0 | 0 | 0 | 0 |  | 0
| Stage II |  | 2013.06.15 | 2014.09.17 | 91% | 100% | 82.5 | 60 | 0 | - | 0 |  | 0
| Stage III |  | 2014.09.10 | 2015.11.24 | 50% | 60% | 42.3 | - | 0 | - | 0 |  | 0
| Building for Faculty Management Studies & Commerce – 157.5 (Balance) | 62.4 | 2015.06.29 | 2016.04.30 | 33% | 48% | 20.52 | 40 | 0 | - | 0 |  | 0
| Construction of Phase IV building for Faculty of Medical Sciences | 1587.5 | 2014.03.17 | 2016.03.16 | 59% | 77% | 936.33 | 480 | 223.9 | - | 0 |  | 0
| No. of Projects 03 | 2013.4 |  |  |  |  | 1081.65 | 580 | 223.9 | 0 | 0 |  | 0
Cabinet Approved Projects to be Implemented
| 4 Storied building for Faculty of Humanities & Social Sciences | 601 | - | - | - | - | 0 | 0 | 600 | 0 | - |  | 0
| Building programme - Phase I. Stage IV & V for the Faculty of Applied Sciences (363.5) | (Balance from Phase I) | - | - | - | - | 0 | 100 | 150 | 50 | - |  | 0
| Extension to the Administration Building of the University of Sri Jayewardenepura | 56 | - | - | - | - | 0 | 56 | 0 | 0 | - |  | 0
| Extension of Faculty of Graduate Studies | 120 | - | - | - | - | 0 | 50 | 35 | 35 | - |  | 0
| Information Technology Resource (computer Lab) - Stage V - faculty of Management Studies and Commerce | 500 | - | - | - | - | 0 | 0 | 200 | 300 | - |  | 0
| Acquisition of Methsewana Land |  | - | - | - | - | 0 | 0 | 100 | 0 | - |  | 0
| Acquisition of Dawatagahawatta Land |  | - | - | - | - | 0 | 0 | 400 | 0 | - |  | 0
| Building for the faculty of Technology | 2640 | - | - | - | - | 0 |  | 250 | 1500 | -
| 3 story extension to the administration building | 54.54 | - | - | - | - | 0 | - | - | - | - | Cabinet approved on 24/3/2016 | -
| No. of Projects 08 | 3971.54 | 0 | 0 | 0 | 0 | 0 | 206 | 1735 | 1885 | 0 |  | 0
Pending NPD Approvel/UGC Approved
| Wimaladharma Hostel | 156.4 | - | - | - | - | - | - | - | - | - | UGC Approved on 14/06/2016 | -
| Staff Quarters -Abeyratne mawatha, Boralesgamuwa | 125.8 | - | - | - | - | - | - | - | - | - | UGC Approved on 14/06/2016 | -
| No. of Projects 02 | 282.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| Total Allocation | 6267.14 | 0 | 0 | 0 | 0 | 1081.65 | 786 | 1958.9 | 1885 | 0
University of Kelaniya
Ongoing Construction Projects
| Five storied Building complex for Faculty of Humanities | 120 | 2013.01.02 | 2014.10.15 | 85.22% | 100% | 102.26 | 18 | - | 0 | 0 |  | 0
| Hostel Complex for 100 male & 100 female student at Faculty of Medicine | 170 | 2013.11.25 | 2015.05.25 | 66% | 99% | 112.2 | 69 | - | 0 | 0 |  | 0
| Six Storied Building complex for the Faculty of Science | 345 | 2014.09.23 | 2016.03.24 | 39% | 52% | 153 | 257 | - | 0 | 0 |  | 0
| Building for the Faculty of Social Sciences - Stage II | 25 | 2013.10.01 | 2015.7.15 | 86% | 100% | 21.46 | 28 | - | 0 | 0 |  | 0
| Building for the Faculty of Social Sciences - Stage III | 19 | 2014.09.15 | 2015.05.15 | 62% | 100% | 11.72 |  | - | 0 | 0 |  | 0
| Building for the Faculty of Commerce & Management | 25 | 2013.08.05 | 2014.08.05 | 100% | 100% | 25.26 | 3 | - | 0 | 0 |  | 0
| Multi purpose Building for the University of Kelaniya | 75 | 2014.05.16 | 2015.12.30 | 95% | 100% | 71.47 | 17 | - | 0 | 0 |  | 0
| Building Complex for the Information and Technology Centre | 183 | 2014.12.24 | 2016.06.25 | 19.13% | 0 | 35.1 | 100 | - | 0 | 0 |  | 0
| Building Complex (ICT) for the Dept. of Industrial Management | 500 | 2015.12.28 | 2018.06.28 | 19% | 0 | 95.48 | 150 | 150 | 100 | - |  | 0
| Multipurpose Building - Faculty of Medicine | 322 | - | - | - | - | 0.18 | 16 | 130 | 142 | - |  | 0
| No. of Projects 10 | 1784 |  |  |  |  | 628.13 | 658 | 280 | 242 | 0 |  | 0
Cabinet Approved Projects to be Implemented
| Centre for Children with Development Disabilities (GOSL=10, Other=15.8) | 25.8 | - | - | - | - | 0 | 0 | 15 | 0 | - | Cabinet approved on 2016.04.05 | -
| Construction of 3rd and 4th floor in the block B in building complex for the Technology Degree programme | 110 | - | - | - | - | - | 22 | 88 | - | - | Cabinet approved on 22.06.2016 | -
| No. of Projects 02 | 135.8 | 0 | 0 |  | 0 | 0 | 22 | 103 | 0 | 0
Pending Cabinet Approval/ NPD Approved
| New Lecture Theatre Complex Faculty of Science | 500 | - | - | - | - | 0 | 0 | 315 | 185 | - | NPD Approved on 6/4/2016 | 0
| Building Complex for the Faculty of Engineering | - | - | - | - | - | - | 0 | 250 | 250 | - |  | -
| No. of Projects 02 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 565 | 435 | 0 |  | 0
| Total Allocation | 2419.8 | 0 | 0 | 0 | 0 | 628.13 | 680 | 948 | 677 | 0
University of Moratuwa
Ongoing Construction Projects
Faculty of Information Technology (Rs.523mn) -
| Stage II | 205 | 2014-05-08 | 30/4/2016 | 73% | 100% | 149.54 | 60 | 8 | - | 0 |  | 0
| Faculty of Architecture (490 M) | - | - | - | - | - | - | 23 | 0 | - | 0 |  | 0
| Phase II - Dept. of Town & Country Planning | 140 | 27/9/2012 | 24/7/2013 | 69% | 100% | 96.55 | 45 | 0 | - | 0 |  | 0
| Phase III - Dept. of Integrated Design | 110 | 2014-08-07 | 31/7/2016 | 43% | 95% | 47.1 | 50 | 0 | - | 0 |  | 0
| Phase IV - Dept. of Architecture | 150 | 2014-09-05 | 31/5/2016 | 51% | 97% | 75.88 | 15 | 0 | - | 0 |  | 0
| Dept. of Transport & Logistics Management | 148.2 | 14/5/2012 | 2014-11-06 | 95% | 100% | 140.39 | 120 | 0 | - | 0 |  | 0
| Extension to Administration building | 282 | 2013-05-12 | 31/5/2016 | 53% | 90% | 148.22 | 19 | 0 | - | 0 |  | 0
| Student Centre & Canteen Extension | 57 | 2014-12-08 | 31/7/2015 | 79% | 100% | 45.28 | 80 | 0 | - | 0 |  | 0
| Multipurpose Building for Faculty of Engineering | 184 | 25/8/2014 | 31/5/2016 | 66% | 83% | 122.35 | 70 | 0 | - | 0 |  | 0
| Lecture Room building for Faculty of Architecture | 164 | 25/8/2014 | 31/5/2016 | 59% | 83% | 96.65 | 13 | 0 | - | 0 |  | 0
| Balance work for the Dept. of Textile & Clothing | 27 | 18/3/2015 | 30/4/2016 | 95% | 100% | 25.78 | 16 | 0 | - | 0 |  | 0
| Advanced Bitumen testing & accelerated payment testing laboratory - Phase II (Highway Materials testing Laboratory - Phase II/ Heavy Vehicle Bitumen Testing Laboratory) (GOSL-18.1, Other-4) | 23.77 | 18.03.2015 | 20.06.2016 | 33% | 52% | 7.88 | 16 | 1 | 0
| No. of Projects 12 | 1490.97 |  |  |  |  | 955.62 | 527 | 9 | 0 | 0 |  | 0
Cabinet Approved Projects to be implemented
| Building complex for the Dept of Material Science & Engineering | 240 | - | - | - | - | 0 | 5 | 230 | 10 | - | Cabinet approved on 6/6/2016 | 0
| Hostel Facilities for 400 students | 194 | - | - | - | - | 0 | 15 | 133 | 8 | - |  | 0
| Faculty of Architecture - Phase V (Storm water collection & disposal system & sewage & waste water collection, treatment & disposal) | 17 | - | - | - | - | 0 | 17 | - | 0 | - |  | 0
| New building for Dept. of Building Economies | 75 | - | - | - | - | 0 | 15 | 60 | - | - |  | 0
| Proposed Health Centre | 330 | - | - | - | - | 0 | - | - | 178 | -
| Proposed building for Outreach centre for University of Moratuwa at Kolombage Mawatha, Colombo1 | 90 | - | - | - | - | 0 | - | - | 55 | -
| International House | 135 | - | - | - | - | 0 | - | - | 88 | -
| Extension to the existing single storey building of the Dept. of Textile & Clothing Technology | 307 | - | - | - | - | 0 | - | 72 | 140 | - | Cabinet approved on 24/3/2016
| No. of Projects 08 | 1388 | 0 | 0 | 0 | 0 | 0 | 52 | 495 | 479 | 0 |  | 0
Pending NPD Approval
| Proposed Building for Dept. of Mechanical Engineering | 247 | - | - | - | - | 0 | - | 127 | 92 | - |  | 0
| No. of Projects 01 | 247 | 0 | 0 | 0 | 0 | 0 | 0 | 127 | 92 | 0 |  | 0
| Total Allocation | 3125.97 |  |  |  |  | 955.62 | 579 | 631 | 571 | 0
University of Ruhuna
Ongoing Construction Projects
| Building for Department of Computer Science & Computer Unit - Stage I, Stage II | 291 | 2013.03.27 | 2014.09.17 | 91% | 100% | 263.72 | 50 | - | - |  |  | 0
| Building complex for the Faculty of Management & Fin. | 331.2 | 2013.09.25 | 2014.12.18 | 68% | 93% | 225.99 | 104.4 | 0 | - | 0 |  | 0
| Building for Library at Faculty of Engineering, Hapugalla | 128.6 | 2013.05.28 | 2014.10.21 | 79% | 100% | 101.8 | 25 | 0 | - | 0 |  | 0
| Construction and Completion of Housing Units for Senior Academic Staff, University of Ruhuna, Wellamadama, Matara | 19.5 | 2014.12.10 | 2015.06.07 | 84% | 100% | 80.69 | 40 | 0 | - | 0 |  | 0
| Construction and Completion of Housing Units for Administrative & Finance Staff, University of Ruhuna, Wellamadama, Matara | 19 | 2014.06.23 | 2015.02.15 |  |  |  |  | 0 | - | 0 |  | 0
| Construction and Completion of Housing Units for Senior Academic Staff, University of Ruhuna, Wellamadama, Matara | 19.25 | 2014.06.23 | 2015.02.28 |  |  |  |  | 0 | - | 0 |  | 0
| Construction and Completion of Housing Unit (Block 01) for Senior Academic Staff, Faculty of Engineering, University of Ruhuna, Hapugala, Galle | 19.5 | 2014.12.10 | 2015.06.07 |  |  |  |  | 0 | - | 0 |  | 0
| Construction and Completion of Housing Unit (Block 02) for Senior Academic Staff, Faculty of Engineering, University of Ruhuna, Hapugala, Galle | 19 | 2014.12.10 | 2015.06.07 |  |  |  |  | 0 | - | 0 |  | 0
| Construction and Completion of proposed Drawing office, lecture room & Auditorium complex (stage II) for faculty of Engineering, Hapugalla | 41.9 |  |  | 105.3% | 0 | 44.11 | 0 | 0 | - | 0 |  | 0
| New student canteen for 1000 students - Faculty of Agriculture | 19.5 | 2015.08.17 | 2016.02.12 | 58% | 100% | 11.26 | 11 | 0 | - | 0 |  | 0
| New student common room for 1000 students - Faculty of Agriculture | 19.5 | 2015.08.17 | 2016.02.12 | 78% | 100% | 15.23 | 13 | 0 | - | 0 |  | 0
| Canteen with a Communication Centre in the Premises of the Faculty of Science | 19.8 | 2015.08.17 | 2016.02.12 | 55% | 100% | 10.87 | 15 | 0 | - | 0 |  | 0
| Examination Hall Building, Faculty of Humanities & Social Sciences | [8 empty] | -
| - P I | 72 | 2011.09.01 | 2013.06.17 | 100% | 100% |  | 19 | 0 | - | 0 |  | 0
| - P II |  | 2014.07.24 | 2014.11.24 | 80% | 100% | 17.02 | 10 |  | -
| Construction of Three Building Blocks for the Faculty of Fisheries & Marine Science | 694.4 | 2015.05.05 | 2016.11.22 | 31% | 35% | 218.56 | 140 | 272 | - | 0
| Small Development Project grant assistance by the Government of India for the establishment of Rabindranath Tagore Memorial Auditorium at the University of Ruhuna, Matara (336.6) | 341.6 | 2016.05.16 | 2017.11.16 | 75% | 4% | 8.93 | 36.6 | 50 | 0 |  | * 300mn is doneted by Governement of India
| No. of Projects 15 | 2055.75 |  |  |  |  | 998.18 | 464 | 322 | 0 | 0
Cabinet Approved Projects to be Implemented
| Boundary Wall- Faculty of Engineering | 9.6 | - | - | - | - | - | 30 | - | - | - |  | -
| No. of Projects 01 | 9.6 | [5 empty] | 30 | 0 | 0 | 0
Pending Cabinet Approval/ NPD Approved
| Playground Improvement Project | 341.6 |  |  |  |  | 0 | 0 | 200 | 141.6 |  | NPD approved on 12/1/2015 | 0
| Construction of two story building as an extension to the existing library building to provide self learning spaces, reading spaces , reading rooms & space for legal deposit collection | 126.32 | [9 empty] | NPD approved on 31/5/2016
| No. of Projects 02 | 467.92 |  |  |  |  | 0 | 0 | 200 | 141.6 | 0
| Total Allocation | 2533.27 | 0 | 0 | 0 | 0 | 998.18 | 494 | 522 | 141.6 | 0
University of Jaffna
Ongoing Construction Projects
| Arts Building (Block) | 120 | 1981 | 2011 | 99% | 100% | 118.21 | 0.5 | 0 | 0 | - |  | 0
| Faculty of Agriculture - Kilinochchi | 393.8 | 2013 | 2015 | 87% | 88% | 341.72 | 10 | 0 | 0 | - |  | 0
| Building Complex for the Faculty of Management Studies and Commerce | 400 | 2009 | 2013 | 45% | 52% | 181.28 | 40 | 50 | 50 | - |  | 0
| Siddha Medicine Five Storied Building | 109.5 | 2012 | 2015 | 61% | 95% | 67.27 | 15 | 20 | 0 | - |  | 0
| Supply, Installation & Commissioning of Passenger lifts (02 Nos) and related civil works | 15.7 | 2012 | 2013 | 100% | 100% | 15.7 | 0 | 0 | 0 | - |  | 0
| Faculty of Engineering | 2437 | 2013 | 2017 | 34% | 60% | 836.33 | 300 | 700 | 600 | - |  | 0
| Natural Science Block - Faculty of Science - Stage II Phase 5 | 53 | 2014 | 2015 | 68% | 100% | 36.21 | 15 | 0 | 0 | - |  | 0
| Building Complex for the Faculty of Graduate Studies | 48 | 2014 | 2015 | 65% | 95% | 31.15 | 15 | 0 | 0 | - |  | 0
| No. of Projects 08 | 3577 |  |  |  |  | 1627.87 | 395.5 | 770 | 650 | 0 |  | 0
Cumulative Expenditure id higher than the TEC
Cabinet Approved Projects to be Implemented
| Construction of five storied building for clinical dept. of faculty of Medicine | 190 | 2013 | 2015 | 0 | 0 | 0 | 0 | 5 | 0 | - |  | 0
| Gymnasium for the University of Jaffna | 242 | 2014 | 2016 | - | - | - | 0 | 5 | 0 | - |  | 0
| Construction of Building and other related Structures for Engineering Technology, University of Jaffna at Ariviyal Nagar , kilinochchi | 525 | - | - | - | - | - | 140 | 270 | 115 | - | Cabinet approved on 22.06.2016
| No. of Projects 03 | 432 |  |  | 0 | 0 | 0 | 0 | 10 | 0 | 0 |  | 0
Pending NPD Approval/UGC Approved
| Construction of Building and Other related structures for the department of Computer Science | 240 | [9 empty] | UGC Approved on 14/06/2016
| No. of Projects 01 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
University of Jaffna - Vavuniya Campus
Ongoing Construction Projects
| Faculty of Business Studies | 92 | 2007 | 2012 | 97% | 100% | 89.08 | 1.75 | 0 |  | 0 |  | 0
| Faculty of Applied Science | 330 | 2007 | 2013 | 51% | 44% | 167.2 | 60 | 97 |  | 0 |  | 0
| Construction of Canteen | 11 | 2014 | 2015 | 100% | 97% | 11 | 0 | 0 |  | 0 |  | 0
| Construction of Gymnasium | 13.75 | 2014 | 2016 | 80% | 100% | 11 | 2.75 | 0 |  | 0 |  | 0
| No. of Projects 04 | 446.75 |  |  |  |  | 278.28 | 64.5 | 97 | 0 | 0 | 0 | 0
Cabinet Approved Projects to be Implemented
| Construction of two story building , services & related structures for the Department of Information & Communication Technology, Faculty of Applied Sciences, Vavuniya Campus | 200 | [5 empty] | 65 | 135 |  |  | Cabinet approved on 6/4/2016
| No. of Projects 01 | 200 | 0 | 0 | 0 | 0 | 0 | 65 | 135 | 0 | 0 | 0 | 0
| Total Allocation | 4655.75 |  |  |  |  | 1906.15 | 525 | 1002 | 650 | 0
The Open University of Sri Lanka
Ongoing Construction Projects
| Construction of new IT Building | 25 | - | - | 68.8% | - | 17.2 | 8 | - | - | - |  | 0
| Three storied building for maintenance building | 15 | - | - | 70.91% | - | 10.637 | 5 | - | - | - |  | 0
| Three storied building for Matara Regional Centre | 12.8 | 2014.09.18 | 2015.04.18 |  | 100% | 0 | 20 | - | - | - |  | 0
| Construction & Completion of proposed 4th floor of faculty of Education Building | 17.3 | 2014.11.03 | 2015.08.03 |  | 30 | 0 | 30 | - | - | - |  | 0
| Construction & Completion of 2nd & 3rd floor of the Anuradhapura Regional Centre | 46.7 | 2015.03.16 | 2016.03.16 | 32% | 98% | 12.7 | 40 | - | - | - |  | 0
| Renovation of Kandy Regional Centre & new student canteen | 15 | - | - | - | - | - | 15 | - | - | -
| Renovation of Health Science department | 3.5 | - | - | - | - | - | 3.5 | - | - | -
| Establish solar power panel to reduce electricity consumption | 45 | - | - | - | - | - | 45 | - | - | -
| No. of Projects 08 | 180.3 |  |  |  |  | 40.537 | 166.5 | 0 | 0 | 0 |  | 0
Pending NPD Approval/UGC Approved
| Construction of four storied Building for Jaffna Regional Centre | 200 | - | - | - | - | - | - | - | - | - | UGC Approved on 14/06/2016 | -
| No. of Projects 01 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1
| Total Allocation | 380.3 | 0 | 0 | 0 | 0 | 40.537 | 166.5 | 0 | 0 | 0 | 0 | 0
Eastern University of Sri Lanka
Ongoing Construction Projects
| Administrative Block for Faculty of Health Care Sciences | 360 | 2014.04.28 | 2015.10.27 | 85% | 99% | 304.4 | 70 | 0 | - | 0 |  | 0
| Professorial unit - Faculty of Health care service | 299 | 2014.04.28 | 2015.10.27 | 54% | 99% | 162.8 | 70 | 0 | - | 0 |  | 0
| Construction of Building for the Auditorium Cum Lecture Hall at the Faculty of Arts & Culture | 44.6 | 2013.12.27 | 2014.6.27 | 75% | 99% | 33.2 | 10 | 0 | - | 0 |  | 0
| Building complex Zoology Dept. | 199 | 2011.12.29 | 2012.06.30 | 86.5% | 99% | 172.144 | 25 | 0 | - | 0 |  | 0
| Building Complex for Faculty of Arts & Culture | 121 | 2011.12.29 | 2013.06.30 | 83.25% | 99% | 100.734 | 22 | 0 | - | 0
| Building Complex for Library | 171 | 2011.12.29 | 2012.12.31 | 82% | 99% | 140.22 | 25 | 0 | - | 0 |  | 0
| Building Complex for Faculty of Com. & Mgt. | 230 | 2011.12.29 | 2013.06.30 | 85% | 99% | 195.1 | 30 | 0 | - | 0 |  | 0
| No. of Projects 07 | 1424.6 |  |  |  |  | 1108.598 | 252 | 0 | 0 | 0 | 0 | 0
| Required for 2015 | 745.5
| Allocation - 2015 | 227
| Carried Forward to 2016 | 518
Cabinet Approved Projects to be Implemented
| Building complex for the Faculty of Agriculture | 255 | [5 empty] | 100 |  |  | 0 |  | 0
| Building complex for the English Language Teaching Unit | 237 | 0 | 0 | 0 | 0 | 0 | 20 | 152 | 65 | 0 | Cabinet approved on 22.06.2016
| Building for Bio System Technology | 238 | 0 | 0 | 0 | 0 | 0 | 50 | 132 | 56 |  | Cabinet approved on 22.06.2016
| No. of Projects 03 | 255 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 |  | 0
Pending Cabinet Approval/ NPD Approved
| Refurbishment of Auditorium and Construction of mini gymnasium , Building complex with audio and vedeo recording cum editing facilities | 275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NPD Approved on 27/05/2016
| No. of Projects 01 | 1005 | 0 | 0 | 0 | 0 | 0 | 20 | 152 | 65 | 0 |  | 0
| Total Allocation | 2684.6 | 0 | 0 | 0 | 0 | 1108.598 | 372 | 152 | 65 | 0 |  | 0
Rajarata University of Sri Lanka
Ongoing Construction Projects
| Bdg. complex for Faculty of Mgt. | 215 | 2012.07.19 | 2014.01.24 | 95% | 100% | 204 | 5 |  | 0 | 0 |  | 0
| Hostels for 250 Students, Puliyankulama | 154 | 2013.05.07 | 2015.09.30 | 66% | 97% | 102 | 16 |  | 0 | 0 |  | 0
| Construction & Completion of building complex, Faculty of Agriculture | 143 | 2014.09.14 | 2015.12.12 | 58% | 96% | 83 | 90 |  | 0 | 0 |  | 0
| Deyata Kirula Project 2012 - Project II | 400 | 2014.12.31 | 2015.11.13 | 89% | 80% | 355 | 36 |  | 0 | 0 |  | 0
| Sports Recreation Complex - Mihintale | 42 | [5 empty] | 0 |  | 0 | 0 |  | 0
| Examination Hall - Minintale (Stage II) | 39.6 | [5 empty] | 0 |  | 0 | 0 |  | 0
| Auditorium with a Balcony of Faculty of Agriculture | 30.8 | [5 empty] | 0 |  | 0 | 0 |  | 0
| Clinical Building Complex of FMAS, Anuradhapura Stage I, II & III | 1283.647 | 2009.12.03 | 2011.12.31 | 94% | 100% | 1206 | 10 |  | 0 | 0 |  | 0
| Social Sciences Faculty Bldg. | 167 | 2012.05.02 | 2012.11.16 | 100.6% | 100% | 168 | 10 |  | 0 | 0 |  | 0
| Construction of Swimming Pool | 168 | 2015.06.09 | 2016.12.30 | 35% | 40% | 58 | 90 |  | 0 | 0 |  | 0
| Construction of Laboratory and Lecture Hall Building | 47 | 2014.05.29 | 2015.09.30 | 79% | 100% | 37 | 5 |  |  | 0
| No. of Projects 11 | 2690.047 |  |  |  |  | 2213 | 262 | 0 | 0 | 0 |  | 0
Cabinet Approved Projects to be Implemented
| Pre Clinical Building | 437 |  |  | 0 | 0 | 0 | 20 | 174.8 | 131.1 |  |  | 0
| Construction of 3 Nos of Twin Quarters for Faculty of Medical & Allied Sciences at Saliyapura | 50 |  |  | 0 | 0 | 0 | 50 |  |  | 0 | Cabinet approved on 24/3/2016
| Construction & completion of proposed Quarters complex for Deans, Registrar, Bursar, Librarian, Academic & Non academic staff | 380 |  |  | 0 | 0 | 0 | 0 | 380 |  | 0 | Cabinet approved on 24/3/2016
| Construction and Completion of proposed Building for Center for Distance and Containing (CDCE) Center | 168.5 | [5 empty] | 30 |  |  |  | Cabinet approved on 22.06.2016
| No. of Projects 04 | 1035.5 | 0 | 0 | 0 | 0 | 0 | 70 | 554.8 | 131.1 | 0 |  | 0
| Total Allocation | 3725.547 | - | - | - | - | 2213 | 332 | 554.8 | 131.1 | 0
Sabaragamuwa University of Sri Lanka
Ongoing Construction Projects
| Hostel for 240 Students - Male | 175 | 2011 | Completed 2013 | 88.35% | 100% | 155.22 | 15 | 0 | 0 | - |  | 0
| Lecture Theatre Complex - Social Science | 672.6 | 2008 | Completed 2012 | 84% | 100% | 567.27 | 5 | 0 | 0 | - |  | 0
| Play Ground | 121 | 2009 | Completed 2013 | 94.16% | 100% | 113.93 | 15 | 0 | 0 | - |  | 0
| Applied Science Building | 296 | 2010 | Completed 2013 | 85% | 100% | 268.7 | 15 | 0 | 0 | - |  | 0
| Geomatics Faculty Building | 261.3 | 2011 | Completed 2013 | 92% | 100% | 240.8 | 10 | 0 | 0 | - |  | 0
| Mini Constructions | 18 | - | - | 0 | - | 0 | 0 | 0 | 0 | - |  | -
| Administrative Building | 60 | - | - | 2% | - | 1.49 | 40 | 21 | 24 | - |  | 0
| Geomatics Building - Stage II | 173.2 | - | - | - | - | 0 | 60 | 60.62 | 69.28 | - |  | 0
| No. of Projects 08 | 1777.1 |  |  |  |  | 1347.41 | 160 | 81.62 | 93.28 |  |  | 0
Cabinet Approved Projects to be Implemented
| Students Cafeterias - 2 Nos | 80.07 | - | - | - | - | - | 50 | 0 | 0 | - |  | -
| IT Centre | 121 | - | - | - | - | 0 | 0 | 66.6 | 24.2 | - |  | 0
| Inner Road | 126 | - | - | - | - | 0 | 0 | 25.2 | 31.5 | - |  | 0
| Basic facilities for ICC hostel Complex (New) | 37.5 | - | - | - | - | - | 37.5 | 0 | - | - |  | -
| No. of Projects 04 | 364.57 |  |  |  |  | 0 | 87.5 | 91.8 | 55.7 |  |  | 0
NPD Approved/ Pending Cabinet Approvel
| Construction of a new Gymnasium Complex and Obtaininf Motor Vehicle | 337.5 | [9 empty] | Approved on 6/4/2016
| Construction of a new building complex for the university library phase I | 371.83 | [9 empty] | NPD Approved on 31.05.2016
| No. of Projects 02 | 709.33 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0
Pending NPD Approval/UGC Approved
| Library Building | 350 |  |  |  |  | 0 | 0 | 120 | 80 |  |  | 0
| Staff Quarters | 400 |  |  |  |  | 0 | 0 | 40 | 80
| Mini Hotel | 50 |  |  |  |  | 0 | 0 | 40 | 10
| Applied Sciences Stage II | 400 |  |  |  |  | 0 | 0 | 56.5 | 113
| Management Stage II | 350 |  |  |  |  | 0 | 0 | 60 | 120
| Summer Huts 15 | 7.5 | [6 empty] | 7.5 | 0
| Indoor Stadium | 450 | [6 empty] | 45 | 90
| Building complex of the Faculty of Social Sciences S I, P II | 500 | [6 empty] | 50 | 100
| No. of Projects 09 | 2507.5 | 0 | 0 | 0 | 0 | 0 | 0 | 419 | 593 | 0 |  | 0
| Total Allocation | 5358.5 | 0 | 0 | 0 | 0 | 1347.41 | 247.5 | 592.42 | 741.98 | 0
South Eastern University of Sri Lanka
Ongoing Construction Projects
| Building Complex for Students Hostel & Staff Quarters at the Faculty of Applied Sciences | 149 | 2011.11.01 | 2015.12.31 | 47.2% | 95% | 70.3 | 37 |  | 0 | 0 |  | 0
| Building Complex for Faculty Management & Commerce | 160 | 2010.07.01 | 2014.02.15 | 96% | 100% | 153.2 | 2 |  | 0 | 0 |  | 0
| Building Complex for Main Library | 200 | 2010.05.10 | 2014.02.15 | 101% | 100% | 201.3 | 10 |  | 0 | 0 |  | 0
| Building Complex for Faculty of Applied Sciences | 170 | 2011.10.31 | 2014.02.15 | 80% | 100% | 136.1 | 33 |  | 0 | 0 |  | 0
| No. of Projects 04 | 679 |  |  |  |  | 560.9 | 82 | 0 | 0 | 0 | 0 | 0
| Pending Cabinet Approval/ NPD Approved | [14 empty] | 810
| Engineering Laboratory (Phase I) ** | [7 empty] | 300 |  | 0 |  | 0 |  |  | 500
| Engineering Laboratory (Phase II) ** | [7 empty] | 200 |  | 0 |  |  |  |  | 1310
| No. of Projects 02 | [6 empty] | 0 | 500 | 0 | 0 |  | 0
Pending NPD Approval/UGC Approved
| Building Cpmplex for Information Communication Technology Centre | 638.3 | [9 empty] | UGC Approved on 14/06/2016
| No. of Projects 01 | 638.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Allocation | 1317.3 | 0 | 0 | 0 | 0 | 560.9 | 82 | 500 | 0 | 0 | 0 | 0
Wayamba University of Sri Lanka
Ongoing Construction Projects
Kuliyapitiya Premises
| Health Center Stage II, Kuliyapitiya | 17.5 | 2011.10.31 | 2012.08.06 | 73.03% | 100% | 12.9 | 1.8 | 0 | 0 |  |  | 0
| Bachelor Academic Staff Quarters,Kuliyapitiya | 49 | 2011.10.31 | 2016.06.30 | 37% | 85% | 18.3 | 10 |  |  |  |  | 0
| Faculty Building Stage I, FBSF, Kuliyapitiya | 165 | 2011.04.06 | 2012.06.06 | 71% | 100% | 116.9 | 7.4 | 0 | 0 |  |  | 0
| Planting of Grass and other Improvements of the Play Ground, Kuliyapitiya | 50 | 2012.10.18 | 2016.03.21 | 60% | 95% | 30.08 | 28 | 0 | 0 |  |  | 0
| Canteen Stage I & Stage II, Kuliyapitiya | 45 | 2014.08.18 | 2015.08.15 | 75% | 98% | 34.12 | 15.5 |  | 0 |  |  | 0
| Faculty of Applied Sciences Stage III (Final), Kuliyapitiya | 367 | 2014.08.29 | 2016.08.30 | 39% | 70% | 145.1 | 126 | 125 | 0 |  |  | 0
| Admin Building Stage II, Kuliyapitiya | 100 | 2014.09.27 | 2016.03.27 | 16% | 40% | 16 | 21.56 | 38 | 2 |  |  | 0
| Hostel Stage IV - Kuliyapitiya | 69 | [6 empty] | 0 | 0 |  |  | 0
| Gymnasium | 250 | 2013.09.16 | 2014.02.15 | 46% | 100% | 115.3 | 8 | 0 | 0 |  |  | 0
| Auditorium | 250 | 2013.09.16 | 2014.02.15 | 92.36% | 100% | 230.89 | 20 | 0 | 0 |  |  | 0
| Nano - Technology Laboratory | 30 | 2013.09.16 | 2014.02.15 | 57% | 100% | 16.9 | 13 | 0 | 0 |  |  | 0
Makandura Premises
| Faculty Building Stage II, Faculty of Agriculture & Plantation Management , Makandura | 125 | 2012.08.02 | 2013.08.02 | 56% | 100% | 70.69 | 29 | 16 | 0 |  |  | 0
| Hostel Stage V, Makandura | 69 | 2013.05.02 | 2014.05.02 | 99.3% | 100% | 68.57 | 17 | 0 | 0 |  |  | 0
| Hostel Stage VI, Makandura | 69 | 2013.05.02 | 2014.05.02 | 47% | 100% | 33.1 | 14.25 | 0 | 0 |  |  | 0
| Faculty Building Stage III, (Final Stage) Faculty of Livestock, Fisheries and Nutrition, Makandura | 169.5 | 2013.10.21 | 2015.04.21 | 32% | 40% | 54.99 | 19 | 10 | 0 |  |  | 0
| Health Center Stage II, Makandura | 17.5 | 2014.01.17 | 2015.09.30 | 50% | 70% | 8.78 | 1.25 |  | 0 |  |  | 0
| Bachelor Academic Staff Quarters, Makandura | 49 | 2011.10.05 | 2013.03.12 | 65.04% | 100% | 31.87 | 0.45 | 0 | 0 |  |  | 0
| No. of Projects 17 | 1891.5 |  |  |  |  | 1004.49 | 332.21 | 189 | 2 | 0 | 0 | 0
Pending NPD Approval
| Construction of Road Stage II, Makandura * | 49 | [6 empty] | 14 |  | 0
| No. of Projects 01 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 |  | 0
| Total Allocation | 1940.5 | 0 | 0 | 0 | 0 | 1004.49 | 332.21 | 203 | 2 | 0
* Allocation for 2016 is considered under the UGC Budget
University of Visual & Performing Arts
Ongoing Construction Projects
Albert Crescent Development Project
| (a) Music Building - Stage III - Phase III | 48 | 2012.04.24 | 2013.05.21 | 42% | 75% | 20 | 160 |  |  |  |  | 0
| (b) Music Faculty Building - Stage IV | 143 | 2013.06.14 | 2014.12.31 | 92% | 100% | 132
| (c) Administration Building | 124 | 2012.12.28 | 2014.06.15 | 89.02% | 100% | 111
| Hostel for 400 Male students at Dehiwala | 205 | 2011.05.10 | 2014.09.30 | 76.5% | 100% | 157 | 50 |  |  | 0 |  | 0
| Hostel for 400 Female students at Rajagiriya | 193 | 2011.06.06 | 2014.08.30 | 81% | 100% | 156 | 40 |  |  | 0 |  | 0
| No. of Projects 03 | 713 |  |  |  |  | 576 | 250 |  | 0 | 0 |  | 0
Cabinet Approved Projects to be Implemented
| Proposed Building & landscape for Faculty of Visual Arts * | 492 |  |  |  |  | 0 |  | 196 | 196 |  | Cabinet approved on 24/3/2016
| Proposed Building for Faculty of Music & Common Facilities | 775 | [5 empty] | 37 | 517 | 221 |  | Cabinet approved on 22.06.2016
| No. of Projects 02 | 1267 | 0 | 0 | 0 | 0 | 0 | 37 | 713 | 417 | 0 |  | 0
| Total Allocation | 1980 | - | - | - | - | #REF! | 287 | 713 | 417 | 0
* Allocation for 2016 is considered under the UGC Budget
Uwa Wellassa University
Ongoing Construction Projects
Establishment of Uwa Wellassa University
Phase - I
| I. Administration Block | 350 | 03.08.2005 | 16.10.2006 | 99% | 100% | 348
| II. Lecture Hall + Lab - Block 'A' |  |  | 01.11.2006 |  | 100%
| III. Lecture Hall + Lab - Block 'B' |  |  | 11.10.2006 |  | 100%
| IV. Lecture Hall + Lab - Block 'C' |  |  | 11.10.2006 |  | 100%
| Phase - II | [11 empty] | 0
| Hostel Block No. 1 | 457 | 01.07.2006 | 30.05.2007 | 87% | 100% | 399 | 56
| Hostel Block No. 2 |  | 01.09.2006 | 31.08.2007
| Hostel Block No. 3 |  | 01.08.2006 | 30.07.2007
| Hostel Block No. 4 |  | 01.11.2006 | 31.10.2007
| Dinning & Study Hall |  | 15.05.2006 | 30.06.2006
| Kitchen for Dining & Study Hall |  | 01.08.2006 | 30.01.2007
| Metering Cubicle (Phase 1) | 8 | 31.08.2006 | 30.11.2006 | 66% | 100% | 5 | 3
| Metering Cubicle ( For Hostels) | 16 | 01.06.2007 | 30.09.2007 | 61% | 100% | 10 | -
| Water Sump & Pump House | 16 | 01.09.2006 | 31.08.2008 | 73% | 100% | 11 | -
| Landscaping - Phase - 1 Area | 36 | 01.01.2007 | 30.12.2008 | 70% | 100% | 25 | -
| Name Board and Developments at entrance | 8 | 01.07.2007 | 28.02.2008 | 35% | 100% | 3 | -
| Temporary Sports Court | 7 | 15.01.2007 | - | 70% | 100% | 5 | -
| Fiber Network (IT back-born at Phase 1 buildings) | 24 | 21.03.2013 | 21.06.2013 | 97% | 100% | 23 | 1
| Vice Chancellor's Bungalow | 32 | 08.09.2008 | 15.07.2009 | 98% | 100% | 31
| Play Ground (For 200m track) | 40 | 01.04.2007 | 30.09.2009 | 63% | 100% | 25 | 4
| Internal Road Network A, B & D | 56 | 01.03.2007 | 30.03.2009 | 66% | 100% | 36 | 12 | 8
| Lecture Hall & Lab Complex Block 'E' | [6 empty] | 170 | 110
| Lecture Hall & Lab Complex Block 'F' | 812 | 05.09.2008 | 31.08.2010 | 65% | 100% | 529
| Lecture Hall & Lab Complex Block 'D' |  | 01.01.2009 | 15.02.2010 |  | 100%
| Sewerage System |  | 27.01.2010 | 27.04.2011 |  | 100% |  | 24
| Storm Water Drainage System | 24 | [5 empty] | 16
| Library | 31 | 30.12.2009 | 30.06.2010 | 17% | 65% | 5 | 40 | 37 | 25
| Shrine Room | 102 | [5 empty] | 3 | 5 | 3
| Quarters for Deans/ Registrar/ Bursar & Course Directors | 91 | 01.12.2011 | 31.12.2012 | 77% | 100% | 70 | 20
| Staff Quarters (Studio Apartments) | 194 | 25.11.2012 | 15.12.2011 | 50% | 100% | 97 | 35 | 38 | 25
| Boundary Fence | 14 | [5 empty] | 7 | 2
| Roads and Landscaping at Phase 2 Area | 38 | 17.12.2009 | 09.03.2010 | 41% | 50% | 16 | 12 | 6 | 4
| Sports Center & Gymnasium | 117 | 30.12.2014 | 31.12.2015 | 25% | 25% | 29 | 35 | 3
| Pavilion |  | 06.08.2015 | 16.12.2015 |  | 5% |  | 0
| Health Centre, Students Council | 52 | [5 empty] | 25 | 15 | 12
| Cafeteria and Toilets | 27 | 27.08.2012 | 26.08.2013 | 103% | 100% | 28 | 2
| Maintenance section | 18 | 08.01.2014 | 08.10.2014 | 66% | 100% | 12 | 6
| Senate Building | 117 | 20.08.2013 | 31.12.2014 | 85% | 95% | 100 | 0
| Balance work Roads and Landscaping | 57 | 22.03.2014 | 22.08.2014 | 44% | 65% | 25 | 10 | 2
| Alternative Water Supply System | 36 | [5 empty] | 15 | 13 | 8
| Auditorium | 117 | [5 empty] | 50 | 40 | 27
| Fiber Network (Master network cabling of Phase – 2 | 24 | 05.02.2013 | 05.03.2013 | 5% | 100% | 1 | 1 | 3
| Waste water drainage and treatment works | 31 | 14.10.2010 | 14.12.2011 | 36% | 85% | 11 | 7 | 5
| Finishing of 200m track and turfing of Playground | 12 | 01.04.2007 | 30.09.2009 | 36% | 55% | 4 | 8
| Control & Metering Cubicle (Phase 2 buildings) | 11 | 05.09.2011 | 20.10.2012 | 64% | 100% | 7 | 4
| Staff learning unit | 88 | [5 empty] | 35 | 33 | 20
| Co-operate Relation Unit | 57 | [5 empty] | 30 | 16 | 11
| University Guest House | 12 | 05.11.2012 | 17.08.2013 | 96% | 100% | 12 | 1 | 0
| Consultancy & Other Payments | 100 | N/A | N/A | 64% |  | 64 | 10 | 16 | 10
| No. of Projects 02 | 3232 | 0 | 0 |  |  | 1931 | 352 | 145 | 0 |  |  | 0
Pending NPD Approval
| Acquisition of Land | 100 | [5 empty] | 0 | 50 | 50 |  |  | 0
| Establishment of Agriculture farm | 120 | [5 empty] | 0 | 30 | 90 |  |  | 0
| Lecture Hall Complex for new Degree Programs | 188.5 | [5 empty] | 0 | 87 | 101.5 |  |  | 0
| No. of Projects 03 | 408.5 | 0 | 0 | 0 | 0 | 0 | 0 | 167 | 241.5
| Development of University Township with Accomadation & Recreation Facilities for 1500 students | 950 | [5 empty] | 0 |  | 100 | 150
| Total Allocation | 3640.5 | 0 | 0 | 0 | 0 | 1931 | 352 | 312 | 241.5 | 0
Trincomalee Campus, Eastern University
Ongoing Construction Projects
| Bldg. Complex for the Faculty of Applied Science | 410 | 2014.09.04 | 2017.04.10 | 28% | 26% | 116 | 92 | 150 |  | 0
| Bldg. Complex for the IT Centre | 304.4 | 2014.09.04 | 2016.06.17 | 76% | 93% | 231 | 125 | 60 |  | 0
| Bldg. Complex for the Library | 326.2 | 2014.09.04 | 2016.08.18 | 50% | 68% | 162 | 100 | 100 |  | 0
| Bldg. Complex for the Canteen with Recreation Centre | 130.4 | 2014.09.04 | 2016.10.15 | 31% | 35% | 41 | 60 | 0 |  | 0
| Constrcution of Playground | 50 | 2014.04.29 | 2016.04.29 | 59% | 85% | 29.5 | 17 | 0
| No. of Projects 05 | 1221 |  |  |  |  | 579.5 | 394 | 310 |  | 0
| Total Allocation | 1221 | 0 | 0 | 0 | 0 | 579.5 | 394 | 310 | 0 | 0 | 0 | 0
| Postgraduate Institute of Medicine (PGIM) | [13 empty] | 499
Ongoing Construction Projects
| Eight storied building for Medical Education & Research Centre, University of Colombo | 169 | 2014.06.14 | 2015.12.14 | 23% | 1% | 563.32 | 0 | 0 | 0 |  |  | 0
| PGIM Rodney Street Development Project Colombo 05 - University of Colombo | 2500 | 2014.06.14 | 2015.12.14 | 81% | 100% | 137.16 | - |  |  |  |  | 0
| No. of Projects 02 | 2669 |  |  |  |  | 700.48 | 0 | 0 | 0
| Total Allocation | 2669 |  |  |  |  | 700.48 | 0 | 0 | 0 | 0
Postgraduate Institute of English (PGIE)
Ongoing Construction Projects
| PGIE Building Project | 93 | 2014.10.27 | 2016.01.16 | 71% | 85% | 66.2 | 23 | 0 | 0 | 0 |  | 0
| No. of Projects 01 | 93 |  |  |  |  | 66.2 | 23 | 0 | 0 | 0 |  | 0
| Total Allocation | 93 | [5 empty] | 23 | 0 | 0 | 0
University of Colombo School of Computing (UCSC)
Ongoing Construction Projects
| New building for lecture halls, reading rooms & multipurpose auditorium | 225.71 | 2014.10.01 | 2016.09.30 | 65% | 80% | 161.4 | 150 | 0 | 0 | 0 |  | 0
| No. of Projects 01 | 225.71 |  |  |  |  | 161.4 | 150 | 0 | 0 | 0
Pending Cabinet Approval/ NPD Approved
| Construction of Canteen Block - Phase II | 82.9 |  |  |  |  | 0 | 0 | 82.9 |  | 0 | Cabinet approved on 24/3/2016 | 0
| No. of Projects 01 | 82.9 |  |  |  |  | 0 | 0 | 82.9 | 0 | 0 |  | 0
| Total Allocation | [6 empty] | 150 | 82.9 | 0 | 0
Gampaha Wickramaarachchi Ayurveda Institute (GWAI)
Ongoing Construction Projects
| Wathupitiwala Garden | 7.2 |  |  | 0 |  | 0 | 0 | 6.7 | 0 |  |  | 0
| Admin Building | 79 | 15.05.2014 | 29.4.2016 | 62% | 85% | 41.15 | 18 | 0 | 0 |  |  | 0
| Four storied Academic Building | 134.4 | 10.09.2014 | 03.03.2016 | 25% | 25% | 11.95 | 66 | 0 | 0 |  |  | 0
| Student Centre - Stage II | 46 | 19.03.2016 | 30.05.2016 | 97% | 90% | 44.7 | 20 | 0 | 0 |  |  | 0
| Boundary Wall | 45 |  |  | 0 |  | 0 | 45 | 0 | 0 |  |  | 0
| No. of Projects 05 | 311.6 |  |  |  |  | 97.8 | 149 | 6.7 | 0 |  |  | 0
Pending NPD Approval
| Acquisition of Land * | 20 | [5 empty] | 0 | 0 | 0 |  |  | 0
| Construction of Male Hostel | 135.5 | [5 empty] | 0 | 100 | 35 |  |  | 0
| Construction of Dravyaguna Building * | 16 | [5 empty] | 0 | 0 | 0 |  |  | 0
| Eco Ayurveda & Recreation Centre - Wathupitiwala | 400 | [5 empty] | 0 | 300 | 100 |  |  | 0
| Construction of four storied Academic Building | 111 | [5 empty] | 0 | 110 | 0 |  |  | 0
| Construction of playground | 100 | [5 empty] | 0 | 100 | 0 |  |  | 0
| Academic & Non-Academic Quarters | 80 | [5 empty] | 0 | 80 | 0 |  |  | 0
| No. of Projects 07 | 862.5 |  |  |  |  | 0 | 0 | 690 | 135 |  |  | 0
| Total Allocation | 1174.1 |  |  |  |  | 97.8 | 149 | 696.7 | 135 | 0
Institute of Agro Technology and Rural Sciences
Cabinet Approved Projects to be Implemented
| Establishment of a Building Complex for Tissue Culture Laboratories , University of colombo Institute of Agro Technology and Rural Sciences (UCIARS) | 150 | [5 empty] | 10 | 140 |  |  | Cabinet approved on 22.06.2016
| No. of Projects 01 | 150 | 0 | 0 | 0 | 0 | 0 | 10 | 140 | 0 |  |  | 0
| Total Allocation | 150 | 0 | 0 | 0 | 0 | 0 | 10 | 140 | 0 | 0 | 0 | 0
* Allocation for 2016 is considered under the UGC Budget
University Grants Commission (UGC)
| Ongoing Construction Projects | [12 empty] | 3.8071
| UGC Admin Building | 75 | 2015.06.09 | 2016.06.09 | 3.811% | 15% | 19.68 | 55 |  | 0 | 0
| No. of Projects 01 | 75 |  |  |  |  | 19.68 | 55 | 0 | 0 | 0
| Total Allocation | [6 empty] | 55 | 0 | 0 | 0
Pending NPD Approval (Projects recognized by the UGC as Prioritized Projects)
University of Colombo
| Pre Clinical Building - Stage III | 5000 | 2016 | [5 empty] | 300 | 1800 | 1800
| Faculty of Management & Finance | 800 | 2016 | [5 empty] | 100 | 400 | 300
Sabaragamuwa University of Sri Lanka
| Mini Hotel | 50 | 2016 | [5 empty] | 25 | 25
Rajarata University of Sri Lanka
| Staff Quarters | 50 | 2016 | [5 empty] | 50
Wayamba University of Sri Lanka
| Construction of Road Stage II, Makandura | [7 empty] | 35
University of Visual & Performing Arts
| Proposed Building & landscape for Faculty of Visual Arts | [7 empty] | 100
Gampaha Wickramaarachchi Ayurveda Institute (GWAI)
| Acquisition of Land | [7 empty] | 20
| Construction of Dravyaguna Building | [7 empty] | 16
| No. of Projects 08 | 5900 | [6 empty] | 646 | 2225 | 2100
| Total | [6 empty] | 0 | 646 | 2225 | 2100
| Technology Stream - (Refer Table I) | [6 empty] | 0 | 1017.73 | 1180.59 | 448.49
| Total Allocation- UGC | [6 empty] | 55 | 1663.73 | 3405.59 | 2548.49
Note - Rs. 646 Mn to be retained by the UGC in order to allocate when the project is approved.
Note on B26: admin: Letter of approval sent to the uni on 18.11.2015
Note on B33: admin: Cabinet Approved on 05.01.2015
Note on B56: admin: Cabinet has granted approval & 2nd stage to be completed in 2016 Letter dated 15.12.2015
Note on B58: admin: expected to be commenced on 30th October 2015
Note on B60: only - progress review report
Note on B71: admin: UGC has allocated funds & started preliminary work.
Note on B74: admin: Same as the Science Premises
Note on B90: admin: Granted approval to enroll 50 students on 15.03.2016
Note on B101: admin: NPD Letter on 02.11.2015
Note on B106: admin: Approval Letter on 01.12.2015 - Cabinet Letter 01.11.2015
Note on B128: admin: Letter sent to the Uni on 18.11.2015
Note on B138: Has been recommended by the Cabinet in 2007, but not implemented since it is still in the designing stage.
Note on B162: admin: Approved on 06.06.2013. No cost revision letter on 15.03.2016
Note on B169: admin: NPD Approved on 04.11.2015
Note on B181: admin: submit a programme for increasing the students. Letter dated 14.03.2016
Note on B498: admin: letter of approval sent to uni on 18.11.2015
Note on C25: admin: mtp -41.2
Note on I12: admin: mtp report - 3
Note on I13: admin: mtp report 75
Note on I14: admin: as per mtp report 100
Note on I15: admin: mpt - 5
Note on I16: admin: mtp -40
Note on I17: admin: mtp-50
Note on I20: admin: 50
Note on I23: admin: mtp -100
Note on I24: admin: mtp - 25

## Summary (hidden)
Head No: 214 - UNIVERSITY GRANTS COMMISSION
Budget Estimate 2016 - Summary of Prioritized Construction Projects
Rs. Million
Name of the University & Construction Project | No. of Projects | Original / Amended TCE | Cumulative upto 31.05.2015 | Allocation 2015 | Estimated Value
[5 empty] | 2016 | 2017 | 2018
Major Summary
Ongoing Construction Projects | 131 | 33085.837 | 18012.485 | #REF! | 4765.51 | 2150.12 | 113.28
Cabinet Approved Projects to be Implemented | 31 | #REF! | #VALUE! | #REF! | #REF! | #REF! | #REF! | -501
Pending Cabinet Approval/ NPD Approved | 23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Pending NPD Approval | 21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
New | 2 | 49 | 0 | 0 | 14 | 0 | 0
Projects to be implemented by the University system as the Prioritised Projects | 4 | 5900 | 0 | 0 | 646 | 2225 | 2100
| 212 | #REF! | #VALUE! | #REF! | #REF! | #REF! | #REF! |  | #REF!
University of Peradeniya
Ongoing Construction Projects | 13 | 3430.56 | 1503.22 | 578 | 1121.4 | 501.6 | 18
Cabinet Approved Projects to be Implemented | 4 | 4764.48 | 0 | 66 | 786.3 | 2894.3 | 425
Pending Cabinet Approval/ NPD Approved | 9 | 6610.4 | 0 | 74 | 934.3 | 3588.286 | 1015.048
| 26 | 14805.44 | 1503.22 | 718 | 2842 | 6984.186 | 1458.048
University of Colombo
Ongoing Construction Projects | 2 | 1351.3 | 810.82 | #REF! | 267 | 24.2 | 0
Cabinet Approved Projects to be Implemented | 1 | 7492.64 | - | #REF! | 93.95 | 1196.7 | 0
Pending Cabinet Approval/ NPD Approved | 2 | 1799.418 | 0 | 0 | 270.2 | 645.3 | 0
| 5 | 10643.358 | 810.82 | #REF! | 631.15 | 1866.2 | 0
University of Sri Jayewardenepura
Ongoing Construction Projects | 3 | 2013.4 | 1081.65 | 580 | 223.9 | 0 | 0
Cabinet Approved Projects to be Implemented | 7 | 282.2 | 0 | 0 | 0 | 0 | 0
| 10 | 2295.6 | 1081.65 | 580 | 223.9 | 0 | 0
University of Kelaniya
Ongoing Construction Projects | 8 | 1784 | 628.13 | 658 | 280 | 242 | 0
Cabinet Approved Projects to be Implemented | 2 | 135.8 | 0 | 22 | 103 | 0 | 0
Pending Cabinet Approval/ NPD Approved | 3 | 500 | 0 | 0 | 565 | 435 | 0
| 13 | 2419.8 | 628.13 | 680 | 948 | 677 | 0
University of Moratuwa
Ongoing Construction Projects | 8 | 1490.97 | 955.62 | 527 | 9 | 0 | 0
Cabinet Approved Projects to be Implemented | 8 | 1388 | 0 | 52 | 495 | 479 | 0
Pending NPD Approval | 2 | 247 | 0 | 0 | 127 | 92 | 0
| 18 | 3125.97 | 955.62 | 579 | 631 | 571 | 0
University of Ruhuna
Ongoing Construction Projects | 14 | 2055.75 | 998.18 | 464 | 322 | 0 | 0
Cabinet Approved Projects to be Implemented (Foreign Funded) | 1 | 9.6 | 0 | 30 | #REF! | 0 | 0
Pending Cabinet Approval/ NPD Approved | 1 | 467.92 | 0 | 0 | 200 | 141.6 | 0
| 16 | 2533.27 | 998.18 | 494 | #REF! | 141.6 | 0
University of Jaffna
Ongoing Construction Projects | 8 | 3577 | 1627.87 | 395.5 | 770 | 650 | 0
Cabinet Approved Projects to be Implemented (2 Projects - Foreign Funded) | 2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
University of Jaffna - Vavuniya Campus
Ongoing Construction Projects | 4 | 200 | 0 | 65 | 135 | 0 | 0
| 4 | 200 | 0 | 65 | 135 | 0 | 0
The Open University of Sri Lanka
Ongoing Construction Projects | 8 | 180.3 | 40.537 | 166.5 | 0 | 0 | 0
| 8 | 180.3 | 40.537 | 166.5 | 0 | 0 | 0
Eastern University of Sri Lanka
Ongoing Construction Projects | 7 | 1424.6 | 1108.598 | 252 | 0 | 0 | 0
Cabinet Approved Projects to be Implemented | 1 | 255 | 0 | 100 | 0 | 0 | 0
Pending Cabinet Approval/ NPD Approved | 1 | 1005 | 0 | 20 | 152 | 65 | 0
| 9 | 2684.6 | 1108.598 | 372 | 152 | 65 | 0
Rajarata University of Sri Lanka
Ongoing Construction Projects | 7 | 2690.047 | 2213 | 262 | 0 | 0 | 0
Cabinet Approved Projects to be Implemented | 1 | 1035.5 | 0 | 70 | 554.8 | 131.1 | 0
Pending Cabinet Approval/ NPD Approved | 3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Sabaragamuwa University of Sri Lanka
Ongoing Construction Projects | 8 | 1777.1 | 1347.41 | #REF! | 160 | 81.62 | 93.28
Cabinet Approved Projects to be Implemented | 4 | 364.57 | 0 | #REF! | 87.5 | 91.8 | 55.7
Pending NPD Approval | 8 | 2507.5 | 0 | 0 | 419 | 593 | 0
| 20 | 4649.17 | 1347.41 | #REF! | 666.5 | 766.42 | 148.98
South Eastern University of Sri Lanka
Ongoing Construction Projects | 4 | 679 | 560.9 | 82 | 0 | 0 | 0
Pending Cabinet Approval/ NPD Approved | 2 | 0 | 0 | 0 | 500 | 0 | 0
| 6 | 679 | 560.9 | 82 | 500 | 0 | 0
Wayamba University of Sri Lanka
Ongoing Construction Projects | 17 | 1891.5 | 1004.49 | #REF! | 332.21 | 189 | 2
New | 2 | 49 | 0 | 0 | 14 | 0 | 0
| 19 | 1940.5 | 1004.49 | #REF! | 346.21 | 189 | 2
University of the Visual Performing Arts
Ongoing Construction Projects | 3 | 713 | 576 | #REF! | 250 | 0 | 0
Pending Cabinet Approval/ NPD Approved | 1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Pending NPD Approval | 1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Uwa Wellassa University
Ongoing Construction Projects | 2 | 3232 | 1931 | #REF! | 352 | 145 | 0
Pending NPD Approval | 3 | 408.5 | 0 | 0 | #REF! | 167 | 241.5
| 5 | 3640.5 | 1931 | #REF! | #REF! | 312 | 241.5
Trincomalee Campus - Eastern University of Sri Lanka
Ongoing Construction Projects | 5 | 1221 | 579.5 | #REF! | 394 | 310 | 0
| 5 | 1221 | 579.5 | #REF! | 394 | 310 | 0
Postgraduate Institute of Medicine (PGIM)
Ongoing Construction Projects | 2 | 2669 | 700.48 | #REF! | 0 | 0 | 0
| 2 | 2669 | 700.48 | #REF! | 0 | 0 | 0
Postgraduate Institute of English (PGIE)
Ongoing Construction Projects | 1 | 93 | 66.2 | 23 | 0 | 0 | 0
| 1 | 93 | 66.2 | 23 | 0 | 0 | 0
University of Colombo School of Computing (UCSC)
Ongoing Construction Projects | 1 | 225.71 | 161.4 | 150 | 0 | 0 | 0
Pending Cabinet Approval/ NPD Approved | 1 | 82.9 | 0 | 0 | 82.9 | 0 | 0
| 2 | 308.61 | 161.4 | 150 | 82.9 | 0 | 0
Gampaha Wickramarachchi Ayurveda Institute (GWAI)
Ongoing Construction Projects | 5 | 311.6 | 97.8 | #REF! | 149 | 6.7 | 0
Pending NPD Approval | 7 | 862.5 | 0 | #REF! | 0 | 690 | 135
| 12 | 1174.1 | 97.8 | #REF! | 149 | 696.7 | 135
University Grants Commission (UGC)
Ongoing Construction Projects | 1 | 75 | 19.68 | 55 | 0 | 0 | 0
Projects to be implemented by the University system as the Prioritised Projects | 4 | 5900 | 0 | 0 | 646 | 2225 | 2100
| 5 | 5975 | 19.68 | 55 | 646 | 2225 | 2100

## Index (hidden)
Head No: 214 - UNIVERSITY GRANTS COMMISSION
Budget Estimate 2016 - Prioritized Construction Projects
Pg No.
Summary of Three Year Projection of Cash Outflow………… | 1 - 4
University of Peradeniya…………………………………….. | 5 - 12
University of Colombo………………………………………. | 13 - 17
University of Sri Jayawardenepura…………………………… | 18 - 22
University of Kelaniya……………………………………….. | 23 - 27
University of Moratuwa……………………………………… | 28 - 35
University of Ruhuna…………………………………………. | 36 - 44
University of Jaffna…………………………………………… | 45 - 55
Open University of Sri Lanka………………………………… | 56
Eastern University of Sri Lanka………………………………. | 57 - 61
Rajarata Univerity of Sri Lanka………………………………. | 62 - 69
Sabaragamuwa University of Sri Lanka………………………. | 70 - 76
South Eastern University of Sri Lanka………………………… | 77 - 80
Wayamba University of Sri Lanka……………………………. | 81 - 91
University of Visual & Performing Arts………………………. | 92 - 96
Uwa Wellassa University…………………………………….. | 97 - 106
Trincomalee Campus, Eastern University of Sri Lanka………. | 107 - 110
Postgraduate Institute of Medicine…………………………… | 107
Postgraduate Institute of English……………………………… | 111 - 113
University of Colombo School of Computing………………… | 111 , 114
Gampaha Wickramaarachchi Ayurvedic Institute…………….. | 115 - 116
University Grants Commission……………………………….. | 118 - 119

## Sum Revised (hidden)
Head No: 214 - UNIVERSITY GRANTS COMMISSION
Three Year Financial Plan - Construction Projects of the Universities/ HEIs 2016 - 2018
Rs. Million
Name of the University/ Approval Stage of the Project | No. of Projects | Original / Amended TCE | Estimated Value
|  |  | 2016 | 2017 | 2018
Major Summary
Ongoing Construction Projects | 131 | 33085.837 | 4765.51 | 2150.12 | 113.28
Cabinet Approved Projects to be Implemented | 31 | #REF! | #REF! | #REF! | #REF!
Technology Stream Projects | 5 | 0 | 1017.73 | 1180.59 | 448.49
Projects recognized by the UGC as Prioritised Projects | 8 | 5900 | 646 | 2225 | 2100
Pending Cabinet Approval/ NPD Approved | 23 | #REF! | #REF! | #REF! | #REF!
Pending NPD Approval | 22 | #REF! | #REF! | #REF! | #REF!
| 220 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
University of Peradeniya | [6 empty] | #REF!
Ongoing Construction Projects | 13 | 3430.56 | 1121.4 | 501.6 | 18
Cabinet Approved Projects to be Implemented | 4 | 4764.48 | 786.3 | 2894.3 | 425
Pending Cabinet Approval/ NPD Approved | 9 | 6610.4 | 934.3 | 3588.286 | 1015.048
| 26 | 14805.44 | 2842 | 6984.186 | 1458.048
University of Colombo
Ongoing Construction Projects | 2 | 1351.3 | 267 | 24.2 | 0
Cabinet Approved Projects to be Implemented | 1 | 7492.64 | 93.95 | 1196.7 | 0
Pending Cabinet Approval/ NPD Approved | 2 | 1799.418 | 270.2 | 645.3 | 0
| 5 | 10643.358 | 631.15 | 1866.2 | 0
University of Sri Jayewardenepura
Ongoing Construction Projects | 3 | 2013.4 | 223.9 | 0 | 0
Cabinet Approved Projects to be Implemented | 7 | 282.2 | 0 | 0 | 0
| 10 | 2295.6 | 223.9 | 0 | 0
University of Kelaniya
Ongoing Construction Projects | 8 | 1784 | 280 | 242 | 0
Cabinet Approved Projects to be Implemented | 2 | 135.8 | 103 | 0 | 0
Pending Cabinet Approval/ NPD Approved | 3 | 500 | 565 | 435 | 0
| 13 | 2419.8 | 948 | 677 | 0
University of Moratuwa
Ongoing Construction Projects | 8 | 1490.97 | 9 | 0 | 0
Cabinet Approved Projects to be Implemented | 8 | 1388 | 495 | 479 | 0
Pending NPD Approval | 2 | 247 | 127 | 92 | 0
| 18 | 3125.97 | 631 | 571 | 0
University of Ruhuna
Ongoing Construction Projects | 14 | 2055.75 | 322 | 0 | 0
Cabinet Approved Projects to be Implemented (Foreign Funded) | 1 | 9.6 | #REF! | 0 | 0
Pending Cabinet Approval/ NPD Approved | 1 | 467.92 | 200 | 141.6 | 0
| 16 | 2533.27 | #REF! | 141.6 | 0
University of Jaffna
Ongoing Construction Projects | 8 | 3577 | 770 | 650 | 0
Cabinet Approved Projects to be Implemented (2 Projects - Foreign Funded) | 2 | #REF! | #REF! | #REF! | #REF!
| 10 | #REF! | #REF! | #REF! | #REF!
University of Jaffna - Vavuniya Campus
Ongoing Construction Projects | 4 | 200 | 135 | 0 | 0
| 4 | 200 | 135 | 0 | 0
The Open University of Sri Lanka
Ongoing Construction Projects | 8 | 180.3 | 0 | 0 | 0
| 8 | 180.3 | 0 | 0 | 0
Eastern University of Sri Lanka
Ongoing Construction Projects | 7 | 1424.6 | 0 | 0 | 0
Cabinet Approved Projects to be Implemented | 1 | 255 | 0 | 0 | 0
Pending Cabinet Approval/ NPD Approved | 1 | 1005 | 152 | 65 | 0
| 9 | 2684.6 | 152 | 65 | 0
Rajarata University of Sri Lanka
Ongoing Construction Projects | 7 | 2690.047 | 0 | 0 | 0
Cabinet Approved Projects to be Implemented | 1 | 1035.5 | 554.8 | 131.1 | 0
Pending Cabinet Approval/ NPD Approved | 3 | #REF! | #REF! | #REF! | #REF!
| 11 | #REF! | #REF! | #REF! | #REF!
Sabaragamuwa University of Sri Lanka
Ongoing Construction Projects | 8 | 1777.1 | 160 | 81.62 | 93.28
Cabinet Approved Projects to be Implemented | 4 | 364.57 | 87.5 | 91.8 | 55.7
Pending NPD Approval | 8 | 2507.5 | 419 | 593 | 0
| 20 | 4649.17 | 666.5 | 766.42 | 148.98
South Eastern University of Sri Lanka
Ongoing Construction Projects | 4 | 679 | 0 | 0 | 0
Pending Cabinet Approval/ NPD Approved | 2 | 0 | 500 | 0 | 0
| 6 | 679 | 500 | 0 | 0
Wayamba University of Sri Lanka
Ongoing Construction Projects | 17 | 1891.5 | 332.21 | 189 | 2
Pending NPD Approval | 1 | 49 | 0 | 0 | 0
| 18 | 1940.5 | 332.21 | 189 | 2
University of the Visual Performing Arts
Ongoing Construction Projects | 3 | 713 | 250 | 0 | 0
Pending Cabinet Approval/ NPD Approved | 1 | #REF! | 0 | #REF! | #REF!
Pending NPD Approval | 1 | #REF! | #REF! | #REF! | #REF!
| 5 | #REF! | #REF! | #REF! | #REF!
Uwa Wellassa University
Ongoing Construction Projects | 2 | 3232 | 352 | 145 | 0
Pending NPD Approval | 3 | 408.5 | #REF! | 167 | 241.5
| 5 | 3640.5 | #REF! | 312 | 241.5
Trincomalee Campus - Eastern University of Sri Lanka
Ongoing Construction Projects | 5 | 1221 | 394 | 310 | 0
| 5 | 1221 | 394 | 310 | 0
Postgraduate Institute of Medicine (PGIM)
Ongoing Construction Projects | 2 | 2669 | 0 | 0 | 0
| 2 | 2669 | 0 | 0 | 0
Postgraduate Institute of English (PGIE)
Ongoing Construction Projects | 1 | 93 | 0 | 0 | 0
| 1 | 93 | 0 | 0 | 0
University of Colombo School of Computing (UCSC)
Ongoing Construction Projects | 1 | 225.71 | 0 | 0 | 0
Pending Cabinet Approval/ NPD Approved | 1 | 82.9 | 82.9 | 0 | 0
| 2 | 308.61 | 82.9 | 0 | 0
Gampaha Wickramarachchi Ayurveda Institute (GWAI)
Ongoing Construction Projects | 5 | 311.6 | 149 | 6.7 | 0
Pending NPD Approval | 7 | 862.5 | 0 | 690 | 135
| 12 | 1174.1 | 149 | 696.7 | 135
University Grants Commission (UGC)
Ongoing Construction Projects | 1 | 75 | 0 | 0 | 0
Projects recognized by the UGC as Prioritised Projects | 8 | 5900 | 646 | 2225 | 2100
Technology Stream | 5 | 0 | 1017.73 | 1180.59 | 448.49
| 14 | 5975 | 1663.73 | 3405.59 | 2548.49

## Himali Ms. (hidden)
Head No: 214 - UNIVERSITY GRANTS COMMISSION
Three Year Financial Plan - Construction Projects
2016 - 2018
Rs. Million
Name of the University/ Approval Stage of the Project | No. of Projects | Original / Amended TCE | Estimated Value
|  |  | 2016 | 2017 | 2018
Major Summary
Ongoing Construction Projects | 131 | 33085.837 | 4765.51 | 2150.12 | 113.28
Cabinet Approved Projects to be Implemented | 31 | #REF! | #REF! | #REF! | #REF!
Technology Stream Projects | 5 | 0 | 1017.73 | 1180.59 | 448.49
Projects recognized by the UGC as Prioritised Projects | 8 | 5900 | 646 | 2225 | 2100
Pending Cabinet Approval/ NPD Approved | 23 | #REF! | #REF! | #REF! | #REF!
Pending NPD Approval | 22 | #REF! | #REF! | #REF! | #REF!
| 220 | #REF! | #REF! | #REF! | #REF!
University of Peradeniya
Ongoing Construction Projects | 13 | 3430.56 | 1121.4 | 501.6 | 18
Cabinet Approved Projects to be Implemented | 4 | 4764.48 | 786.3 | 2894.3 | 425
Pending Cabinet Approval/ NPD Approved | 9 | 6610.4 | 934.3 | 3588.286 | 1015.048
| 26 | 14805.44 | 2842 | 6984.186 | 1458.048
University of Colombo
Ongoing Construction Projects | 2 | 1351.3 | 267 | 24.2 | 0
Cabinet Approved Projects to be Implemented | 1 | 7492.64 | 93.95 | 1196.7 | 0
Pending Cabinet Approval/ NPD Approved | 2 | 1799.418 | 270.2 | 645.3 | 0
| 5 | 10643.358 | 631.15 | 1866.2 | 0
University of Sri Jayewardenepura
Ongoing Construction Projects | 3 | 2013.4 | 223.9 | 0 | 0
Cabinet Approved Projects to be Implemented | 7 | 282.2 | 0 | 0 | 0
| 10 | 2295.6 | 223.9 | 0 | 0
University of Kelaniya
Ongoing Construction Projects | 8 | 1784 | 280 | 242 | 0
Cabinet Approved Projects to be Implemented | 2 | 135.8 | 103 | 0 | 0
Pending Cabinet Approval/ NPD Approved | 3 | 500 | 565 | 435 | 0
| 13 | 2419.8 | 948 | 677 | 0
University of Moratuwa
Ongoing Construction Projects | 8 | 1490.97 | 9 | 0 | 0
Cabinet Approved Projects to be Implemented | 8 | 1388 | 495 | 479 | 0
Pending NPD Approval | 2 | 247 | 127 | 92 | 0
| 18 | 3125.97 | 631 | 571 | 0
University of Ruhuna
Ongoing Construction Projects | 14 | 2055.75 | 322 | 0 | 0
Cabinet Approved Projects to be Implemented (Foreign Funded) | 1 | 9.6 | #REF! | 0 | 0
Pending Cabinet Approval/ NPD Approved | 1 | 467.92 | 200 | 141.6 | 0
| 16 | 2533.27 | #REF! | 141.6 | 0
University of Jaffna
Ongoing Construction Projects | 8 | 3577 | 770 | 650 | 0
Cabinet Approved Projects to be Implemented (2 Projects - Foreign Funded) | 2 | #REF! | #REF! | #REF! | #REF!
| 10 | #REF! | #REF! | #REF! | #REF!
University of Jaffna - Vavuniya Campus
Ongoing Construction Projects | 4 | 200 | 135 | 0 | 0
| 4 | 200 | 135 | 0 | 0
The Open University of Sri Lanka
Ongoing Construction Projects | 8 | 180.3 | 0 | 0 | 0
| 8 | 180.3 | 0 | 0 | 0
Eastern University of Sri Lanka
Ongoing Construction Projects | 7 | 1424.6 | 0 | 0 | 0
Cabinet Approved Projects to be Implemented | 1 | 255 | 0 | 0 | 0
Pending Cabinet Approval/ NPD Approved | 1 | 1005 | 152 | 65 | 0
| 9 | 2684.6 | 152 | 65 | 0
Rajarata University of Sri Lanka
Ongoing Construction Projects | 7 | 2690.047 | 0 | 0 | 0
Cabinet Approved Projects to be Implemented | 1 | 1035.5 | 554.8 | 131.1 | 0
Pending Cabinet Approval/ NPD Approved | 3 | #REF! | #REF! | #REF! | #REF!
| 11 | #REF! | #REF! | #REF! | #REF!
Sabaragamuwa University of Sri Lanka
Ongoing Construction Projects | 8 | 1777.1 | 160 | 81.62 | 93.28
Cabinet Approved Projects to be Implemented | 4 | 364.57 | 87.5 | 91.8 | 55.7
Pending NPD Approval | 8 | 2507.5 | 419 | 593 | 0
| 20 | 4649.17 | 666.5 | 766.42 | 148.98
South Eastern University of Sri Lanka
Ongoing Construction Projects | 4 | 679 | 0 | 0 | 0
Pending Cabinet Approval/ NPD Approved | 2 | 0 | 500 | 0 | 0
| 6 | 679 | 500 | 0 | 0
Wayamba University of Sri Lanka
Ongoing Construction Projects | 17 | 1891.5 | 332.21 | 189 | 2
Pending NPD Approval | 1 | 49 | 0 | 0 | 0
| 18 | 1940.5 | 332.21 | 189 | 2
University of the Visual Performing Arts
Ongoing Construction Projects | 3 | 713 | 250 | 0 | 0
Pending Cabinet Approval/ NPD Approved | 1 | #REF! | 0 | #REF! | #REF!
Pending NPD Approval | 1 | #REF! | #REF! | #REF! | #REF!
| 5 | #REF! | #REF! | #REF! | #REF!
Uwa Wellassa University
Ongoing Construction Projects | 2 | 3232 | 352 | 145 | 0
Pending NPD Approval | 3 | 408.5 | #REF! | 167 | 241.5
| 5 | 3640.5 | #REF! | 312 | 241.5
Trincomalee Campus - Eastern University of Sri Lanka
Ongoing Construction Projects | 5 | 1221 | 394 | 310 | 0
| 5 | 1221 | 394 | 310 | 0
Postgraduate Institute of Medicine (PGIM)
Ongoing Construction Projects | 2 | 2669 | 0 | 0 | 0
| 2 | 2669 | 0 | 0 | 0
Postgraduate Institute of English (PGIE)
Ongoing Construction Projects | 1 | 93 | 0 | 0 | 0
| 1 | 93 | 0 | 0 | 0
University of Colombo School of Computing (UCSC)
Ongoing Construction Projects | 1 | 225.71 | 0 | 0 | 0
Pending Cabinet Approval/ NPD Approved | 1 | 82.9 | 82.9 | 0 | 0
| 2 | 308.61 | 82.9 | 0 | 0
Gampaha Wickramarachchi Ayurveda Institute (GWAI)
Ongoing Construction Projects | 5 | 311.6 | 149 | 6.7 | 0
Pending NPD Approval | 7 | 862.5 | 0 | 690 | 135
| 12 | 1174.1 | 149 | 696.7 | 135
University Grants Commission (UGC)
Ongoing Construction Projects | 1 | 75 | 0 | 0 | 0
Projects recognized by the UGC as Prioritised Projects | 8 | 5900 | 646 | 2225 | 2100
Technology Stream | 5 | 0 | 1017.73 | 1180.59 | 448.49
| 14 | 5975 | 1663.73 | 3405.59 | 2548.49

## Meet Index (hidden)
Head No: 214 - UNIVERSITY GRANTS COMMISSION
Three Year Financial Plan - Construction Projects
2016 - 2018
Pg No.
Summary - Three Year Financial Plan - Construction Projects…………………………………………………….. | 1 - 4
University of Peradeniya…………………………………….. | 5 - 10
University of Colombo………………………………………. | 11 - 12
University of Sri Jayawardenepura…………………………… | 13 - 16
University of Kelaniya……………………………………….. | 17 - 20
University of Moratuwa……………………………………… | 21 - 26
University of Ruhuna…………………………………………. | 27 - 31
University of Jaffna…………………………………………… | 32 - 40
Eastern University of Sri Lanka………………………………. | 41 - 44
Rajarata Univerity of Sri Lanka………………………………. | 45 - 50
Sabaragamuwa University of Sri Lanka………………………. | 51 - 55
South Eastern University of Sri Lanka………………………… | 56 - 58
Wayamba University of Sri Lanka……………………………. | 59 - 67
University of Visual & Performing Arts………………………. | 68 - 71
Uwa Wellassa University…………………………………….. | 72 - 78
Trincomalee Campus, Eastern University of Sri Lanka………. | 79 - 81
University of Colombo School of Computing………………… | 82
Gampaha Wickramaarachchi Ayurvedic Institute…………….. | 83 - 84

## Suranji Ms (hidden)
Head No: 214 - UNIVERSITY GRANTS COMMISSION
Objective 1: Widen participation & equitable access to higher education
Objective 2: Improve physical & aesthetic environment & stakeholder satisfaction
| Programme: Construction Projects | [10 empty] | Rs. Million
| Name of the University & Construction Project | Original / Amended TCE | Implementation Period |  | Progress as at 31.07.2015 |  | Cumulative upto 31.07.2015 | Allocation 2015 | Estimated Value |  |  | Project KPI
|  |  | Date of Start | Expected date of Completion | Financial (%) | Physical (%) |  |  | 2016 | 2017 | 2018
University of Peradeniya
Construction / Development Projects - Continuation
| Faculty of Medicine - Stage I | 280 | 2005.08.31 | 2008.08.30 | 78% | 100% | 241.8 | 0.4 | 15 | 0 | 0 | 0
| Building for the Dept. of Management Studies | 78.5 | [6 empty] | 3 | 0 | 0 | 0
| Building for the Faculty of Allied Health Science - P I , P II | 157 | 2011.12.15 | 2013.06.14 | 51% | 60% | 22.1 | 21.1 | 75 | 50 | 0 | 0
| Construction of Para Clinical Building - Stage II | 794.58 | 2013.07.15 | 2015.07.14 | 30% | 45% | 183.8 | 50 | 100 | 300 | 0 | 0
| Expansion of Student Hostel at Sarasavi Uyana | 89.53 | 2013.10.28 | 2014.10.27 | 68% | 93% | 53.6 | 24.2 | 5 | 0 | 0 | 0
| Construction of Chemical Engineering Building - Stage II | 85.71 | 2014.07.11 | 2015.07.10 | 42% | 55% | 36.1 | 49.4 | 40 | 0 | 0 | 0
| Proposed Extension to the Surgical Ward Faculty of Medicine | 81.25 | 2014.07.25 | 2016.07.24 | 26% | 25% | 21.1 | 0.3 | 50 | 0 | 0 | 0
| Building for the Dept. of Management Studies | [10 empty] | 0
| Stage I Phase III | 93.1 |  |  | 50% | 100% |  | 55.8 | 0 | 0 | 0 | 0
| Stage II |  | 2014.07.15 | 2015.07.14 | 40% | 60% | 37.1 |  | 50 | 0 | 0 | 0
| Construction of Five storied Building for Faculty of Dental Science | 209.59 | 2014.08.15 | 2016.02.19 | 24% | 20% | 49.2 | 0.3 | 125 | 50 | 0 | 0
| Master plan development Faculty of Agriculture - Phase I | 930.4 | 2014.08.29 | 2017.02.28 | 29% | 30% | 255.3 | 2 | 300 | 300 | 0 | 0
| Building for the Dept. of Statistical and Computer Science | 179 | 2014 June 27 awarded |  | 0 | 0 | 0 | 0 | 100 | 75 | 4 | 0
| Construction of Faculty Center - Faculty of Engineering | 36 | [6 empty] | 25 | 5 | 0 | 0
| Construction of Upper Floor & Completion of Balance Work of the Drawing Office II (DO II), Faculty of Engineering | 41.2 | [6 empty] | 25 | 18 | 0 | 0
| No. of Projects 13 | 3055.86 |  |  |  |  | 900.1 | 203.5 | 913 | 798 | 4
Cabinet Approved Projects to be Implemented
| Master Plan development for the Faculty of Agriculture - Phase II | 383.8 |  |  |  |  | 0 | 0 | 0 | 300 | 50 | 0
| Geology Building - Stage II | 165.75 |  |  |  |  | 0 | 0 | 0 | 150 | 15 | 0
| Construction of Hockey & athletic pavilion for physical Education Dpt. | 30.6 |  |  |  |  | 0 | 0 | 0 | 30 | 0 | 0
| Construction of Convocation Hall | 328 |  |  |  |  | 0 | 0 | 0 | 200 | 100 | 0
| No. of Projects 04 | 908.15 |  |  |  |  | 0 | 0 | 0 | 680 | 165 | 0
Pending Cabinet Approval/ NPD Approved
| Building for the Computing Centre, Engineering Mathematics. Postgraduate & Engineering | 353.2 |  |  |  |  | 0 | 20 | 0 | 300 | 50 | Allocation for Year 2015 has been used for other projects.
| Extension to the Mechanical Engineering | 144.77 |  |  |  |  | 0 | 10 | 0 | 125 | 15
| Postgraduate school of Advanced Medical Science | 4144.9 |  |  |  |  | 0 | 100 | 0 | 100 | 200
| Rehabilitation of the water supply system | 212.03 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| Clinical Research & Service Lab., Faculty of Medicine | 50.8 |  |  |  |  | 0 | 0 | 0 | 95 | 0 | 0
| Construction of New Building Complex for Faculty of Arts | 488.78 | [6 empty] | 0 | 400 | 75
| Proposed Extension to Farm Animal Production and Health Faculty of Vet Medicine & Animal Science | 126 | [6 empty] | 0 | 125 | 0
| Proposed Building Extension to the Dept. of Production Engineering, Faculty of Engineering | 41.8 | [6 empty] | 0 | 42 | 0
| Reactivating the unfinished section of the New Building of the Dept. of Electrical & Electronic Engineering | 82 | [6 empty] | 0 | 80 | 0
| No. of Projects 09 | 5644.28 |  |  |  |  | 0 | 130 | 0 | 1267 | 340 | 0
| Total Allocation | [6 empty] | 333.5 | 913 | 2745 | 509
University of Colombo
Construction / Development Projects - Continuation
1. | Building complex at Maradana road (Pre Clinical Building)
| - S II | 842 |  |  | 36.7% | 8% | 309 | 129 | 410 | 21 | 0 | 0
2. | Extension to the Existing Building of Faculty of Education | 128.3 | 2015.12.01 | 2016.01.11 | 39% | 42% | 50 | 75 | 48 | 3.2 | 0 | 0
| No. of Projects 02 | 970.3 |  |  |  |  | 359 | 204 | 458 | 24.2 | 0 | 0
Cabinet Approved Projects to be Implemented
1. | Extension to the East Wing Building, Faculty of Management & Finance | 130 |  |  |  |  | 0 | 50 | 75.8 | 3.3 | 0 | 0
| No. of Projects 01 | 130 | 0 | 0 | 0 | 0 | 0 | 50 | 75.8 | 3.3 | 0 | 0
Pending Cabinet Approval/ NPD Approved
1. | Student service centre at faculty of Science Premises
| Stage I | 277.2 |  |  |  |  | 0 | 0 |  | 270.2 |  | 0
| Stage II | 191.1 |  |  |  |  | 0 | 0 |  |  | 186.1
2. | Information & learning centre for the faculty of Science Premises
| Stage I | 471.2 |  |  |  |  | 0 | 0 |  |  | 459.2
| No. of Projects 02 | 939.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270.2 | 645.3 | 0
| Total Allocation | [6 empty] | 254 | 533.8 | 297.7 | 645.3
University of Sri Jayewardenepura
Construction / Development Projects - Continuation
Building Programme - Faculty of Applied Sciences - Phase I
| Stage I | 363.5 |  |  | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0
| Stage II |  | 2013.06.15 | 2014.09.17 | 83% | 99% | 115.3 | 100 | 16.49 | 0 | 0 | 0
| Stage III |  | 2014.09.10 | 2015.11.24 | 50% | 60% | 42.3 | 0 |  | 0 | 0 | 0
| Building for Faculty Management Studies & Commerce – 157.5 (Balance) | 62.4 | 2015.07.01 | 2016.04.30 | 14% | 2% | 9.1 | 50 | 50 | 0 | 0 | 0
| Construction of Phase IV building for Faculty of Medical Sciences | 1599.4 | 2014.03.17 | 2016.03.16 | 42% | 59% | 663 | 240 | 700 | 223.9 | 0 | 0
| No. of Projects 03 | 2025.3 |  |  |  |  | 829.7 | 390 | 766.49 | 223.9 | 0 | 0
Cabinet Approved Projects to be Implemented
| 4 Storied building for Faculty of Humanities & Social Sciences | 601 |  |  |  |  | 0 |  | 0 | 600 | 0 | 0
| Building programme - Phase I. Stage IV & V for the Faculty of Applied Sciences (363.5) | (Balance from Phase I) |  |  |  |  | 0 |  | 100 | 150 | 50 | 0
| Extension to the Administration Building of the University of Sri Jayewardenepura | 56 | [6 empty] | 56 | 0 | 0 | 0
| Extension of Faculty of Graduate Studies | 120 | [6 empty] | 50 | 35 | 35 | 0
| Information Technology Resource (computer Lab) - Stage V - faculty of Management Studies and Commerce | 500 | [6 empty] | 0 | 200 | 300 | 0
| Acquisition of Methsewana Land | [7 empty] | 0 | 100 | 0 | 0
| Acquisition of Dawatagahawatta Land | [7 empty] | 0 | 400 | 0 | 0
| Building for the faculty of Technology | 2640 | [6 empty] | 250 | 1500 | 890
| No. of Projects 07 | 1277 |  |  |  |  | 0 | 0 | 206 | 1485 | 385 | 0
| Total Allocation | [6 empty] | 390 | 972.49 | 1708.9 | 385
University of Kelaniya
Ongoing Construction Projects
| Five storied Building complex for Faculty of Humanities | 120 | 2013.01.02 | 2014.10.15 | 85.22% | 100% | 102.26 | 35 | 18 | 0 | 0 | 0
| Hostel Complex for 100 male & 100 female student at Faculty of Medicine | 170 | 2013.11.25 | 2015.05.25 | 66% | 99% | 112.2 | 35 | 69 | 0 | 0 | 0
| Six Storied Building complex for the Faculty of Science | 345 | 2014.09.23 | 2016.03.24 | 27% | 35% | 93.15 | 43 | 257 | 0 | 0 | 0
| Building for the Faculty of Social Sciences - Stage II | 25 |  |  | 53.2% | 100% | 13.3 | 13 | 28 | 0 | 0 | 0
| Building for the Faculty of Social Sciences - Stage III | 19 |  |  | 49.42% | 45% | 9.39 | 15 |  | 0 | 0 | 0
| Building for the Faculty of Commerce & Management | 25 | 2013.08.05 | 2014.08.05 | 96.2% | 100% | 24.05 | 9.25 | 1 | 0 | 0 | 0
| Multi purpose Building for the University of Kelaniya | 75 | 2014.05.16 | 2015.11.16 | 52% | 85% | 39 | 25 | 35 | 0 | 0 | 0
| Building Complex for the Information and Technology Centre | 183 | 2014.12.24 | 2016.06.23 | 19.13% | 0 | 35 | 25 | 147 | 0 | 0 | 0
| No. of Projects 08 | 962 |  |  |  |  | 428.35 | 200.25 | 555 | 0 | 0 | 0
Cabinet Approved Projects to be Implemented
| Building Complex (ICT) for the Dept. of Industrial Management | 500 |  |  |  |  | 0 | 100 | 150 | 150 | 100 | 0
| Multipurpose Building - Faculty of Medicine | 322 |  |  |  |  | 0 | 20 | 50 | 130 | 142 | 0
| No. of Projects 02 | 822 |  |  |  |  | 0 | 120 | 200 | 280 | 242
Pending Cabinet Approval/ NPD Approved
| Centre for Children with Development Disabilities (GOSL=10, Other=15.8) | 25.8 |  |  |  |  | 0 | 15 | 0 | 15 | 0 | 0
| New Lecture Theatre Complex Faculty of Science | 500 |  |  |  |  | 0 | 0 | 0 | 315 | 185 | 0
| Building Complex for the Faculty of Engineering | [7 empty] | 0 | 250 | 250
| No. of Projects 03 | 525.8 |  |  | 0 | 0 | 0 | 15 | 0 | 580 | 435 | 0
| Total Allocation | [6 empty] | 335.25 | 755 | 860 | 677
University of Moratuwa
Ongoing Construction Projects
Faculty of Information Technology (Rs.523mn) -
| Stage II | 205 | 2012 | 2017 | 40% | 62% | 81.9 | 15 | 119.574 | 8 | 0 | 0
| Faculty of Architecture (490 M) | [7 empty] | 0 | 0 | 0 | 0
| Phase II - Dept. of Town & Country Planning | 140 | 2012 | 2016 | 56.17% | 100% | 78.6 | 15 | 61.483 | 0 | 0 | 0
| Phase III - Dept. of Integrated Design | 110 | 2011 | 2016 | 29% | 35% | 31.9 | 15 | 80.363 | 0 | 0 | 0
| Phase IV - Dept. of Architecture | 150 | 2012 | 2016 | 33% | 55% | 49 | 15 | 104.741 | 0 | 0 | 0
| Dept. of Transport & Logistics Management | 148.2 | 2008 | 2015 | 85.71% | 100% | 127.5 | 22.5 | 21.179 | 0 | 0 | 0
| Extension to Administration building | 282 | 2008 | 2016 | 38% | 62% | 105.8 | 16.5 | 181.075 | 0 | 0 | 0
| Student Centre & Canteen Extension | 57 | 2013 | 2016 | 40.58% | 75% | 27 | 15 | 33.868 | 0 | 0 | 0
| Multipurpose Building for Faculty of Engineering | 184 | 2013 | 2016 | 41% | 44% | 75.9 | 20 | 150.446 | 0 | 0 | 0
| Lecture Room building for Faculty of Architecture | 164 | 2013 | 2016 | 25.09% | 48% | 41.141 | 20 | 122.859 | 0 | 0 | 0
| Balance work for the Dept. of Textile & Clothing | 27 | 2014 | 2016 | 22% | 50% | 6 | 0 | 22.6 | 0 | 0 | 0
| No. of Projects 08 | 1467.2 |  |  |  |  | 624.741 | 154 | 898.188 | 8 | 0 | 0
Cabinet Approved Projects to be implemented
| Building complex for the Dept of Material Science & Engineering | 240 |  |  |  |  | 0 | 0 |  | 230 | 10 | 0
| Hostel Facilities for 400 students | 194 |  |  |  |  | 0 | 2 | 53 | 133 | 8 | 0
| Advanced Bitumen testing & accelerated payment testing laboratory - Phase II (Highway Materials testing Laboratory - Phase II/ Heavy Vehicle Bitumen Testing Laboratory) (GOSL-18.1, Other-4) | 22.1 |  |  |  |  | 0 | 5 | 22.765 | 1 | 0 | 0
| Faculty of Architecture - Phase V (Storm water collection & disposal system & sewage & waste water collection, treatment & disposal) | 17 |  |  |  |  | 0 | 3 | 16.2 | 0.8 | 0 | 0
| New building for Dept. of Building Economies | 75 |  |  |  |  | 0 | 0 |  | 75 |  | 0
| Proposed Health Centre | 330 | [8 empty] | 178
| Proposed building for Outreach centre for University of Moratuwa at Kolombage Mawatha, Colombo1 | 90 | [8 empty] | 55
| International House | 135 | [8 empty] | 88
| No. of Projects 08 | 1103.1 |  |  |  |  | 0 | 10 | 91.965 | 439.8 | 339 | 0
Pending NPD Approval
| Proposed Building for Dept. of Mechanical Engineering | 247 |  |  |  |  | 0 | 0 |  | 127 | 92 | 0
| Extension to the existing single storey building of the Dept. of Textile & Clothing Technology | 307 |  |  |  |  | 0 | 0 |  | 72 | 140 | 0
| No. of Projects 02 | 554 |  |  |  |  | 0 | 0 | 0 | 199 | 232 | 0
| Total Allocation | [6 empty] | 164 | 990.153 | 646.8 | 571
University of Ruhuna
Ongoing Construction Projects
| Building for Department of Computer Science & Computer Unit - Stage I, Stage II | 291 | 2013.03.27 | 2015.02.01 | 60% | 80% | 193.5 | 102.6 | 98 |  |  | 0
| Building complex for the Faculty of Management & Fin. | 331.2 | 2013.09.25 | 2014.12.18 | 43% | 68% | 144.6 | 151.7 | 186.6 | 0 | 0 | 0
| Building for Library at Faculty of Engineering, Hapugalla | 128.6 | 2013.05.28 | 2014.10.21 | 79% | 100% | 101.8 | 4 | 25 | 0 | 0 | 0
| Construction and Completion of Housing Units for Senior Academic Staff, University of Ruhuna, Wellamadama, Matara | 19.5 | 2014.12.10 | 2015.06.07 | 27% | 40% | 5.4 | 73 | 53 | 0 | 0 | 0
| Construction and Completion of Housing Units for Administrative & Finance Staff, University of Ruhuna, Wellamadama, Matara | 19 | 2014.06.23 | 2015.02.15 | 89.89% | 90% | 17.1 |  |  | 0 | 0 | 0
| Construction and Completion of Housing Units for Senior Academic Staff, University of Ruhuna, Wellamadama, Matara | 19.25 | 2014.06.23 | 2015.02.28 | 84% | 95% | 16.5 |  |  | 0 | 0 | 0
| Construction and Completion of Housing Unit (Block 01) for Senior Academic Staff, Faculty of Engineering, University of Ruhuna, Hapugala, Galle | 19.5 | 2014.12.10 | 2015.06.07 | 18% | 15% | 3.51 |  |  | 0 | 0 | 0
| Construction and Completion of Housing Unit (Block 02) for Senior Academic Staff, Faculty of Engineering, University of Ruhuna, Hapugala, Galle | 19 | 2014.12.10 | 2015.06.07 | 0 | 20% | 0 |  |  | 0 | 0 | 0
| Construction and Completion of proposed Drawing office, lecture room & Auditorium complex (stage II) for faculty of Engineering, Hapugalla | 41.9 |  |  | 105.3% | 0 | 44.11 | 3 | 0 | 0 | 0 | 0
| New student canteen for 1000 students - Faculty of Agriculture | 19.5 | 2015.08.17 | 2016.02.12 | 0 | 0 | 0 | 19.5 | 1 | 0 | 0 | 0
| New student common room for 1000 students - Faculty of Agriculture | 19.5 | 2015.08.17 | 2016.02.12 | 0 | 0 | 0 | 19.5 | 1 | 0 | 0 | 0
| Canteen with a Communication Centre in the Premises of the Faculty of Science | 19.8 | 2015.08.17 | 2016.02.12 | 0 | 0 | 0 | 19.8 | 1 | 0 | 0 | 0
Examination Hall Building, Faculty of Humanities & Social Sciences
| - P I | 72 | 2011.09.01 | 2013.06.17 | 100% | 100% | 52.9 | 15.98 | 19 | 0 | 0 | 0
| - P II |  | 2014.07.24 | 2014.11.24 | 27% | 60%
| Construction of Three Building Blocks for the Faculty of Fisheries & Marine Science | 694.4 | 2014.05.30 | 2015.11.30 | 0.7% | 1% | 80.4 | 88 | 250 | 272 | 0
| No. of Projects 14 | 1714.15 |  |  |  |  | 659.82 | 497.08 | 634.6 | 272 | 0
Cabinet Approved Projects to be Implemented
| Small Development Project grant assistance by the Government of India for the establishment of Rabindranath Tagore Memorial Auditorium at the University of Ruhuna, Matara (336.6) | 341.6 |  |  |  |  | 0 | 0 | 0 | 50 | 0 | * Three hundred million is doneted by Governement of India
| No. of Projects 01 | 341.6 |  |  |  |  | 0 | 0 | 0 | 50 | 0
Pending Cabinet Approval/ NPD Approved
| Playground Improvement Project | 341.6 |  |  |  |  | 0 | 0 | 0 | 200 | 141.6 | 0
| No. of Projects 01 | 341.6 |  |  |  |  | 0 | 0 | 0 | 200 | 141.6
| Total Allocation | [6 empty] | 497.08 | 634.6 | 522 | 141.6
University of Jaffna
Ongoing Construction Projects
| Arts Building (Block) | 29 | 1981 | 2011 | 98% | 100% | 117 | 2 | 5 | 0 | 0 | 0
| Faculty of Agriculture - Kilinochchi | 393.8 | 2013 | 2015 | 85% | 88% | 334.7 | 20 | 47.5 | 0 | 0 | 0
| Building Complex for the Faculty of Management Studies and Commerce | 400 | 2009 | 2013 | 44% | 52% | 177 | 40 | 120 | 50 | 50 | 0
| Siddha Medicine Five Storied Building | 109.5 | 2012 | 2015 | 61% | 80% | 66.5 | 35 | 40 | 20 | 0 | 0
| Supply, Installation & Commissioning of Passenger lifts (02 Nos) and related civil works | 15.7 | 2012 | 2013 | 100% | 100% | 15.7 | 3 | 0 | 0 | 0 | 0
| Faculty of Engineering | 2437 | 2013 | 2017 | 19% | 26% | 452.2 | 80 | 500 | 700 | 600 | 0
| Natural Science Block - Faculty of Science - Stage II Phase 5 | 53 | 2014 | 2015 | 41% | 60% | 21.7 | 30 | 30 | 0 | 0 | 0
| Building Complex for the Faculty of Graduate Studies | 48 | 2014 | 2015 | 28% | 45% | 13.3 | 3 | 15 | 0 | 0 | 0
| No. of Projects 08 | 3486 |  |  |  |  | 1198.1 | 213 | 757.5 | 770 | 650 | 0
* | Cumulative Expenditure id higher than the TEC
Cabinet Approved Projects to be Implemented
| Construction of five storied building for clinical dept. of faculty of Medicine | 190 | [5 empty] | 30 | 0 | 190 | 0 | 0
| Gymnasium for the University of Jaffna | 242 | [5 empty] | 40 | 0 | 240 | 0 | 0
| No. of Projects 02 | 432 |  |  | 0 | 0 | 0 | 70 | 0 | 430 | 0 | 0
University of Jaffna - Vavuniya Campus
Ongoing Construction Projects
| Faculty of Business Studies | 92 | 2007 | 2012 | 95.33% | 95% | 87.7 | 0 | 2 | 0 | 0 | 0
| Faculty of Applied Science | 330 | 2007 | 2013 | 40% | 42% | 131.2 | 80 | 90 | 97 | 0 | 0
| Construction of Canteen | 11 | 2014 | 2015 | 100% | 97% | 11 | 0 | 0 | 0 | 0 | 0
| Construction of Gymnasium | 13.75 | 2014 | 2015 | 80% | 70% | 11 | 0 | 2 | 0 | 0 | 0
| No. of Projects 04 | 446.75 |  |  |  |  | 240.9 | 80 | 94 | 97 | 0 | 0
| Total Allocation | [6 empty] | 363 | 851.5 | 1297 | 650
The Open University of Sri Lanka
Ongoing Construction Projects
| Construction of new IT Building | 25 |  |  | 68.8% |  | 17.2 | 4 | 8 |  |  | 0
| Three storied building for maintenance building | 15 |  |  | 70.91% |  | 10.637 | 5 | 5 |  |  | 0
| Three storied building for Matara Regional Centre | 20 |  |  | 22.79% |  | 4.557 | 12 | 16 |  |  | 0
| Construction & Completion of proposed 4th floor of faculty of Education Building | 20 |  |  | 17.39% |  | 3.479 | 15 | 15 |  |  | 0
| Construction & Completion of 2nd & 3rd floor of the Anuradhapura Regional Centre | 45 |  |  | 20.76% |  | 9.34 | 25 | 20 |  |  | 0
| Renovation of Kandy Regional Centre & new student canteen | 15 | [5 empty] | 15 | 15
| Renovation of Health Science department | 3.5 | [5 empty] | 3.5 | 3.5
| Establish solar power panel to reduce electricity consumption | 45 | [5 empty] | 45 | 45
| No. of Projects 08 | 188.5 |  |  |  |  | 45.213 | 124.5 | 127.5 | 0 | 0 | 0
| Total Allocation | [6 empty] | 124.5 | 127.5 | 0 | 0
Eastern University of Sri Lanka
Ongoing Construction Projects
| Administrative Block for Faculty of Health Care Sciences | 360 |  |  | 30.17% | 35% | 108.622 | 60 | 175 | 0 | 0 | 0
| Professorial unit - Faculty of Health care service | 299 |  |  | 27% | 51% | 80.73 | 265 | 205 | 0 | 0 | 0
| Construction of Building for the Auditorium Cum Lecture Hall at the Faculty of Arts & Culture | 44.6 |  |  | 55.71% | 98% | 24.847 | 27 | 1 | 0 | 0 | 0
| Building complex Zoology Dept. | 199 |  |  | 86.5% | 99% | 172.144 | 20 | 7 | 0 | 0 | 0
| Building Complex for Faculty of Arts & Culture | 121 |  |  | 83.25% | 99% | 100.734 | 15 | 6 | 0 | 0
| Building Complex for Library | 171 |  |  | 83.7% | 99% | 143.124 | 20 | 5 | 0 | 0 | 0
| Building Complex for Faculty of Com. & Mgt. | 230 |  |  | 87.44% | 99% | 201.11 | 26 | 27 | 0 | 0 | 0
| No. of Projects 07 | 1424.6 |  |  |  |  | 831.311 | 433 | 426 | 0 | 0 | 0
| Required for 2015 | 745.5
| Allocation - 2015 | 227
| Carried Forward to 2016 | 518
Cabinet Approved Projects to be Implemented
| Building complex for the Faculty of Agriculture, EUSL | 303 | [5 empty] | 0 | 100 | 200 | 0 | 0
| No. of Projects 01 | 303 |  |  |  |  | 0 | 0 | 100 | 200 | 0 | 0
Pending Cabinet Approval/ NPD Approved
| Building complex for the English Language Teaching Unit, EUSL | 237 | [5 empty] | 0 | 0 | 237 | 0 | 0
| No. of Projects 01 | 237 |  |  |  |  | 0 | 0 | 0 | 237 | 0 | 0
| Total Allocation | [6 empty] | 433 | 526 | 437 | 0
Rajarata University of Sri Lanka
Ongoing Construction Projects
| Bdg. complex for Faculty of Mgt. | 215 | 2012.07.19 | 2014.01.24 | 87% | 100% | 186.3 | 50 | 15 | 0 | 0 | 0
| Hostels for 250 Students, Puliyankulama | 154 | 2013.05.07 | 2015.09.30 | 64% | 60% | 98.1 | 75 | 16 | 0 | 0 | 0
| Construction & Completion of building complex, Faculty of Agriculture | 143 | 2014.09.14 | 2015.12.12 | 10% | 50% | 14.4 | 40 | 100 | 0 | 0 | 0
| Deyata Kirula Project 2012 - Project II | 400 | 2014.12.31 | 2015.11.13 | 84% | 45% | 335.6 | 83 | 37 | 0 | 0 | 0
| Sports Recreation Complex - Mihintale | 42 | [6 empty] | 0 | 0 | 0 | 0
| Examination Hall - Minintale (Stage II) | 39.6 | [6 empty] | 0 | 0 | 0 | 0
| Auditorium with a Balcony of Faculty of Agriculture | 30.8 | [6 empty] | 0 | 0 | 0 | 0
| Clinical Building Complex of FMAS, Anuradhapura Stage I, II & III | 1283.647 | 2009.12.03 | 2011.12.31 | 102.7% | 100% | 1318 | 20 | 78 | 0 | 0 | 0
| Social Sciences Faculty Bldg. | 167 | 2012.05.02 | 2012.11.16 | 100.6% | 100% | 168 | 10 | 10 | 0 | 0 | 0
| Construction of Swimming Pool | 168 | 2015.06.09 | 2016.12.30 | 10% | 5% | 16.1 | 5 | 130 | 0 | 0 | 0
| No. of Projects 07 | 2643.047 |  |  |  |  | 2136.5 | 283 | 386 | 0 | 0 | 0
Cabinet Approved Projects to be Implemented
| Pre Clinical Building | 437 |  |  | 0 | 0 | 0 | 5 | 131.1 | 174.8 | 131.1 | 0
| No. of Projects 01 | 437 |  |  |  |  | 0 | 5 | 131.1 | 174.8 | 131.1 | 0
Pending Cabinet Approval/ NPD Approved
| Construction of 3 Nos of Twin Quarters for Faculty of Medical & Allied Sciences at Saliyapura | 50 |  |  | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0
| Construction of Laboratory and Lecture Hall Building | 47 |  |  | 0 | 0 | 0 | 0 | 0 | 47 | 0 | 0
| Construction & completion of proposed Quarters complex for Deans, Registrar, Bursar, Librarian, Academic & Non academic staff | 380 |  |  | 0 | 0 | 0 | 0 | 0 | 380 | 0
| No. of Projects 03 | 477 |  |  |  |  | 0 | 0 | 0 | 477 | 0 | 0
| Total Allocation | [6 empty] | 288 | 517.1 | 651.8 | 131.1
Sabaragamuwa University of Sri Lanka
Ongoing Construction Projects
| Hostel for 240 Students - Male | 175 | 2011 | Completed 2013 | 80% | 100% | 139.9 | 38 | 40 | 0 | 0 | 0
| Lecture Theatre Complex - Social Science | 672.6 | 2008 | Completed 2012 | 99% | 100% | 664.5 | 11.4 | 12 | 0 | 0 | 0
| Play Ground | 121 | 2009 | Completed 2013 | 88.93% | 100% | 107.6 | 13.4 | 59 | 0 | 0 | 0
| Applied Science Building | 296 | 2010 | Completed 2013 | 91% | 100% | 268.7 | 27.2 | 74 | 0 | 0 | 0
| Geomatics Faculty Building | 261.3 | 2011 | Completed 2013 | 92.54% | 100% | 241.9 | 19.5 | 65 | 0 | 0 | 0
| Mini Constructions | 18 |  |  | 0 |  | 0 | 5 | 0 | 0 | 0 | 0
| Administrative Building | 60 |  |  |  |  | 0 | 25 | 15 | 21 | 24 | 0
| Geomatics Building - Stage II | 173.2 |  |  |  |  | 0 | 45 | 43.3 | 60.62 | 69.28 | 0
| No. of Projects 08 | 1777.1 |  |  |  |  | 1422.6 | 184.5 | 308.3 | 81.62 | 93.28 | 0
Cabinet Approved Projects to be Implemented
| Students Cafeterias - 3 Nos | 75 | [6 empty] | 75 | 0 | 0
| IT Centre | 121 |  |  |  |  | 0 | 0 | 0 | 66.6 | 24.2 | 0
| Inner Road | 126 |  |  |  |  | 0 | 0 | 0 | 25.2 | 31.5 | 0
| Basic facilities for ICC hostel Complex (New) | 75 | [6 empty] | 75 | 0
| No. of Projects 04 | 397 |  |  |  |  | 0 | 0 | 150 | 91.8 | 55.7 | 0
Pending NPD Approval
| Library Building | 350 |  |  |  |  | 0 | 0 |  | 120 | 80 | 0
| Staff Quarters | 400 |  |  |  |  | 0 | 0 |  | 40 | 80
| Mini Hotel | 50 |  |  |  |  | 0 | 0 |  | 40 | 10
| Applied Sciences Stage II | 400 |  |  |  |  | 0 | 0 |  | 56.5 | 113
| Management Stage II | 350 |  |  |  |  | 0 | 0 | 0 | 60 | 120
| Summer Huts 15 | 7.5 | [6 empty] | 0 | 7.5 | 0
| Indoor Stadium | 450 | [7 empty] | 45 | 90
| Building complex of the Faculty of Social Sciences S I, P II | 500 | [7 empty] | 50 | 100
| No. of Projects 08 | 2507.5 |  |  |  |  | 0 | 0 | 0 | 419 | 593 | 0
| Total Allocation | [6 empty] | 184.5 | 458.3 | 592.42 | 741.98
South Eastern University of Sri Lanka
Ongoing Construction Projects
| Building Complex for Students Hostel & Staff Quarters at the Faculty of Applied Sciences | 149 | 2011.11.01 | 2014.12.31 | 47% | 85% | 70.3 | 46 | 80 | 0 | 0 | 0
| Building Complex for Faculty Management & Commerce | 160 | 2010.07.01 | 2014.02.15 | 96% | 100% | 153.2 | 20 | 2 | 0 | 0 | 0
| Building Complex for Main Library | 200 | 2010.05.10 | 2014.02.15 | 101% | 100% | 201.3 | 25 | 10 | 0 | 0 | 0
| Building Complex for Faculty of Applied Sciences | 170 | 2011.10.31 | 2014.02.15 | 80% | 100% | 136.1 | 35 | 33 | 0 | 0 | 0
| No. of Projects 04 | 679 |  |  |  |  | 560.9 | 126 | 125 | 0 | 0 | 0
Pending Cabinet Approval/ NPD Approved
| Engineering Laboratory (Phase I) ** | [7 empty] | 0 | 300 | 0 | 0
| Engineering Laboratory (Phase II) ** | [7 empty] | 0 | 200 | 0
| No. of Projects 02 | [6 empty] | 0 | 0 | 500 | 0 | 0
| Total Allocation | [6 empty] | 126 | 125 | 500 | 0
Wayamba University of Sri Lanka
Ongoing Construction Projects
Kuliyapitiya Premises
| Health Center Stage II, Kuliyapitiya | 17.5 | 2011.10.31 | 2012.12.06 | 73.03% | 100% | 12.9 | 2.3 | 1.8 | 0 | 0 | 0
| Bachelor Academic Staff Quarters,Kuliyapitiya | 49 | 2011.10.31 | 2012.08.27 | 37% | 75% | 18.3 |  | 20 |  |  | 0
| Faculty Building Stage I, FBSF, Kuliyapitiya | 165 | 2011.04.06 | 2013.03.20 | 71% | 100% | 116.9 | 5 | 7.4 | 0 | 0 | 0
| Planting of Grass and other Improvements of the Play Ground, Kuliyapitiya | 50 | 2012.10.24 | 2015.10.15 | 50% | 75% | 24.8 | 5 | 28 | 0 | 0 | 0
| Canteen Stage I & Stage II, Kuliyapitiya | 45 | 2014.08.18 | 2015.08.15 | 27.31% | 85% | 12.29 | 5 | 37 |  | 0 | 0
| Faculty of Applied Sciences Stage III (Final), Kuliyapitiya | 367 | 2014.08.29 | 2016.04.12 | 11.08% | 35% | 40.678 | 5 | 150 | 125 | 0 | 0
| Admin Building Stage II, Kuliyapitiya | 100 |  |  | 3.19% | 10% | 3.19 | 0 | 60 | 38 | 2 | 0
| Hostel Stage IV - Kuliyapitiy | 69 | 2012.01.05 | 2013.09.30 | 73% | 100% | 50.1 | 0 | 2.5 | 0 | 0 | 0
| Gymnasium | 250 | 2013.09.16 | 2014.02.15 | 43.46% | 100 | 108.65 | 0 | 141.3 | 0 | 0 | 0
| Auditorium | 250 | 2013.09.16 | 2014.02.15 | 92.36% | 100 | 230.89 | 0 | 20 | 0 | 0 | 0
| Nano - Technology Laboratory | 30 | 2013.09.16 | 2014.02.15 | 57% | 100 | 16.9 | 5.7 | 13 | 0 | 0 | 0
Makandura Premises
| Faculty Building Stage II, Faculty of Agriculture & Plantation Management , Makandura | 125 | 2012.08.02 | 2013.08.02 | 51% | 100% | 63.2 | 5 | 50 | 16 | 0 | 0
| Hostel Stage V, Makandura | 69 | 2013.05.02 | 2014.09.24 | 71% | 100% | 48.7 | 5 | 28.4 | 0 | 0 | 0
| Hostel Stage VI, Makandura | 69 | 2013.05.02 | 2014.09.24 | 47.84% | 100% | 33.1 | 2.5 | 30.2 | 0 | 0 | 0
| Faculty Building Stage III, (Final Stage) Faculty of Livestock, Fisheries and Nutrition, Makandura | 169.5 | 2013.10.21 | 2015.04.21 | 25.43% | 60% | 43.1 | 1.5 | 97.3 | 10 | 0 | 0
| Health Center Stage II, Makandura | 17.5 | 2014.01.17 | 2015.09.30 | 29% | 35% | 5 | 1 | 17 |  | 0 | 0
| Bachelor Academic Staff Quarters, Makandura | 49 | 2011.10.05 | 2013.03.12 | 65.04% | 100% | 31.87 | 2 | 0.8 | 0 | 0 | 0
| No. of Projects 17 | 1891.5 |  |  |  |  | 860.568 | 45 | 704.7 | 189 | 2 | 0
Pending NPD Approval
| Construction of Road Stage II, Makandura * | 49 | [6 empty] | 0 | 14 | 0
| No. of Projects 02 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0
| Total Allocation | [6 empty] | 45 | 704.7 | 203 | 2
* Allocation for 2016 is considered under the UGC Budget
University of Visual & Performing Arts
Ongoing Construction Projects
Albert Crescent Development Project
| (a) Music Building - Stage III - Phase III | 48 |  |  | 40.4% | 90% | 19.394 | 155 | 160 |  |  | 0
| (b) Music Faculty Building - Stage IV | 143 |  |  | 61.6% |  | 88.086
| (c) Administration Building | 124 |  |  | 89.02% |  | 110.39
| Hostel for 400 Male students at Dehiwala | 205 | 2011.05.10 | 2014.09.30 | 74.08% | 100% | 130.6 | 45 | 30 |  | 0 | 0
| Hostel for 400 Female students at Rajagiriya | 193 | 2011.06.06 | 2014.08.30 | 66.49% | 100% | 116.6 | 45 | 35 |  | 0 | 0
| No. of Projects 03 | 713 |  |  |  |  | 465.07 | 245 | 225 | 0 | 0 | 0
Pending Cabinet Approval/ NPD Approved
| Proposed Building & landscape for Faculty of Visual Arts * | 492 |  |  |  |  | 0 |  | 0 | 196 | 196 | 0
| No. of Projects 01 | 492 |  |  |  |  | 0 | 0 | 0 | 196 | 196 | 0
Pending NPD Approval
| Proposed Building for Faculty of Music & Common Facilities | [7 empty] | 0 | 400 | 375 | 0
| No. of Projects 01 | [5 empty] | 0 | 0 | 0 | 400 | 375 | 0
| Total Allocation | [6 empty] | 245 | 225 | 596 | 571
* Allocation for 2016 is considered under the UGC Budget
Uwa Wellassa University
Ongoing Construction Projects
Establishment of Uwa Wellassa University
Phase - I
| I. Administration Block | 350 | 03.08.2005 | 16.10.2006 | 99% | 100% | 348 | 10
| II. Lecture Hall + Lab - Block 'A' |  |  | 01.11.2006 |  | 100%
| III. Lecture Hall + Lab - Block 'B' |  |  | 11.10.2006 |  | 100%
| IV. Lecture Hall + Lab - Block 'C' |  |  | 11.10.2006 |  | 100%
| Phase - II | [10 empty] | 0
| Hostel Block No. 1 | 457 | 01.07.2006 | 30.05.2007 | 87% | 100% | 399 | 2 | 56
| Hostel Block No. 2 |  | 01.09.2006 | 31.08.2007
| Hostel Block No. 3 |  | 01.08.2006 | 30.07.2007
| Hostel Block No. 4 |  | 01.11.2006 | 31.10.2007
| Dinning & Study Hall |  | 15.05.2006 | 30.06.2006
| Kitchen for Dining & Study Hall |  | 01.08.2006 | 30.01.2007
| Metering Cubicle (Phase 1) | 8 | 31.08.2006 | 30.11.2006 | 66% | 100% | 5 | - | 3
| Metering Cubicle ( For Hostels) | 16 | 01.06.2007 | 30.09.2007 | 61% | 100% | 10 | -
| Water Sump & Pump House | 16 | 01.09.2006 | 31.08.2008 | 73% | 100% | 11 | -
| Landscaping - Phase - 1 Area | 36 | 01.01.2007 | 30.12.2008 | 70% | 100% | 25 | -
| Name Board and Developments at entrance | 8 | 01.07.2007 | 28.02.2008 | 35% | 100% | 3 | -
| Temporary Sports Court | 7 | 15.01.2007 | - | 70% | 100% | 5 | -
| Fiber Network (IT back-born at Phase 1 buildings) | 24 | 21.03.2013 | 21.06.2013 | 97% | 100% | 23 | - | 1
| Vice Chancellor's Bungalow | 32 | 08.09.2008 | 15.07.2009 | 98% | 100% | 31 | -
| Play Ground (For 200m track) | 40 | 01.04.2007 | 30.09.2009 | 63% | 100% | 25 | 11 | 4
| Internal Road Network A, B & D | 56 | 01.03.2007 | 30.03.2009 | 66% | 100% | 36 | - | 12 | 8
| Lecture Hall & Lab Complex Block 'E' | [6 empty] | - | 170 | 110
| Lecture Hall & Lab Complex Block 'F' | 812 | 05.09.2008 | 31.08.2010 | 65% | 100% | 529 | 2
| Lecture Hall & Lab Complex Block 'D' |  | 01.01.2009 | 15.02.2010 |  | 100% |  | -
| Sewerage System |  | 27.01.2010 | 27.04.2011 |  | 100% |  | - | 24
| Storm Water Drainage System | 24 | [5 empty] | - | 16
| Library | 31 | 30.12.2009 | 30.06.2010 | 17% | 65% | 5 | 10 | 40 | 37 | 25
| Shrine Room | 102 | [5 empty] | - | 3 | 5 | 3
| Quarters for Deans/ Registrar/ Bursar & Course Directors | 91 | 01.12.2011 | 31.12.2012 | 77% | 100% | 70 | - | 20
| Staff Quarters (Studio Apartments) | 194 | 25.11.2012 | 15.12.2011 | 50% | 100% | 97 | - | 35 | 38 | 25
| Boundary Fence | 14 | [5 empty] | 5 | 7 | 2
| Roads and Landscaping at Phase 2 Area | 38 | 17.12.2009 | 09.03.2010 | 41% | 50% | 16 |  | 12 | 6 | 4
| Sports Center & Gymnasium | 117 | 30.12.2014 | 31.12.2015 | 25% | 25% | 29 | 50 | 35 | 3
| Pavilion |  | 06.08.2015 | 16.12.2015 |  | 5% |  |  | 0
| Health Centre, Students Council | 52 | [5 empty] | - | 25 | 15 | 12
| Cafeteria and Toilets | 27 | 27.08.2012 | 26.08.2013 | 103% | 100% | 28 | - | 2
| Maintenance section | 18 | 08.01.2014 | 08.10.2014 | 66% | 100% | 12 | - | 6
| Senate Building | 117 | 20.08.2013 | 31.12.2014 | 85% | 95% | 100 | 17 | 0
| Balance work Roads and Landscaping | 57 | 22.03.2014 | 22.08.2014 | 44% | 65% | 25 | 10 | 10 | 2
| Alternative Water Supply System | 36 | [5 empty] | 0 | 15 | 13 | 8
| Auditorium | 117 | [5 empty] | 0 | 50 | 40 | 27
| Fiber Network (Master network cabling of Phase – 2 | 24 | 05.02.2013 | 05.03.2013 | 5% | 100% | 1 | 20 | 1 | 3
| Waste water drainage and treatment works | 31 | 14.10.2010 | 14.12.2011 | 36% | 85% | 11 | 8 | 7 | 5
| Finishing of 200m track and turfing of Playground | 12 | 01.04.2007 | 30.09.2009 | 36% | 55% | 4 | - | 8
| Control & Metering Cubicle (Phase 2 buildings) | 11 | 05.09.2011 | 20.10.2012 | 64% | 100% | 7 | - | 4
| Staff learning unit | 88 | [5 empty] | - | 35 | 33 | 20
| Co-operate Relation Unit | 57 | [5 empty] | - | 30 | 16 | 11
| University Guest House | 12 | 05.11.2012 | 17.08.2013 | 96% | 100% | 12 | - | 1 | 0
| Consultancy & Other Payments | 100 | N/A | N/A | 64% |  | 64 | - | 10 | 16 | 10
| No. of Projects 02 | 3232 | 0 | 0 |  |  | 1931 | 145 | 642 | 352 | 145 | 0
Pending NPD Approval
| Acquisition of Land | 100 | [5 empty] | 0 |  | 50 | 50 | 0
| Establishment of Agriculture farm | 120 | [5 empty] | 0 |  | 30 | 90 | 0
| Lecture Hall Complex for new Degree Programs | 188.5 | [5 empty] | 0 |  | 87 | 101.5 | 0
| No. of Projects 03 | 408.5 |  |  |  |  | 0 | 0 |  | 167 | 241.5
*
| Development of University Township with Accomadation & Recreation Facilities for 1500 students | 950 | [5 empty] | 0 |  | 100 | 150
| Total Allocation | [6 empty] | 145 | 642 | 519 | 386.5
Trincomalee Campus, Eastern University
Ongoing Construction Projects
| Bldg. Complex for the Faculty of Applied Science | 410 | 2014.09.04 | 2016.03.03 | 20% | 14% | 74 | 40 | 200 | 150 | 0
| Bldg. Complex for the IT Centre | 304.4 | 2014.09.04 | 2016.03.03 | 35% | 42% | 101 | 37.5 | 203.4 | 60 | 0
| Bldg. Complex for the Library | 326.2 | 2014.09.04 | 2016.03.03 | 20% | 25% | 60 | 35 | 100 | 100 | 0
| Bldg. Complex for the Canteen with Recreation Centre | 130.4 | 2014.09.04 | 2016.03.03 | 20% | 23% | 23 | 20 | 107.4 | 0 | 0
| Constrcution of Playground | 50 | 2014.04.29 | 2014.11.28 | 48% | 70% | 24 | 0 | 26 | 0
| No. of Projects 05 | 1221 |  |  |  |  | 282 | 132.5 | 636.8 | 310 | 0
| Total Allocation | [6 empty] | 132.5 | 636.8 | 310 | 0
Postgraduate Institute of Medicine (PGIM)
Ongoing Construction Projects
| Eight storied building for Medical Education & Research Centre, University of Colombo | 169 |  |  | 44.5% |  | 75.2 | 113.3 | 0 | 0 | 0 | 0
| PGIM Rodney Street Development Project Colombo 05 - University of Colombo | 1600 | 2015 December |  |  |  | 0 | 620 | 500 | 600 | 500 | 0
| No. of Projects 02 | 1769 |  |  |  |  | 75.2 | 733.3 | 500 | 600 | 500
| Total Allocation | [6 empty] | 733.3 | 500 | 600 | 500
Postgraduate Institute of English (PGIE)
Ongoing Construction Projects
| PGIE Building Project | 73 | 2014.10.27 | 2016.01.16 | 40% | 32% | 36 | 50 | 23 | 0 | 0 | 0
| No. of Projects 01 | 73 |  |  |  |  | 36 | 50 | 23 | 0 | 0 | 0
| Total Allocation | [6 empty] | 50 | 23 | 0 | 0
University of Colombo School of Computing (UCSC)
Ongoing Construction Projects
| New building for lecture halls, reading rooms & multipurpose auditorium | 256 | 2014.10.01 | 2016.09.30 | 35% | 45% | 87.2 | 0 | 156 | 0 | 0 | 40% - Genereated Income
| No. of Projects 01 | 256 |  |  |  |  | 87.2 | 0 | 156 | 0 | 0
Pending Cabinet Approval/ NPD Approved
| Construction of Canteen Block - Phase II | 82.9 |  |  |  |  | 0 | 0 | 0 | 82.9 | 0 | 0
| No. of Projects 01 | 82.9 |  |  |  |  | 0 | 0 | 0 | 82.9 | 0 | 0
| Total Allocation | [6 empty] | 0 | 156 | 82.9 | 0
Gampaha Wickramaarachchi Ayurveda Institute (GWAI)
Ongoing Construction Projects
| Wathupitiwala Garden | 7.2 |  |  | 0 |  | 0 | 0.5 | 0 | 6.7 | 0 | 0
| Admin Building | 79 | 15.05.2014 | 05.11.2015 | 63% | 65% | 36 | 20 | 46 | 0 | 0 | 0
| Four storied Academic Building | 134.4 | 10.09.2014 | 03.03.2016 | 26% | 20% | 26 | 15 | 130 | 0 | 0 | 0
| Student Centre - Stage II | 46 | 19.03.2014 | 19.03.2015 | 40% | 65% | 18 | 20 | 30 | 0 | 0 | 0
| Boundary Wall | 45 |  |  | 0 |  | 0 | 9.4 | 45 | 0 | 0 | 0
| No. of Projects 05 | 311.6 |  |  |  |  | 80 | 64.9 | 251 | 6.7 | 0 | 0
Pending NPD Approval
| Acquisition of Land * | 20 | [5 empty] | 0 | 0 | 0 | 0 | 0
| Construction of Male Hostel | 135.5 | [5 empty] | 0 | 0 | 100 | 35 | 0
| Construction of Dravyaguna Building * | 16 | [5 empty] | 0 | 0 | 0 | 0 | 0
| Eco Ayurveda & Recreation Centre - Wathupitiwala | 400 | [5 empty] | 0 | 0 | 300 | 100 | 0
| Construction of four storied Academic Building | 111 | [5 empty] | 0 | 0 | 110 | 0 | 0
| Construction of playground | 100 | [5 empty] | 0 | 0 | 100 | 0 | 0
| Academic & Non-Academic Quarters | 80 | [5 empty] | 0 | 0 | 80 | 0 | 0
| No. of Projects 07 | 862.5 |  |  |  |  | 0 | 0 | 0 | 690 | 135 | 0
| Total Allocation | [6 empty] | 64.9 | 251 | 696.7 | 135
* Allocation for 2016 is considered under the UGC Budget
University Grants Commission (UGC)
Ongoing Construction Projects
| UGC Admin Building | 75 | 2015.06.09 | 2016.06.09 | 0.2 | 0.01 | 20 | 25 | 55 | 0 | 0
| No. of Projects 01 | 75 |  |  |  |  | 20 | 25 | 55 | 0 | 0
| Total Allocation | [6 empty] | 25 | 55 | 0 | 0
Pending NPD Approval (Projects recognized by the UGC as Prioritized Projects)
University of Colombo
| Pre Clinical Building - Stage III | 5000 | 2016 | [5 empty] | 300 | 1800 | 1800
| Faculty of Management & Finance | 800 | 2016 | [5 empty] | 100 | 400 | 300
Sabaragamuwa University of Sri Lanka
| Mini Hotel | 50 | 2016 | [5 empty] | 25 | 25
Rajarata University of Sri Lanka
| Staff Quarters | 50 | 2016 | [5 empty] | 50
Wayamba University of Sri Lanka
| Construction of Road Stage II, Makandura | [7 empty] | 35
University of Visual & Performing Arts
| Proposed Building & landscape for Faculty of Visual Arts | [7 empty] | 100
Gampaha Wickramaarachchi Ayurveda Institute (GWAI)
| Acquisition of Land | [7 empty] | 20
| Construction of Dravyaguna Building | [7 empty] | 16
| No. of Projects 08 | 5900 | [6 empty] | 646 | 2225 | 2100
| Total | [6 empty] | 0 | 646 | 2225 | 2100
| Technology Stream - (Refer Table I) | [6 empty] | 0 | 1017.73 | 1180.59 | 448.49
| Total Allocation- UGC | [6 empty] | 25 | 1718.73 | 3405.59 | 2548.49
Note - Rs. 646 Mn to be retained by the UGC in order to allocate when the project is approved.
Note on B29: admin: Letter of approval sent to the uni on 18.11.2015
Note on B38: admin: Cabinet Approved on 05.01.2015
Note on B52: admin: Cabinet has granted approval & 2nd stage to be completed in 2016 Letter dated 15.12.2015
Note on B54: admin: expected to be commenced on 30th October 2015
Note on B62: admin: UGC has allocated funds & started preliminary work.
Note on B65: admin: Same as the Science Premises
Note on B85: admin: NPD Letter on 02.11.2015
Note on B90: admin: Approval Letter on 01.12.2015 - Cabinet Letter 01.11.2015
Note on B109: admin: Letter sent to the Uni on 18.11.2015
Note on B151: admin: NPD Approved on 04.11.2015
Note on B333: admin: Medical Faculty Building on 02.12.2015
Note on B471: admin: letter of approval sent to uni on 18.11.2015

## Sheet1 (hidden)
Uni/ HEI | Not in the Three Year Financial plan | NPD Approved Project included in the Budget 2016 | Pending NPD Approval
RUSL | Acq. Of Land & Building | Construction of Lab. & Lecture hall building - Fac. Of Applied Science
| CDCE centre building, stage I (using generated fund stage I - 2016) | Building for Uni Staff accomodation
Acq. Of Land - Mihintale
CMB | 25% of the cost of the project of construction of proposed building for Faculty of Graduate Studies
RUH | Boundary walls, Faculty of Engineering
Transforming six universities to International status
Vavuniya | Construction of two storied Pre cast Lecture Hall at Pampaimadu
EUSL |  | Building complex for the English Language Teaching Unit, EUSL
SUSL |  |  | Summer Huts 15 Nos
WUSL | Faculty Building Stage III (Final) - FAPM Makandura
Laboratory building to introduce Engineering Degree Programme Kuliyapitiya
PGIE | Lift for the Building
Generator for the Building
PDN |  | Building for the Computing Centre, Engineering Mathematics. Postgraduate & Engineering
Extension to the Mechanical Engineering
Rehabilitation of the water supply system
Clinical Research & Service Lab., Faculty of Medicine
Construction of New Building Complex for Faculty of Arts
Proposed Extension to Farm Animal Production and Health Faculty of Vet Medicine & Animal Science
Proposed Building Extension to the Dept. of Production Engineering, Faculty of Engineering
Reactivating the unfinished section of the New Building of the Dept. of Electrical & Electronic Engineering

## Sheet2 (hidden)
Name of the University & Construction Project | Original / Amended TCE | Implementation Period |  | Progress as at 31.05.2016 |  | Cumulative upto 31.05.2016 | Allocation 2015 | Estimated Value |  |  | Remarks | Project KPI
|  | Date of Start | Expected date of Completion | Financial (%) | Physical (%) |  |  | 2016 | 2017 | 2018
Note on A24: admin: Letter of approval sent to the uni on 18.11.2015
Note on A33: admin: Cabinet Approved on 05.01.2015
Note on A50: admin: Cabinet has granted approval & 2nd stage to be completed in 2016 Letter dated 15.12.2015
Note on A52: admin: expected to be commenced on 30th October 2015
Note on A60: admin: UGC has allocated funds & started preliminary work.
Note on A63: admin: Same as the Science Premises
Note on A77: admin: Granted approval to enroll 50 students on 15.03.2016
Note on A88: admin: NPD Letter on 02.11.2015
Note on A93: admin: Approval Letter on 01.12.2015 - Cabinet Letter 01.11.2015

## PDN
Head No: 214 - UNIVERSITY GRANTS COMMISSION
Public Investment Programme 2018- 2021
| Name of the University & Construction Project | Priority | Original / Amended TCE | Awarded Value (With Tax) | Cabinet/NPD Approved Date | Implementation Period |  | Progress as at 30.04.2018 |  | Cumulative upto 30.04.2018 | Expenditure from Jan -April 2018 | Allocation 2018 | Estimated Cost |  |  | Remarks
|  | (A) |  |  |  | Date of Start | Expected date of Completion | Financial (%) | Physical (%) |  |  |  | 2019 | 2020 | 2021
University of Peradeniya
Construction / Development Projects - Continuation
| Faculty of Medicine Para Clinical Building - Stage I - 280 mn |  | 1074.6 | 0 | 0 | 2005.08.31 | 2013.04.30 | [8 empty] | Stage I (TEC 280 mn , fp 100% pp 86%)
| Construction of Para Clinical Building - Stage II -795 mn |  |  | 680.8 | 2013.04.04 | 2013.05.27 | 2015.05.26
| Building for the Faculty of Allied Health Science - P I , P II |  | 157 | 80.9 | 2010.08.11 | 2016.01.06 | 2017.07.05
| Expansion of Student Hostel at Sarasavi Uyana |  | 89.53 | 77.7 | 2012.10.31 | 2013.10.28 | 2014.10.27
| Construction of Chemical Engineering Building - Stage II |  | 85.71 | 85.4 | 2013.04.04 | 2014.07.11 | 2015.07.10
| Proposed Extension to the Surgical Ward Faculty of Medicine |  | 81.25 | 80.9 | 2015.06.06 | 2014.07.25 | 2016.07.24
| Building for the Dept. of Management Studies |  | 93.1 | 92.9 | 2013.06.06 | 2014.07.15 | 2015.07.14
Stage I Phase III
Stage II
| Construction of Five storied Building for Faculty of Dental Science |  | 209.59 | 207.3 | 2013.04.04 | 2014.08.13 | 2016.02.19
| Master plan development Faculty of Agriculture - P I |  | 930.4 | 892.9 | 2013.03.21 | 2014.08.29 | 2017.02.28
| Building for the Dept. of Statistical and Computer Science |  | 179 | 166 | 2013.04.04 | - | -
| Master Plan development for the Faculty of Agriculture - P II |  | 383.8 | 0 | 0 | 2015.12.07 | 2017.12.06
| Construction of Upper Floor & Completion of Balance Work of the Drawing Office II (DO II), Faculty of Engineering |  | 32.1 | 35.6 | 0 | 2015.11.02 | 2016.08.01
| Geology Building - Stage II |  | 165.75 | 154.8 | 2014.07.10 | - | -
| Construction of Hockey & athletic pavilion for physical Education Dpt. |  | 30.6 | 36.4 | 2013.04.04 | - | -
| Construction of a Building for the Department of Geography Faculty of Arts |  | 95.23 | 0 | 2016.07.14 | - | -
| Extension to the Mechanical Engineering |  | 144.48 | 149.3 | 2016.07.14 | - | -
| Building for the Computing Centre, Engineering Mathematics. Postgraduate & Engineering |  | 353.2 | 294.1 | 2016.07.14 | - | -
| Proposed extension to the MainLibrary |  | 302.43 | 252.5 | 2016.06.27 | - | -
| New building for the centre for research in oral cancer for the faculty of dental science |  | 48.78 | 0 | 2016.10.04 | - | -
| Proposed Extension to Farm Animal Production and Health Faculty of Vet Medicine & Animal Science |  | 126.028 | 0 | 2016.06.27 | - | -
| No. of Projects 19 |  | 4582.578 | 3287.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Cabinet Approved Projects to be Implemented
| Extension to the Senaka Bibile Building to house pharmaceutical labs for the FAHS |  | 92.7 | 0 | 2017.01.04 | - | -
| Renovation for Hilda Obeysekara hall |  | 182.8 | 0 | 2017.07.12 | - | -
| Renovation for Heritage Buildings |  | 982.13 | 0 | 2017.04.05 | - | -
P 1 -(Wijewardana hall 240.51 mn , Arunachalam hall 45.18 mn , Jayathilaka hall 45.55 mn)
P 11 - (Ramanthan hall 221.14 mn , Sangamitta hall 96.30 mn , Akbar nel hall 141.40 mn)
Rehabilitation of the water supply system | Rehabilitation of the water supply system |  | 714.5 | 0 | 2017.07.12 | 0 | 0
| Extension to the existing Administrative Building, Faculty of Science |  | 73.38 | 0 | 2017.07.12 | - | -
| Extension to the existing Building of the department of the Molecular Biology and Biotechnology, Faculty of Science |  | 88.28 | 0 | 2017.07.12 | - | -
| Construction of New Building Complex for Faculty of Arts |  | 488.78 | 0 | 2017.07.12 | - | - | [8 empty] | 50 mn GI
| Extension to the dpt of Electrical & Electronic Engineering, Faculty of Engineering |  | 2720 | 0 | 2017.10.31 | 0 | 0
| No. of Projects 08 |  | 5342.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Pending Cabinet Approval/ NPD Approved
| Rehabilitation of the water supply system |  | 212.03 | 0 | 0 | - | - | [5 empty] | 0 | 0 | 0
| Clinical Research & Service Lab., Faculty of Medicine |  | 50.8 | 0 | 0 | - | -
| Building Extension to the Dept. of Production Engineering, Faculty of Engineering |  | 41.8 | 0 | 0 | - | -
| Postgraduate school of Advanced Medical Science |  | 4144.9 | 0 | 2013 Budget Speech | - | -
| New Canteen at Meewatura hostel premises |  | 96.77 | 0 | 2017.07.17 | 0 | 0 | [5 empty] | 0 | 0 | 0 | transfer to ramanathan hostel
| No. of Projects 05 |  | 4546.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Pending NPD Approval/ UGC Approved
| Waste water disposal system |  | 464 | 0 | 0 | - | - | [5 empty] | - | - | -
| Kandy city development project |  | 270 | 0 | 0 | - | - | [5 empty] | - | - | -
| No. of Projects 02 |  | 734 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Total Allocation |  | 15205.448 | 3287.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
* Allocation for 2016 is considered under the UGC Budget
* Allocation for 2016 is considered under the UGC Budget
Pending NPD Approval (Projects recognized by the UGC as Prioritized Projects)
University of Colombo
| Pre Clinical Building - Stage III |  | 5000 |  |  | 2016 | [6 empty] | 300 | 1800 | 1800
| Faculty of Management & Finance |  | 800 |  |  | 2016 | [6 empty] | 100 | 400 | 300
Sabaragamuwa University of Sri Lanka
| Mini Hotel |  | 50 |  |  | 2016 | [6 empty] | 25 | 25
Rajarata University of Sri Lanka
| Staff Quarters |  | 50 |  |  | 2016 | [6 empty] | 50
Wayamba University of Sri Lanka
| Construction of Road Stage II, Makandura | [11 empty] | 35
University of Visual & Performing Arts
| Proposed Building & landscape for Faculty of Visual Arts | [11 empty] | 100
Gampaha Wickramaarachchi Ayurveda Institute (GWAI)
| Acquisition of Land | [11 empty] | 20
| Construction of Dravyaguna Building | [11 empty] | 16
| No. of Projects 08 |  | 5900 | [9 empty] | 646 | 2225 | 2100
| Total | [10 empty] | 0 | 646 | 2225 | 2100
| Technology Stream - (Refer Table I) | [10 empty] | 0 | 1017.73 | 1180.59 | 448.49
| Total Allocation- UGC | [10 empty] | 50 | 1668.73 | 3405.59 | 2548.49
Note - Rs. 646 Mn to be retained by the UGC in order to allocate when the project is approved.
Note on B20: admin: Letter of approval sent to the uni on 18.11.2015
Note on B48: admin: Cabinet Approved on 05.01.2015
Note on B165: admin: Approved on 06.06.2013. No cost revision letter on 15.03.2016
Note on B172: admin: NPD Approved on 04.11.2015
Note on D21: admin: mtp -41.2
Note on D48: admin: 5485.17 budget speech 2013

## Sheet4 (hidden)
Head No: 214 - UNIVERSITY GRANTS COMMISSION
Budget Estimate 2016 - Summary of Prioritized Construction Projects
Rs. Million
Name of the University & Construction Project | No. of Projects | Original / Amended TCE | Cumulative upto 31.05.2015 | Allocation 2015 | Estimated Value
[5 empty] | 2016 | 2017 | 2018
Major Summary
Ongoing Construction Projects
Cabinet Approved Projects to be Implemented | [7 empty] | -501
Pending Cabinet Approval/ NPD Approved
Pending NPD Approval
New
Projects to be implemented by the University system as the Prioritised Projects
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
University of Peradeniya
Ongoing Construction Projects
Cabinet Approved Projects to be Implemented
Pending Cabinet Approval/ NPD Approved
| 0 | 0 | 0 | 0 | 0 | 0 | 0
University of Colombo
Ongoing Construction Projects
Cabinet Approved Projects to be Implemented
Pending Cabinet Approval/ NPD Approved
| 0 | 0 | 0 | 0 | 0 | 0 | 0
University of Sri Jayewardenepura
Ongoing Construction Projects | [6 empty] | 0
Cabinet Approved Projects to be Implemented | [6 empty] | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
University of Kelaniya
Ongoing Construction Projects | [6 empty] | 0
Cabinet Approved Projects to be Implemented | [6 empty] | 0
Pending Cabinet Approval/ NPD Approved | [6 empty] | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
University of Moratuwa
Ongoing Construction Projects
Cabinet Approved Projects to be Implemented
Pending NPD Approval
| 0 | 0 | 0 | 0 | 0 | 0 | 0
University of Ruhuna
Ongoing Construction Projects | [6 empty] | 0
Cabinet Approved Projects to be Implemented (Foreign Funded) | [6 empty] | 0
Pending Cabinet Approval/ NPD Approved | [6 empty] | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
University of Jaffna
Ongoing Construction Projects
Cabinet Approved Projects to be Implemented (2 Projects - Foreign Funded)
| 0 | 0 | 0 | 0 | 0 | 0 | 0
University of Jaffna - Vavuniya Campus
Ongoing Construction Projects
| 0 | 0 | 0 | 0 | 0 | 0 | 0
The Open University of Sri Lanka
Ongoing Construction Projects | [5 empty] | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
Eastern University of Sri Lanka
Ongoing Construction Projects | [6 empty] | 0
Cabinet Approved Projects to be Implemented | [6 empty] | 0
Pending Cabinet Approval/ NPD Approved | [6 empty] | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
Rajarata University of Sri Lanka
Ongoing Construction Projects
Cabinet Approved Projects to be Implemented
Pending Cabinet Approval/ NPD Approved
| 0 | 0 | 0 | 0 | 0 | 0 | 0
Sabaragamuwa University of Sri Lanka
Ongoing Construction Projects
Cabinet Approved Projects to be Implemented
Pending NPD Approval
| 0 | 0 | 0 | 0 | 0 | 0 | 0
South Eastern University of Sri Lanka
Ongoing Construction Projects
Pending Cabinet Approval/ NPD Approved
| 0 | 0 | 0 | 0 | 0 | 0 | 0
Wayamba University of Sri Lanka
Ongoing Construction Projects
New
| 0 | 0 | 0 | 0 | 0 | 0 | 0
University of the Visual Performing Arts
Ongoing Construction Projects
Pending Cabinet Approval/ NPD Approved
Pending NPD Approval
| 0 | 0 | 0 | 0 | 0 | 0 | 0
Uwa Wellassa University
Ongoing Construction Projects
Pending NPD Approval
| 0 | 0 | 0 | 0 | 0 | 0 | 0
Trincomalee Campus - Eastern University of Sri Lanka
Ongoing Construction Projects
| 0 | 0 | 0 | 0 | 0 | 0 | 0
Postgraduate Institute of Medicine (PGIM)
Ongoing Construction Projects
| 0 | 0 | 0 | 0 | 0 | 0 | 0
Postgraduate Institute of English (PGIE)
Ongoing Construction Projects
| 0 | 0 | 0 | 0 | 0 | 0 | 0
University of Colombo School of Computing (UCSC)
Ongoing Construction Projects
Pending Cabinet Approval/ NPD Approved
| 0 | 0 | 0 | 0 | 0 | 0 | 0
Gampaha Wickramarachchi Ayurveda Institute (GWAI)
Ongoing Construction Projects
Pending NPD Approval
| 0 | 0 | 0 | 0 | 0 | 0 | 0
University Grants Commission (UGC)
Ongoing Construction Projects
Projects to be implemented by the University system as the Prioritised Projects
| 0 | 0 | 0 | 0 | 0 | 0 | 0

## CMB (hidden)
Head No: 214 - UNIVERSITY GRANTS COMMISSION
Medium Term Projects 2017 - 2020
Objective 1: Widen participation & equitable access to higher education
Objective 2: Improve physical & aesthetic environment & stakeholder satisfaction
Programme: Construction Projects | [10 empty] | Rs. Million
Name of the University & Construction Project | Original / Amended TCE | Implementation Period |  | Progress as at 30.09.2016 |  | Cumulative upto 30.09.2016 | Allocation 2017 | Estimated Value |  |  | Remarks
|  | Date of Start | Expected date of Completion | Financial (%) | Physical (%) |  |  | 2018 | 2019 | 2020
University of Colombo
Construction / Development Projects - Continuation
Building complex at Maradana road (Pre Clinical Building)
- S II | 840 | 2014.02.07 | 2016.04.29 | 57% | 79% | 478.6 | 219 | 167.9 | 84 | 0
University of Colombo | [13 empty] | 4549
Construction and completion of remaining stage of Pre - Clinical Department, Library and Canteen for Faculty of Medicine -S II , III | 5688 | 2014.02.07 | 2016.04.29 | 66% | 91.9% | 0 | 20 | 1364.7 | 1819.6 | 1137.25 | (TEC 1139 FP 92% PP 66%) | 5688 | 5668
Extension to the Existing Building of Faculty of Education | 128.3 | 2015.01.28 | 2016.04.09 | 96% | 100% | 123.22 | 10 |  | - | - |  | 5.08 | -4.92
Extension to the East Wing Building, Faculty of Management & Finance S I,II | 130 | 2015.11.17 | 2017.05.16 | 49% | 67% | 63 | 32 | 10.5 | 14 | 10.5 |  | 67 | 35
25% of the cost of th e Project of Construction of Proposes Building for Faculty of Graduate Studies | 253 | 2014.07.21 | 2015.07.21 | 63% | 75% | 160 | 29 | 19.2 | 25.6 | 19.2 | 25% GOSL 75% GI | 93 | 64
No. of Projects 04 | 6199.3 | #VALUE! | #VALUE! |  |  | 346.22 | 91 | 1394.4 | 1859.2 | 1166.95 |  | #REF!
Cabinet Approved Projects to be Implemented
Establishment of a Student service center at the faculty of Science | 468.4 | - | - | - | - | 0 | 0 | 140.52 | 187.36 | 140.52
Information and Learning Center at the Faculty of Science | 850 | - | - | - | - | 0 | 0 | 255 | 340 | 255
Six Storied Building for the Department of Stastices , Faculty of Science | 485.8 | - | - | - | - | 0 | 0 | 145.74 | 194.32 | 145.74
Extension to the west wing building of the faculty of management and Finance | 290 | - | - | - | - | 0 | 0 | 87 | 116 | 87
Project Proposal for Establishment of A Faculty of Technology | 2087 | - | - | - | - | 0 | 0 | 626.1 | 834.8 | 626.1 | Technology stream
No. of Projects 05 | 4181.2 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 1254.36 | 1672.48 | 1254.36
Pending Cabinet Approval/ NPD Approved
Six Storied Bilding for the Department of Statistics Faculty of Science | 191.118 | - | - | - | - | 0 | 0 | 0 | 57.3354 | 76.4472
proposed help zone | 530 | - | - | - | - | - | - | - | - | 530
No. of Projects 02 | 721.118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57.3354 | 606.4472
3
Sri Palee Campus - University of Colombo
Cabinet Approved Projects to be Implemented
Extension to Library Building | 60.44 | - | - | - | - | - | - | 18.132 | 24.176 | 18.132
Administration Building | 149.97 | - | - | - | - | - | - | 44.991 | 59.988 | 44.991
No. of Projects 02 | 210.41 | 0 | 0 | 0 | 0 | 0 | 0 | 63.123 | 84.164 | 63.123
Total Allocation | 11312.028 |  |  |  |  | #REF! | #REF! | 2711.883 | 3673.1794 | 3090.8802
4
Note on A13: admin: Cabinet has granted approval & 2nd stage to be completed in 2016 Letter dated 15.12.2015
Note on A17: admin: expected to be commenced on 30th October 2015
Note on A19: only - progress review report

## SJP
Head No: 214 - UNIVERSITY GRANTS COMMISSION
Public Investment Programme 2018- 2021
Objective 1: Widen participation & equitable access to higher education
Objective 2: Improve physical & aesthetic environment & stakeholder satisfaction
Programme: Construction Projects | [13 empty] | Rs. Million
Name of the University & Construction Project | Priority | Original / Amended TCE | Awarded Value (With Tax) | Cabinet/NPD Approved Date | Implementation Period |  | Progress as at 30.04.2018 |  | Cumulative upto 30.04.2018 | Expenditure from Jan -April 2018 | Allocation 2018 | Estimated Cost |  |  | Remarks
| (A) |  |  |  | Date of Start | Expected date of Completion | Financial (%) | Physical (%) |  |  |  | 2019 | 2020 | 2021
University of Sri Jayewardenepura
Construction / Development Projects - Continuation
Building Programme - Faculty of Applied Sciences - Phase I |  | 363.5 | 0 | 0 | 2013.06.15 | 2014.09.17
Stage II
Stage III |  |  |  |  | 2014.09.10 | 2015.11.24
Building for Faculty Management Studies & Commerce – 157.5 (Balance) |  | 62.4 | 55.09 | 2011.09.28 | 2015.06.29 | 2016.04.30
Construction of Phase IV building for Faculty of Medical Sciences |  | 1599.4 | 1559.4 | 2014.02.21 | 2014.03.17 | 2016.03.16
Three storied extension to the Administration building |  | 55.54 | 47.7 | 2016.03.24 | 2016.07.29 | 2017.05.25
Wimaladharma Hostel |  | 156.4 | 150.95 | 2016.10.04 | 2017.08.03 | 2018.08.03
Staff Quarters -Abeyratne mawatha, Boralesgamuwa |  | 125.8 | 122.3 | 2016.10.04 | 2017.08.03 | 2018.11.03
Boundry wall & gates for Faculty of Medical Science |  | 26 | 0 | 0 | 2017.03.08 | 2017.10.04
Building for the faculty of Technology |  | 2640 | 3073.47 | 2015.11.24 | 2017.08.10 | 2020.08.09 | [8 empty] | Technology Stream
Faculty of Engineering -Building & Infrastucture |  | 2941 | 0 | 2016.07.12 | 0 | 0
No. of Projects 09 |  | 7970.04 | 5008.91 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
Cabinet Approved Projects to be Implemented
Multipurpose building for faculty of Humanities & social science & services dpt |  | 1364 | 0 | 2017.07.12 | 32 Months | - | [8 empty] | 0
Multipurpose building complex for faculty of management studies & commerce |  | 1761.4 | 0 | 2017.07.12 | 32 Months | - | [8 empty] | 0
No. of Projects 02 |  | 3125.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
NPD Approved/ Pending Cabinet Approval
Budget proposal for obtain global accreditation for the faculty of Management Studies & Commerce |  | 40
Budget proposal for Establishment of a centre for Entrepreneurship & innovation foe the purpose of Nurturing an entrepreneurial culture through innovation |  | 724.85 |  | 2018.03.19
No. of Projects 02 |  | 764.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Total Allocation |  | 11860.29 | 5008.91 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Note on A11: admin: Granted approval to enroll 50 students on 15.03.2016
Note on A20: admin: Approval Letter on 01.12.2015 - Cabinet Letter 01.11.2015

## CMB.
Head No: 214 - UNIVERSITY GRANTS COMMISSION
Public Investment Programme 2018- 2021
Objective 1: Widen participation & equitable access to higher education
Objective 2: Improve physical & aesthetic environment & stakeholder satisfaction
Programme: Construction Projects
Rs. Million
Name of the University & Construction Project | Priority | Original / Amended TCE | Awarded Value (With Tax) | Cabinet/NPD Approved Date | Implementation Period |  | Progress as at 30.04.2018 |  | Cumulative upto 30.04.2018 | Expenditure from Jan -April 2018 | Allocation 2018 | Estimated Cost
| (A) |  |  |  | Date of Start | Expected date of Completion | Financial (%) | Physical (%) |  |  |  | 2019 | 2020 | 2021
University of Colombo
Construction / Development Projects - Continuation
Building complex at Maradana road (Pre Clinical Building)
- S II |  | 840 |  |  | 2014.02.07 | 2016.04.29 | 57% | 79% | 478.6 |  | 219 | 167.9 | 84 | 0
University of Colombo
Ongoing Construction Projects
Construction and completion of remaining stage of Pre - Clinical Department, Library and Canteen for Faculty of Medicine -S I , II |  | 6604 | 840 | 2014.01.03 | 2014.02.07 | 2020 May
Construction and completion of remaining stage of Pre - Clinical Department, Library and Canteen for Faculty of Medicine -S III (872 mn GI) |  |  | 5630.25 | 2017.05.18
Extension to the Existing Building of Faculty of Education |  | 128.3 | 133.63 | 2013.06.06 | 2015.01.28 | 2016.04.09
Extension to the East Wing Building, Faculty of Management & Finance S I,II |  | 130 | 130.35 | 2013.06.06 | 2015.11.17 | 2017.05.16
25% of the cost of th e Project of Construction of Proposes Building for Faculty of Graduate Studies |  | 253 | 0 | 2016.06.22 | 2014.07.21 | 2015.07.21
Establishment of a Student service center at the faculty of Science |  | 468.4 | 0 | 0 | 2017 | 2020
Information and Learning Center at the Faculty of Science |  | 850 | 0 | 0 | 2017 | 2020
Six Storied Building for the Department of Stastices , Faculty of Science |  | 485.8 | 419.42 | 2017.07.11 | 2017 | 2020
Extension to the west wing building of the faculty of Management and Finance |  | 290 | 272.9 | 2017.07.04 | 2017 | 2020
proposed help zone |  | 530 | 0 | 2017.04.05 | 2017 | 2020
Project Proposal for Establishment of A Faculty of Technology |  | 2087 | 2072.59 | 2016.10.12 | - | -
7 storied building Faculty of Graduate Studies - S 1,11,111 (GI) |  | 405 | 0 | 0 | 2014.07.21 | 2018.06.04
No. of Projects 11 |  | 12231.5 | 9499.14 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0
Pending NPD Approval/UGC Approved
Proposal for establishment of a faculty of Technology -S 2 (ADB Funds) |  | 4389
Extension to the Next Art Wing bulding of the faculty of Art - p1 |  | 581
No. of Projects 02 |  | 4970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Sri Palee Campus - University of Colombo
Ongoing Construction Projects
Extension to Library Building |  | 60.44 | 0 | 2016.11.08 | - | -
Administration Building |  | 149.97 | 0 | 2016.11.08 | - | -
No. of Projects 02 |  | 210.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Total Allocation |  | 17411.91 | 9499.14 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
9
Note on A13: admin: Cabinet has granted approval & 2nd stage to be completed in 2016 Letter dated 15.12.2015
Note on A19: admin: expected to be commenced on 30th October 2015
Note on A21: only - progress review report

## KLN
Head No: 214 - UNIVERSITY GRANTS COMMISSION
Public Investment Programme 2018- 2021
Name of the University & Construction Project | Priority | Original / Amended TCE | Awarded Value (With Tax) | Cabinet/NPD Approved Date | Implementation Period |  | Progress as at 30.04.2018 |  | Cumulative upto 30.04.2018 | Expenditure from Jan -April 2018 | Allocation 2018 | Estimated Cost |  |  | Remarks
| (A) |  |  |  | Date of Start | Expected date of Completion | Financial (%) | Physical (%) |  |  |  | 2019 | 2020 | 2021
University of Kelaniya
Ongoing Construction Projects
Six Storied Building complex for the Faculty of Science |  | 345 | 259.8 | 2017.12.09 | 2014.09.23 | 2016.03.24
Building for the Faculty of Social Sciences - Stage II |  | 25 | 24.8 | 2007.12.19 | 2013.10.01 | 2015.7.15
Building for the Faculty of Social Sciences - Stage III |  | 19 | 17.9 | 2014.07.10 | 2014.09.15 | 2015.05.15
Multi purpose Building for the University of Kelaniya |  | 75 | 0 | 2013.06.06 | 2014.05.16 | 2015.12.30
Building Complex for the Information and Technology Centre |  | 183 | 181.2 | 2013.04.09 | 2014.12.24 | 2016.06.25
Building Complex (ICT) for the Dept. of Industrial Management |  | 500 | 494.6 | 2014.05.30 | 2015.12.28 | 2018.06.28
Multipurpose Building - Faculty of Medicine |  | 322 | 317.8 | 2014.07.10 | 2016.11.17 | 2018.11.17
New Lecture Theatre Complex Faculty of Science |  | 500 | 448.9 | 2016.07.12 | - | -
Construction of 3rd and 4th floor in the block B in building complex for the Technology Degree programme |  | 110 | 109.1 | 2016.06.22 | - | - | [8 empty] | Technology Stream
No. of Projects 09 |  | 2079 | 1854.1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Cabinet Approved Projects to be Implemented
Multi story Building complex by Alumni Association |  | 1602 | 0 | 2017.03.28 | - | - | [8 empty] | 820Mn GI , 782 Mn GF
No. of Projects 01 |  | 1602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Pending NPD Approval/ UGC Approved
National centre of execllence for children with disabilities (100% Donation) |  | 350 | 0 | 0 | 0 | 0
10 Story faculty building Faculty of Mgt & Commerce |  | 1417 | 0 | 0 | 0 | 0
Completion works of 6 storied building of lecture hall , examination hall (GOSL - 156 , 60 GF) |  | 216 | 0 | 0 | 0 | 0
No. of Projects 03 |  | 1983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Total Allocation |  | 5664 | 1854.1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Note on A12: admin: Letter sent to the Uni on 18.11.2015
Note on A14: Has been recommended by the Cabinet in 2007, but not implemented since it is still in the designing stage.

## MRT
Head No: 214 - UNIVERSITY GRANTS COMMISSION
Public Investment Programme 2018- 2021
Name of the University & Construction Project | Priority | Original / Amended TCE | Awarded Value (With Tax) | Cabinet/NPD Approved Date | Implementation Period |  | Progress as at 30.04.2018 |  | Cumulative upto 30.04.2018 | Expenditure from Jan -April 2018 | Allocation 2018 | Estimated Cost |  |  | Remarks
| (A) |  |  |  | Date of Start | Expected date of Completion | Financial (%) | Physical (%) |  |  |  | 2019 | 2020 | 2021
University of Moratuwa
Ongoing Construction Projects
Faculty of Information Technology (Rs.523mn) -S II |  | 205 | 143.09 | 2008.05.04 | 5.8.2014 | 30.4.2016
Faculty of Architecture (490 M)
Phase II - Dept. of Town & Country Planning |  | 140 | 109.39 | 2005.08.03 | 27.9.2012 | 24.7.2013
Phase III - Dept. of Integrated Design |  | 110 | 88.99 | 2006.08.03 | 8.7.2014 | 31.7.2016
Phase IV - Dept. of Architecture |  | 150 | 109.45 | 2007.08.03 | 9.5.2014 | 31.5.2016
Extension to Administration building |  | 282 | 222.66 | 2012.03.23 | 5.12.2013 | 31.5.2016
Student Centre & Canteen Extension |  | 57 | 53.53 | 2013.06.06 | 12.8.2014 | 31.7.2015
Multipurpose Building for Faculty of Engineering |  | 184 | 178.96 | 2013.06.06 | 25.8.2014 | 31.5.2016
Lecture Room building for Faculty of Architecture |  | 164 | 161.19 | 2013.06.06 | 25.8.2014 | 31.5.2016
Balance work for the Dept. of Textile & Clothing |  | 30 | 26.86 | 0 | 18.3.2015 | 30.4.2016
Advanced Bitumen testing & accelerated pavement testing laboratory - Phase II Highway Materials testing Laboratory |  | 23.77 | 15.23 | 0 | 18.03.2015 | 20.06.2016 | [8 empty] | GOSL-18.1 Mn Other-4 Mn
Hostel Facilities for 400 students |  | 194 | 0 | 0 | 0 | -
New building for Dept. of Building Economies |  | 75 | 0 | 0 | - | -
Building for Extension for the Dept. of Textile & Clothing Technology |  | 307 | 0 | 0 | - | -
No. of Projects 13 |  | 1921.77 | 1109.35 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Cabinet Approved to be Implemented
Proposed Building for Dept. of Mechanical Engineering |  | 247 | 0 | 2017.03.28 | - | -
Design, Construction and completion of the proposes Building for the Department of Materials Science and Engineering |  | 439 | 0 | 2017.03.28 | - | 0
No. of Projects 02 |  | 686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Pending NPD Approval/UGC Approved
4 Storied Hostel building for Academics (Staff quarters) (GOSL -141mn ,GF 35mn) |  | 176 | 0 | 0 | - | -
Design construction & completion of a 4 storied reinforced concrete building - kohombage mawatha (GOSL - 22mn ,GF 91 mn) |  | 113 | 0 | 0 | - | -
No. of Projects 02 |  | 289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | #VALUE! | #VALUE!
Total Allocation |  | 2896.77 | 1109.35 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | #VALUE! | #VALUE!
Note on A20: admin: NPD Approved on 04.11.2015

## RUH
Head No: 214 - UNIVERSITY GRANTS COMMISSION
Public Investment Programme 2018- 2021
Name of the University & Construction Project | Priority | Original / Amended TCE | Awarded Value (With Tax) | Cabinet/NPD Approved Date | Implementation Period |  | Progress as at 30.04.2018 |  | Cumulative upto 30.04.2018 | Expenditure from Jan -April 2018 | Allocation 2018 | Estimated Cost |  |  | Remarks
| (A) |  |  |  | Date of Start | Expected date of Completion | Financial (%) | Physical (%) |  |  |  | 2019 | 2020 | 2021
University of Ruhuna
Ongoing Construction Projects
Building for Department of Computer Science & Computer Unit - Stage I, II |  | 291 | 179.4 | 2004.09.15 | 2013.03.27 | 2014.09.17 | [9 empty] | 291
Building complex for the Faculty of Management & Fin. |  | 331.2 | 231.7 | 2010.08.16 | 2013.09.25 | 2014.12.18 | [9 empty] | 331.2
Construction and Completion of Housing Unit (Block 01) for Senior Academic Staff, Faculty of Engineering, |  | 19 | 20.1 | 0 | 2014.12.10 | 2015.06.07 | [9 empty] | 19
Construction and Completion of Housing Unit (Block 02) for Senior Academic Staff, Faculty of Engineering |  | 19.5 | 20.6 | 0 | 2014.12.10 | 2015.10.08 | [9 empty] | 19.5
New student canteen for 1000 students - Faculty of Agriculture |  | 19.5 | 18.381 | 0 | 2015.08.17 | 2016.02.12 | [9 empty] | 19.5
Canteen with a Communication Centre in the Premises of the Faculty of Science |  | 21.23 | 18.84 | 0 | 2015.08.17 | 2016.02.12 | [9 empty] | 21.23
Construction of Three Building Blocks for the Faculty of Fisheries & Marine Science p I |  | 304.6 | 272.1 | 2011.08.17 | 2012.07.23 | 2013.10.23 | [9 empty] | 304.6
Construction of Three Building Blocks for the Faculty of Fisheries & Marine Science P II |  | 694.4 | 655.088 | 2013.06.06 | 2015.05.05 | 2016.11.22 | [9 empty] | 694.4
Establishment of Rabindranath Tagore Memorial Auditorium - 300mn Indian funds |  | 336.6 | 304.4 | 2015.03.04 | 2016.05.16 | 2017.11.16 | [9 empty] | 336.6
Balance work of proposed Examination hall/Auditoriun/Deans office |  | 21 | 21.3 | 2008.06.16 | 2014.07.24 | 2015.09.11 | [9 empty] | 21
Building complex for the Department of Technology |  | 692 | 611.1 | 2015.10.28 | 0 | 0 | [8 empty] | Technology Stream | 692
Construction of two story building as an extension to the existing library building to provide self learning spaces, reading spaces , reading rooms & space for legal deposit collection |  | 126.32 | 119.8 | 2016.10.04 | 0 | 0
Construction and completion of building complex, Faculty of management and Finance |  | 276.4 | 0 | 2016.11.08 | 0 | 0
Construction of Two Three Storied Building for the Administration Block |  | 260.72 | 0 | 2017.04.05 | 0 | 0 | [9 empty] | NPD approved on 22.12.2016
12 storied building Faculty of Medicine |  | 1179.7 | 0 | 2017.03.28 | 0 | 0 | [8 empty] | contract awrded 20.09.2017 | NPD approved on 06.01.2017
No. of Projects 15 |  | 4593.17 | 2472.809 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 4593.17
Cabinet Approved to be Implemented
proposed building project with equipment for southern centre for naval studies and shipping faculty of engineering |  | 943 |  | 2018.04.03
Proposal to establish new professorial 10 stories ward complex ,FOM at Teaching hospital karapitiya (P1-380mn , P11-670 mn, P3 -250 mn (Equipment) |  | 1300 |  | 2018.04.03
Construction of 3 storied lecture hall building , faculty of technology |  | 412.26 |  | 2018.02.14
No. of Projects 03 |  | 2655.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Pending Cabinet Approval/NPD Approved
Faculty of Allied Health Science |  | 3000
No. of Projects 01 |  | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Pending NPD Approval/UGC Approved
Upgrading the play ground & Construction of a pavilion |  | 639.6 | 0 | 0 | 0 | 0 | [8 empty] | 0
Major renovation -Phase I |  | 400.4 | 0 | 0 | 0 | 0 | [8 empty] | 0
Guest house at the faculty of agricultre |  | 19.5
No. of Projects 03 |  | 1059.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Total Allocation |  | 11307.93 | 2472.809 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Note on A8: admin: submit a programme for increasing the students. Letter dated 14.03.2016

## UJA
Head No: 214 - UNIVERSITY GRANTS COMMISSION
Public Investment Programme 2018- 2021
Name of the University & Construction Project | Priority | Original / Amended TCE | Awarded Value (With Tax) | Cabinet/NPD Approved Date | Implementation Period |  | Progress as at 30.04.2018 |  | Cumulative upto 30.04.2018 | Expenditure from Jan -April 2018 | Allocation 2018 | Estimated Cost |  |  | Remarks
| (A) |  |  |  | Date of Start | Expected date of Completion | Financial (%) | Physical (%) |  |  |  | 2019 | 2020 | 2021
University of Jaffna
Ongoing Construction Projects
Arts Building (Block) |  | 120 | 120 | 1999.11.03 | 1981 | 2011
Renovation of Building Faculty of Agriculture - Kilinochchi |  | 393.8 | 0 | 2012.01.18 | 2013 | 2018
Building Complex for the Faculty of Management Studies and Commerce |  | 400 | 0 | 2008.12.11 | 2009 | 2018
Siddha Medicine Five Storied Building -S I Kaithady |  | 109.5 | 88.7 | 2010.09.02 | 2012 | 2016
Building complex for Faculty of Engineering - Ariviyalangar , Kilinochchi |  | 2437 |  | 2012.12.07 | 2013 | 2017
Natural Science Block-Faculty of Science -S II Phase IV |  | 53 | 39.6 | 2013.05.07 | 2014 | 2015
Building Complex for the Faculty of Graduate Studies |  | 48 | 44.48 | 2014.06.18 | 2014 | 2015
Eight staoried building for the clinical department faculty of medicine |  | 700 | 649.3 | 2016.06.27 | 2017 | 2019
Sport recreation complex (Gymnasium) for the University of Jaffna |  | 242 | 222.7 | 2014.06.16 | 2016.12.28 | 2017.12.31
Construction of Building and other related Structures for Engineering Technology, University of Jaffna at Ariviyal Nagar , kilinochchi |  | 525 | 488.1 | 2016.05.26 | - | -
Staff Quarters of the faculty of Engineering |  | 166.4 | 132.8 | 2016.06.27 | 2017 | 2018
No. of Projects 11 |  | 5194.7 | 1785.68 | #VALUE! | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Cabinet Approved Projects to be Implemented
Construction of Building and other related structures for the Department of Computer Science |  | 240 | 0 | 2017.01.04 | 0 | 0
State of Art building complex for the Allied Health Science |  | 1125 | 0 | 2017.07.12 | 0 | 0
No. of Projects 02 |  | 1365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Pending Cabinet Approval/NPD Approved
Construction & completion of balance 4th & 5th floore of existing 5 story building for siddha medicine unit |  | 130.1 |  | 2017.10.24 | [9 empty] | 0 | 2017.10.24
No. of Projects 01 |  | 130.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
University of Jaffna - Vavuniya Campus
Ongoing Construction Projects
Faculty of Applied Science |  | 330 | 0 | 0 | 2007 | 2013
Construction of two storied pre cast Lecture Hall , Pampaimadu |  | 59.37 | 44.1 | 2013.05.22 | 2013 | 2014
Construction of two story building , services & related structures for the Department of Information & Communication Technology, Faculty of Applied Sciences |  | 200 | 171.2 | 2016.05.26 | - | - | [8 empty] | Technology Stream
No. of Projects 03 |  | 589.37 | 215.3 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Cabinet Approved Projects to be Implemented
3 storied building Library |  | 467 | 0 | 2018.02.14 | 0 | 0
Construction of 3 story building services and related structures for IT centre |  | 200 | 0 | 2018.02.14 | 0 | 0
No. of Projects 02 |  | 667 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Pending Cabinet Approval/NPD Approved
Building and other related structres for Faculty of Business Studies -P 11 |  | 926 |  | 2018.03.12
Administrative Building |  | 584 | 0 | 2018.01.18 | 0 | 0
3 Storied staff residence |  | 350 | 0 | 2018.01.18 | 0 | 0
No. of Projects 03 |  | 1860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Total Allocation |  | 9806.17 | 2000.98 | #VALUE! | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0

## OUSL
Head No: 214 - UNIVERSITY GRANTS COMMISSION
Public Investment Programme 2018- 2021
Name of the University & Construction Project | Priority | Original / Amended TCE | Awarded Value (With Tax) | Cabinet/NPD Approved Date | Implementation Period |  | Progress as at 30.04.2018 |  | Cumulative upto 30.04.2018 | Expenditure from Jan -April 2018 | Allocation 2018 | Estimated Cost |  |  | Remarks
| (A) |  |  |  | Date of Start | Expected date of Completion | Financial (%) | Physical (%) |  |  |  | 2019 | 2020 | 2021
The Open University of Sri Lanka
Ongoing Construction Projects
Establish solar power panel to reduce electricity consumption |  | 45 | 0 | 0 | 2015.12.23 | 2017.12.31
Construction of four storied Building for Jaffna Regional Centre (80mn GOSL) |  | 200 | 0 | 0 | 2017.11.01 | 2019.11.01
No. of Projects 02 |  | 245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Cabinet Approved Projects to be Implemented
5 Storied building for faculty of Health Science (262.5 mn GI) |  | 402.5 | 0 | 2017.07.12 | - | - | [8 empty] | 262.5 mn GI
Extension to the Library Building |  | 169.05 | 0 | 2017.07.12 | - | -
No. of Projects 02 |  | 571.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Pending NPD Approval/UGC Approved
Rehabilitation of Playground |  | 18.31 | 0 | 0 | 0 | 0
No. of Projects 01 |  | 18.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Total Allocation |  | 834.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0

## EUSL
Head No: 214 - UNIVERSITY GRANTS COMMISSION
Public Investment Programme 2018- 2021
Name of the University & Construction Project | Priority | Original / Amended TCE | Awarded Value (With Tax) | Cabinet/NPD Approved Date | Implementation Period |  | Progress as at 30.04.2018 |  | Cumulative upto 30.04.2018 | Expenditure from Jan -April 2018 | Allocation 2018 | Estimated Cost
| (A) |  |  |  | Date of Start | Expected date of Completion | Financial (%) | Physical (%) |  |  |  | 2019 | 2020 | 2021
Eastern University of Sri Lanka
Ongoing Construction Projects
Administrative Block for Faculty of Health Care Sciences , bldg complex for students hostel for 250 male students |  | 360 | 0 | 0 | 2014.04.28 | 2015.10.27
Building complex for Professorial unit - Faculty of Health care science Technology hospital |  | 299 | 0 | 0 | 2014.04.28 | 2015.10.27
Building complex Science faculty Zoology Dept. |  | 199 | 0 | 0 | 2011.12.29 | 2012.06.30
Building Complex for Faculty of Arts & Culture |  | 121 | 0 | 0 | 2011.12.29 | 2013.06.30
Building Complex for Library |  | 171 | 0 | 0 | 2011.12.29 | 2012.12.31
Building Complex for Faculty of Com. & Mgt. |  | 230 | 0 | 0 | 2011.12.29 | 2013.06.30
Building Complex for Faculty of Agriculture |  | 303 | 302.7 | 2016.10.11 | 2016.11.17 | 2018.08.06
Building complex for the English Language Teaching Unit |  | 237 | 207.6 | 2017.07.04 | 2017.08.17 | 2019.02.17
Building for Bio System Technology |  | 238 | 208.2 | 2017.07.04 | 0 | 0
Balance work of the completion of the construction of Bldg Complex for the professorial unit for the Faculty of HCS |  | 140 | 0 | 2017.03.28 | 0 | 0
No. of Projects 10 |  | 2298 | 718.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Pending Cabinet Approval/ NPD Approved
Refurbishment of Auditorium and Construction of mini gymnasium , Building complex with audio and vedeo recording cum editing facilities |  | 275 | 0 | 2016.05.27 | 0 | 0 | [7 empty] | 0
Blgd for Faculty of Technology |  | 3520 | 0 | 0 | 0 | 0 | [7 empty] | 0
Building complex for Faculty of Arts & Culture- P 11 |  | 600 | 0 | 2017.10.31 | 0 | 0 | [7 empty] | 0
No. of Projects 03 |  | 4395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Total Allocation |  | 6693 | 718.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0

## RUSL
Head No: 214 - UNIVERSITY GRANTS COMMISSION
Public Investment Programme 2018- 2021
Name of the University & Construction Project | Priority | Original / Amended TCE | Awarded Value (With Tax) | Cabinet/NPD Approved Date | Implementation Period |  | Progress as at 30.04.2018 |  | Cumulative upto 30.04.2018 | Expenditure from Jan -April 2018 | Allocation 2018 | Estimated Cost
| (A) |  |  |  | Date of Start | Expected date of Completion | Financial (%) | Physical (%) |  |  |  | 2019 | 2020 | 2021
Rajarata University of Sri Lanka
Ongoing Construction Projects
Bdg. complex for Faculty of Mgt. |  | 215 | 190.8 | 2007.10.17 | 2012.07.19 | 2014.01.24
Deyata Kirula Project 2012 - Project II |  | 400 | 400 | 2012 | 2014.12.31 | 2015.11.13
Clinical Building Complex of FMAS, Anuradhapura Stage I - 640 mn , II -271 mn & III - 250 mn |  | 1265 | I-640 mn ,II - 271 mn , III 250 mn | I-2009.11.26 ,II 2011.03.23 , III 2011.02.05 | 2009.12.03 | 2011.12.31
Construction of Swimming Pool |  | 168 | 167 | 2013.06.27 | 2015.06.09 | 2016.12.30
Construction and Completion of proposed Building for Center for Distance and Containing (CDCE) Center (GOSL 81.8mn) |  | 168.5 | 164.7 | 2016.07.08 | 2017.08.16 | 2018.12.16
Construction Quarters complex for Deans, Registrar, Bursar, Librarian, Academic & Non academic staff |  | 380 | 375.7 | 2016.04.05 | 2016 | 2017
Construction of 3 Nos of Twin Quarters for Faculty of Medical & Allied Sciences at Saliyapura |  | 50 | 49.3 | 2016.04.05 | 2017.05.16 | 2018.05.16
Construction of Building complex Dept. of Technology Studies - FAS |  | 156 | 155.3 | 2015.11.26 | 2017.01.31 | 2018.01.31
Construction of 8 Nos Staff Quarters Complex (04 nos. of Twin Quarters) for Dpt of Technological Studies |  | 58.2 | 60.6 | 2017.01.10 | 2017.01.06 | 2017.07.06
Construction of Sewerage Treatment plant for hostel complex |  | 200.4 | 0 | 2017.04.20 | 2018 | 2020
Construction and completion of proposed pre clinical building for FAMS |  | 896 | 0 | 2017.04.20 | 2018 | 2021
Construction and Completion of Proposed bldg Complex for Dpt of Technological Studies p- II & p- III |  | 438 | 0 | 2017.07.20 | 2018 | 2021
No. of Projects 12 |  | 4395.1 | 1563.4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Pending Cabinet Approval/NPD approved
Construction of Laboratory complex cum lecture halls for the faculty of Agriculture |  | 759 | 0 | 2017.10.31 | 0 | 0 | 0
No. of Projects 01 |  | 759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Pending NPD Approval/UGC approved
Construction of Student Canteen for hostel premises |  | 107 | 0 | 0 | 0 | 0 | 0
No. of Projects 01 |  | 107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Total Allocation |  | 5261.1 | 1563.4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0

## SUSL
Head No: 214 - UNIVERSITY GRANTS COMMISSION
Public Investment Programme 2018- 2021
Rs. Million
Name of the University & Construction Project | Priority | Original / Amended TCE | Awarded Value (With Tax) | Cabinet/NPD Approved Date | Implementation Period |  | Progress as at 30.04.2018 |  | Cumulative upto 30.04.2018 | Expenditure from Jan -April 2018 | Allocation 2018 | Estimated Cost
| (A) |  |  |  | Date of Start | Expected date of Completion | Financial (%) | Physical (%) |  |  |  | 2019 | 2020 | 2021
Sabaragamuwa University of Sri Lanka
Ongoing Construction Projects
Hostel for 240 Students - Male |  | 175 | 175 | 2006.11.09 | 2011.06.17 | 2012.06.17
Lecture Theatre Complex - Social Science |  | 672.6 | 672.6 | 2001.08.09 | 20015.09 | 2010.01
Play Ground |  | 121 | 121 | 2005.08.24 | 2010.11.01 | 2011.11.01
Building for Applied Science |  | 296 | 296 | 2009.09.16 | 2010.09 | 2011.09
Building for Faculty of Geomatics |  | 261.3 | 261.3 | 2010.04.06 | 2011.04.05 | 2012.04.05
Geomatics Building - Stage II |  | 151.48 | 174.2 | 2014.08.20 | 2016.09.20 | 2016.09.19
Basic facilities for ICC hostel Complex (New) |  | 37.5 | 0 | 0 | 2016 | 2017
Summer Huts 13 Nos |  | 11 | 0 | 0 | 2016.12.06 | 2017.05.15
Students Cafeterias - 2 Nos |  | 75 | 0 | 0 | - | -
Construction of a new building complex for the university library phase I |  | 371.83 | 0 | 2016.10.19 | 0 | 0
Hosuing Scheme - for staff |  | 414.7 | 409.07 | 2016.08.01 | 0 | 0
Construction of a cafeteria for walawa hostel complex |  | 80.07 | 0 | 2017.01.04 | 0 | 0
New Building complex for -FAS Stage II -Phase I |  | 564.52 | 0 | 2017.07.12 | 0 | 0
Construction of a new Gymnasium Complex -Indian funds |  | 333.7 | 0 | 0 | 0 | 0
No. of Projects 14 |  | 3565.7 | 2109.17 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Cabinet Approved Projects to be Implemented
New Building Complex - Technology Stream |  | 1065 | 0 | 2016.07.21 | 0 | 0
Waste water & sewerage treatment plant |  | 50 | 0 | 2017.03.28 | 0 | 0
Faculty of Medicine |  |  |  | 2018.03.06
No. of Projects 02 |  | 1115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Pending Cabinet Approval / NPD approved
Construction of faculty building P 11 - Mgt studies |  | 734.7 | 0 | 2017.09.25 | 0 | 0
No. of Projects 01 |  | 734.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Pending NPD Approval/UGC approved
Faculty Building complex faculty of Agricultural Science -P 1 |  | 975.92 | 0 | 0 | 0 | 0
No. of Projects 01 |  | 975.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Total Allocation |  | 6391.32 | 2109.17 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Note on A20: admin: onging progress review - 30.8.2017

## SEUSL
Head No: 214 - UNIVERSITY GRANTS COMMISSION
Public Investment Programme 2018- 2021
Name of the University & Construction Project | Priority | Original / Amended TCE | Awarded Value (With Tax) | Cabinet/NPD Approved Date | Implementation Period |  | Progress as at 30.04.2018 |  | Cumulative upto 30.04.2018 | Expenditure from Jan -April 2018 | Allocation 2018 | Estimated Cost
| (A) |  |  |  | Date of Start | Expected date of Completion | Financial (%) | Physical (%) |  |  |  | 2019 | 2020 | 2021
South Eastern University of Sri Lanka
Ongoing Construction Projects
Building Complex for Students Hostel & Staff Quarters at the Faculty of Applied Sciences |  | 149 | 103.61 | 2009.01.28 | 2011.11.01 | 2015.12.31
Building complex for department of Technology studies for Faculty of Applied Science |  | 451 | 0 | 2016.07.21 | 0 | 0
No. of Projects 02 |  | 600 | 103.61 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Pending Cabinet Approval/NPD Approved
Bldg Complex for Staff Quarters (Academic/Non academic) |  | 344.7 | 0 | 22.01.2018 | 0 | 0
Infrasture development at Agro Tech Park |  | 166.35 |  | 22.01.2018
No. of Projects 02 |  | 344.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Pending NPD Approval/UGC Approved
Building Cpmplex for Information Communication Technology Centre |  | 638.3 | 0 | 0 | 0 | 0
No. of Projects 01 |  | 638.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Total Allocation |  | 1583 | 103.61 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0

## WUSL
Head No: 214 - UNIVERSITY GRANTS COMMISSION
Public Investment Programme 2018- 2021
Name of the University & Construction Project | Priority | Original / Amended TCE | Awarded Value (With Tax) | Cabinet/NPD Approved Date | Implementation Period |  | Progress as at 30.04.2018 |  | Cumulative upto 30.04.2018 | Expenditure from Jan -April 2018 | Allocation 2018 | Estimated Cost |  |  | Remarks
| (A) |  |  |  | Date of Start | Expected date of Completion | Financial (%) | Physical (%) |  |  |  | 2019 | 2020 | 2021
Wayamba University of Sri Lanka
Ongoing Construction Projects
Bachelor Academic Staff Quarters,Kuliyapitiya |  | 49 | 30.24 | 2010.12.29 | 2011.10.31 | 2016.06.30
Faculty Building Stage I, FBSF, Kuliyapitiya |  | 165 | 107.28 | 2009.11.18 | 2011.04.06 | 2012.06.06
Planting of Grass and other Improvements of the Play Ground, Kuliyapitiya |  | 50 | 46.07 | 0 | 2012.10.18 | 2016.03.21
Canteen Stage I & Stage II, Kuliyapitiya |  | 45 | 44.6 | 2013.06.06 | 2014.08.18 | 2015.08.15
Faculty of Applied Sciences Stage III (Final), Kuliyapitiya |  | 367 | 353.83 | 2013.03.21 | 2014.08.29 | 2016.08.30
Admin Building Stage II, Kuliyapitiya |  | 100 | 96.94 | 2013.06.06 | 2014.09.27 | 2016.03.27
Hostel Stage IV - Kuliyapitiya |  | 55 | 0 | 0 | 2012.01.05 | 2013.01.03
Gymnasium |  | 250 | 250 | 2013.07.18 | 2013.09.16 | 2014.02.15
Auditorium |  | 250 | 250 | 2013.07.18 | 2013.09.16 | 2014.02.15
Nano - Technology Laboratory |  | 30 | 30 | 2013.07.18 | 2013.09.16 | 2014.02.15
Faculty Building Stage II Faculty of Agriculture & Plantation Management , Makandura |  | 125 | 100.3 | 2010.12.29 | 2012.08.02 | 2013.08.02
Hostel Stage V, Makandura |  | 93 | 80.15 | 2010.12.29 | 2013.05.02 | 2014.05.02
Hostel Stage VI, Makandura |  | 93 | 67.57 | 2010.12.29 | 2013.05.02 | 2014.05.02
Faculty Building Stage III, (Final Stage) Faculty of Livestock, Fisheries and Nutrition, Makandura |  | 169.5 | 149.85 | 2013.04.18 | 2013.10.21 | 2015.04.21
Health Center Stage II, Makandura |  | 17.5 | 12.05 | 0 | 2014.01.17 | 2015.09.30
Bachelor Academic Staff Quarters, Makandura |  | 49 | 30.7 | 2010.12.29 | 2011.10.05 | 2013.03.12
Construction of Laboratory Building to introduction Engineering Technology Degree Programme |  | 282 | 202.4 | 2015.11.26 | 0 | 0 | [8 empty] | Technology Stream
Medical Faculty (Budget Proposal) |  | 3229.4 | 2301.01 | 2016.05.31 | 2017.08.04 | 0
Faculty Building Stage III Faculty of Agriculture & Plantation Management , Makandura |  | 233 | 0 | 2015.11.01 | 2017.01.10 | 2018.07.09
Expansion to the faculty building of the livestock, Fisheries and Nutririon |  | 340.39 | 0 | 2016.11.16 | 0 | 0
No. of Projects 20 |  | 5992.79 | 4152.99 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Cabinet Approved Projects to be Implemented
Faculty Building S -III FBSF ,Kuliyapitiya |  | 232 | 0 | 2017.07.12
Building for Information Communication Technology Centre |  | 212 |  | 2017.03.288 | 0 | 0
Proposed Faculty of Technology - S II |  | 1696 | 0 | 2018.04.03 | 0 | 0
No. of Projects 03 |  | 2140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Pending NPD Approval/UGC Approved
Construction of Road Stage II, Makandura |  | 49 | 0 | 0 | 0 | 0
Extension and redevelopment of main canteen , Faculty of Business Studies & Finance -P 111 |  | 20.5
No. of Projects 02 |  | 69.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Total Allocation |  | 8202.29 | 4152.99 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Note on A5: admin: Medical Faculty Building on 02.12.2015

## UVPA
Head No: 214 - UNIVERSITY GRANTS COMMISSION
Public Investment Programme 2018- 2021
Name of the University & Construction Project | Priority | Original / Amended TCE | Awarded Value (With Tax) | Cabinet/NPD Approved Date | Implementation Period |  | Progress as at 30.04.2018 |  | Cumulative upto 30.04.2018 | Expenditure from Jan -April 2018 | Allocation 2018 | Estimated Cost
| (A) |  |  |  | Date of Start | Expected date of Completion | Financial (%) | Physical (%) |  |  |  | 2019 | 2020 | 2021
University of Visual & Performing Arts
Ongoing Construction Projects
Proposed Building & landscape for Faculty of Visual Arts |  | 492 | 399.05 | 2016.04.05 | 2017.03.06 | 2019.09.06
Proposed Building for Faculty of Music & Common Facilities |  | 775 | 0 | 2016.07.08 | 2017.06.19 | 2020.06.18
No. of Projects 02 |  | 1267 | 399.05 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Total Allocation |  | 1267 | 399.05 | 0 | - | - | - | - | 0 |  | 0 | 0 | 0 | 0

## UWA
Head No: 214 - UNIVERSITY GRANTS COMMISSION
Public Investment Programme 2018- 2021
Name of the University & Construction Project | Priority | Original / Amended TCE | Awarded Value (With Tax) | Cabinet/NPD Approved Date | Implementation Period |  | Progress as at 30.04.2018 |  | Cumulative upto 30.04.2018 | Expenditure from Jan -April 2018 | Allocation 2018 | Estimated Cost
| (A) |  |  |  | Date of Start | Expected date of Completion | Financial (%) | Physical (%) |  |  |  | 2019 | 2020 | 2021
Uwa Wellassa University
Ongoing Construction Projects
Establishment of Uwa Wellassa University
Phase - I
I. Administration Block |  | 350 | 0 | 0 | 03.08.2005 | 16.10.2006
II. Lecture Hall + Lab - Block 'A' | [5 empty] | 01.11.2006
III. Lecture Hall + Lab - Block 'B' | [5 empty] | 11.10.2006
IV. Lecture Hall + Lab - Block 'C' | [5 empty] | 11.10.2006
Phase - II |  |  | 0 | 0
Hostel Block No. 1 |  | 457 | 0 | 0 | 01.07.2006 | 30.05.2007
Hostel Block No. 2 |  |  | 0 | 0 | 01.09.2006 | 31.08.2007
Hostel Block No. 3 |  |  | 0 | 0 | 01.08.2006 | 30.07.2007
Hostel Block No. 4 |  |  | 0 | 0 | 01.11.2006 | 31.10.2007
Dinning & Study Hall |  |  | 0 | 0 | 15.05.2006 | 30.06.2006
Kitchen for Dining & Study Hall |  |  | 0 | 0 | 01.08.2006 | 30.01.2007
Metering Cubicle (Phase 1) |  | 8 | 0 | 0 | 31.08.2006 | 30.11.2006
Metering Cubicle ( For Hostels) |  | 16 | 0 | 0 | 01.06.2007 | 30.09.2007
Water Sump & Pump House |  | 16 | 0 | 0 | 01.09.2006 | 31.08.2008
Landscaping - Phase - 1 Area |  | 36 | 0 | 0 | 01.01.2007 | 30.12.2008
Name Board and Developments at entrance |  | 8 | 0 | 0 | 01.07.2007 | 28.02.2008
Temporary Sports Court |  | 7 | 0 | 0 | 15.01.2007 | -
Fiber Network (IT back-born at Phase 1 buildings) |  | 24 | 0 | 0 | 21.03.2013 | 21.06.2013
Vice Chancellor's Bungalow |  | 32 | 0 | 0 | 08.09.2008 | 15.07.2009
Play Ground (For 200m track) |  | 40 | 0 | 0 | 01.04.2007 | 30.09.2009
Internal Road Network A, B & D |  | 56 | 0 | 0 | 01.03.2007 | 30.03.2009
Lecture Hall & Lab Complex Block 'E' |  |  | 0 | 0
Lecture Hall & Lab Complex Block 'F' |  | 812 | 0 | 0 | 05.09.2008 | 31.08.2010
Lecture Hall & Lab Complex Block 'D' |  |  | 0 | 0 | 01.01.2009 | 15.02.2010
Sewerage System |  |  | 0 | 0 | 27.01.2010 | 27.04.2011
Storm Water Drainage System |  | 31 | 0 | 0 | 30.12.2009 | 30.06.2010
Library |  | 31 | 0 | 0 | 30.12.2009 | 30.06.2010
Shrine Room |  | 11 | 0 | 0
Boundary Fence |  | 14 | 0 | 0
Roads and Landscaping at Phase 2 Area |  | 38 | 0 | 0 | 17.12.2009 | 09.03.2010
Sports Center & Gymnasium |  | 117 | 0 | 0 | 30.12.2014 | 31.12.2015
Pavilion |  |  | 0 | 0 | 06.08.2015 | 16.12.2015
Health Centre, Students Council |  | 52 | 0 | 0
Senate Building |  | 117 | 0 | 0 | 20.08.2013 | 31.12.2014
Balance work Roads and Landscaping |  | 57 | 0 | 0 | 22.03.2014 | 22.08.2014
Alternative Water Supply System |  | 36 | 0 | 0 | 0 | 0
Auditorium |  | 117 | 0 | 0 | 0 | 0
Waste water drainage and treatment works |  | 31 | 0 | 0 | 14.10.2010 | 14.12.2011
Staff learning unit |  | 88 | 0 | 0 | 0 | 0
Co-operate Relation Unit |  | 57 | 0 | 0 | 0 | 0
Consultancy & Other Payments |  | 100 | 0 | 0 | N/A | N/A
Post Graduate Institute |  | 175 | 0 | 0 | - | 0
Sewerage System |  | 24 | 0 | 0 | 0 | 0
University Guest House |  | 12 | 0 | 0 | 05.11.2012 | 17.08.2013
Quarters for Deans/ Registrar/ Bursar & Course Directors |  | 91 | 0 | 0 | 01.12.2011 | 31.12.2012
Staff Quarters (Studio Apartments) |  | 194 | 0 | 0 | 25.11.2012 | 15.12.2011
Maintenance section |  | 18 | 0 | 0 | 08.01.2014 | 08.10.2014
Fiber Network (Master network cabling of Phase – 2 |  | 24 | 0 | 0 | 05.02.2013 | 05.03.2013
Finishing of 200m track and turfing of Playground |  | 12 | 0 | 0 | 01.04.2007 | 30.09.2009
Control & Metering Cubicle (Phase 2 buildings) |  | 11 | 0 | 0 | 05.09.2011 | 20.10.2012
Library |  | 102 | 0 | 0 | 0 | 0
Infrastructure development programme for Technology Stream Degree Programme |  | 316 | 0 | 2016.07.21 | 0 | 0
No. of Projects 39 |  | 3738 | 0 | 0 | 0 | 0 |  |  | 0 |  | 25 | 0 | 0 | 0
Cabinet Approved Projects to be Implemented
Establishment of Uva Wellassa University - P II |  | 1203 | 0 | 2018.01.16 | 0 | 0
No. of Projects 01 |  | 1203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Pending NPD Approval/UGC Approved
Acquisition of Land |  | 100 | 0 | 0 | 0 | 0
No. of Projects 01 |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Total Allocation |  | 5041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 25 | 0 | 0 | 0

## PB (hidden)
Head No: 214 - UNIVERSITY GRANTS COMMISSION
Objective 1: Widen participation & equitable access to higher education
Objective 2: Improve physical & aesthetic environment & stakeholder satisfaction
Programme: Construction Projects | [10 empty] | Rs. Million
Name of the University & Construction Project | Original / Amended TCE | Implementation Period |  | Progress as at 31.05.2016 |  | Cumulative upto 31.05.2016 | Allocation 2016 | Estimated Value |  |  | Remarks
|  | Date of Start | Expected date of Completion | Financial (%) | Physical (%) |  |  | 2017 | 2018 | 2019
Buddhist & Pali University of sri lanka
Five storied building complex at the colombo office | 307.5 | [9 empty] | Cabinet approved on 2016.10.04
Language skill development centre with examination hall | 323.5 | [9 empty] | Cabinet approved on 2016.10.04
Construction of Four Stoied Hostel Buildng for 200 foreign students | 219 | [9 empty] | Cabinet approved on 2016.10.04
No. of Projects 03 | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Allocation | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Trinco
Head No: 214 - UNIVERSITY GRANTS COMMISSION
Public Investment Programme 2018- 2021
Name of the University & Construction Project | Priority | Original / Amended TCE | Awarded Value (With Tax) | Cabinet/NPD Approved Date | Implementation Period |  | Progress as at 30.04.2018 |  | Cumulative upto 30.04.2018 | Expenditure from Jan -April 2018 | Allocation 2018 | Estimated Cost |  |  | Remarks
| (A) |  |  |  | Date of Start | Expected date of Completion | Financial (%) | Physical (%) |  |  |  | 2019 | 2020 | 2021
Trincomalee Campus, Eastern University
Ongoing Construction Projects
Bldg. Complex for the Faculty of Applied Science |  | 410 | 331.9 | 2014.06.19 | 2014.09.04 | 2017.04.10 | [8 empty] | 0
Bldg. Complex for the Library |  | 326.2 | 271 | 2014.06.19 | 2014.09.04 | 2016.08.18 | [8 empty] | 0
Bldg. Complex for the Canteen with Recreation Centre |  | 130.4 | 106.9 | 2014.06.19 | 2014.09.04 | 2016.10.15 | [8 empty] | 0
Construction of IT Building |  | 304.4 | 253.7 | 2014.06.19 | 2014.09.04 | 2016.03.03 | [8 empty] | 0
Construction of Play Ground |  | 50 | 32.4 | 0 | 2014.04.29 | 2017.04.16 | [8 empty] | 0
No. of Projects 05 |  | 1221 | 995.9 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Cabinet Approved Projects to be Implemented
Building for Multipurpose Auditiorium |  | 784.8 | 0 | 2016.11.16 | 0 | 0
Building Complex for Faculty of Commiunication and Business Studies |  | 821.4 | 0 | 2016.11.08 | 0 | 0
Construction of Internal roads |  | 145 | 0 | 2016.11.08 | 0 | 0
No. of Projects 03 |  | 1751.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Total Allocation |  | 2972.2 | 995.9 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0

## PGIE (hidden)
Head No: 214 - UNIVERSITY GRANTS COMMISSION
Medium Term Projects 2017 - 2020
Objective 1: Widen participation & equitable access to higher education
Objective 2: Improve physical & aesthetic environment & stakeholder satisfaction
Programme: Construction Projects | [10 empty] | Rs. Million
Name of the University & Construction Project | Original / Amended TCE | Implementation Period |  | Progress as at 30.09.2016 |  | Cumulative upto 30.09.2016 | Allocation 2017 | Estimated Value |  |  | Remarks
|  | Date of Start | Expected date of Completion | Financial (%) | Physical (%) |  |  | 2018 | 2019 | 2020
Postgraduate Institute of English (PGIE)
Ongoing Construction Projects
PGIE Building Project | 93 | 2014.10.27 | 2016.01.16 | 71.18% | 100% | 66.2 | 0 | 13.4 | 13.4 | 0 |  | 26.8 | 26.8
No. of Projects 01 | 93 | 0 | 0 | 0 | 0 | 66.2 | 0 | 13.4 | 13.4 | 0
Total Allocation | 93 | 0 | 0 | 0 | 0 | 66.2 | 0 | 13.4 | 13.4 | 0

## UGC (hidden)
Head No: 214 - UNIVERSITY GRANTS COMMISSION
Medium Term Projects 2017 - 2020
Objective 1: Widen participation & equitable access to higher education
Objective 2: Improve physical & aesthetic environment & stakeholder satisfaction
Programme: Construction Projects | [10 empty] | Rs. Million
Name of the University & Construction Project | Original / Amended TCE | Implementation Period |  | Progress as at 30.09.2016 |  | Cumulative upto 30.09.2016 | Allocation 2017 | Estimated Value |  |  | Remarks
|  | Date of Start | Expected date of Completion | Financial (%) | Physical (%) |  |  | 2018 | 2019 | 2020
University Grants Commission (UGC)
Ongoing Construction Projects
UGC Admin Building | 75 | 2015.06.09 | 2016.06.09 | 33.98% | 58% | 25.4819 | 50 | 5 |  | 0
No. of Projects 01 | 75 | 0 | 0 | 0 | 0 | 25.4819 | 50 | 5 | 0 | 0
Total Allocation | 75 | 0 | 0 | 0 | 0 | 25.4819 | 50 | 5 | 0 | 0
36

## IIM (hidden)
Head No: 214 - UNIVERSITY GRANTS COMMISSION
Medium Term Projects 2017 - 2019
Objective 1: Widen participation & equitable access to higher education
Objective 2: Improve physical & aesthetic environment & stakeholder satisfaction
Programme: Construction Projects | [10 empty] | Rs. Million
Name of the University & Construction Project | Original / Amended TCE | Implementation Period |  | Progress as at 30.09.2016 |  | Cumulative upto 30.09.2016 | Allocation 2016 | Estimated Value |  |  | Remarks
|  | Date of Start | Expected date of Completion | Financial (%) | Physical (%) |  |  | 2017 | 2018 | 2019
Institute of Indigenous Medicine
Ongoing Construction Projects
UGC Admin Building | 75 | 2015.06.09 | 2016.06.09 | 33.98% | 58% | 25.4819 | 55 | 50 | 5 | 0
No. of Projects 01 | 75 | 0 | 0 | 0 | 0 | 25.4819 | 55 | 50 | 5 | 0
Total Allocation | 75 | 0 | 0 | 0 | 0 | 25.4819 | 55 | 50 | 5 | 0

## summary 21.11.2016 (hidden)
Head No: 214 - UNIVERSITY GRANTS COMMISSION
Medium Term Projects 2017-2019
Rs. Mn
Name of the University /Stage on Approval | No. of Projects | Original / Amended TCE | Cumulative upto 30.09.2016 | Allocation 2016 | Estimated Value
[5 empty] | 2017 | 2018 | 2019
Major Summary
Ongoing Construction Projects | 178 | 33145 | 17997 | 6636 | 7829 | 3651 | 479
Cabinet Approved Projects to be Implemented | 65 | 24956 | 10 | 1081 | 5988 | 7209 | 5959
Pending Cabinet Approval/ NPD Approved | 14 | 6317 | #REF! | #REF! | 1298 | 3036 | 1359
Pending NPD Approval/UGC Approved | 21 | 7657 | #REF! | #REF! | #REF! | 1110 | 3083
Pending UGC Approval | 1 | 488.8 | 0 | 0 | 0 | 147 | 196
| 279 | 72563.8 | #REF! | #REF! | #REF! | 15153 | 11076
278
University of Peradeniya
Ongoing Construction Projects | 14 | 3431 | 1503 | 578 | 1130 | 0 | 0 |  | #REF! | #REF!
Cabinet Approved Projects to be Implemented | 10 | 1735 | 0 | 0 | 662 | 551 | 250 |  | #REF!
Pending Cabinet Approval/ NPD Approved | 7 | 4807 | 0 | 0 | 1243 | 2603 | 570 |  | #REF!
Pending NPD Approval/ UGC Approved | 5 | 2243 | 0 | 0 | 0 | 322 | 430 |  | #REF!
Pending UGC Approval | 1 | 488.8 |  |  |  | 147 | 196 |  | #REF!
| 37 | 12704.8 | 1503 | 578 | 3035 | 3623 | 1446 |  | #REF!
3623
University of Colombo
Ongoing Construction Projects | 4 | 1351.3 | 810.8 | 362 | 210.9 | 1859.2 | 1166.95
Cabinet Approved Projects to be Implemented | 6 | 9869.6 | #REF! | #REF! | 2165.7 | 2932.7 | 3406
Pending Cabinet Approval/ NPD Approved | 1 | 721.118 | 0 | 0 | 0 | 57.3354 | 606.4472
Pending NPD Approval/ UGC Approved | 1 | #REF! | #REF! | #REF! | #REF! | 57 | 76
| 12 | #REF! | #REF! | #REF! | #REF! | 4906.2354 | 5255.3972
University of Sri Jayewardenepura
Ongoing Construction Projects | 3 | 2013.4 | 1081.7 | 580 | 497 | 165 | 0
Cabinet Approved Projects to be Implemented | 10 | 4254 | 0 | 106 | 573 | 588 | 0
| 13 | 6267.4 | 1081.7 | 686 | 1070 | 753 | 0
University of Kelaniya
Ongoing Construction Projects | 9 | 1759 | 603 | 655 | 500 | 373 | 82
Cabinet Approved Projects to be Implemented | 3 | 636 | - | 22 | 33 | 216 | 211
| 12 | 2395 | 603 | 677 | 533 | 589 | 293
University of Moratuwa
Ongoing Construction Projects | 12 | 1491 | 956 | 527 | 279 | 91 | 0
Cabinet Approved Projects to be Implemented | 7 | 1388 | #REF! | 52 | 490 | 576 | 322
Pending Cabinet Approval/NPD Approved | 1 | 247 | 0 | 0 | 0 | 0 | 98
Pending NPD Approval/ UGC Approved | 1 | 439 | 0 | 0 | 0 | 0 | 439
| 21 | 3565 | #REF! | 579 | 769 | 667 | 859
University of Ruhuna
Ongoing Construction Projects(1 Project - Foreign Funded) | 15 | 2055.8 | 998.2 | 464 | 417 | 70 | 0
Cabinet Approved Projects to be Implemented | 3 | 1025 | #REF! | 130 | #REF! | #REF! | 187.2
Pending Cabinet Approval/NPD Approved | 1 | 276 | #REF! | 0 | #REF! | #REF! | 276
Pending NPD Approval/ UGC Approved | 1 | 260.7 | 0 | 0 | 0 | 0 | 260.7
| 20 | 3617.5 | #REF! | 594 | #REF! | #REF! | 723.9
University of Jaffna
Ongoing Construction Projects | 7 | 3561 | 1612 | 396 | 974 | 776 | 0
Cabinet Approved Projects to be Implemented | 3 | 957 | 0 | 140 | 288 | 381 | 288
Pending Cabinet Approval/NPD Approved | 1 | 240 | 0 | 0 | 0 | 0 | 240
Pending NPD Approval/UGC Approved | 1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
University of Jaffna - Vavuniya Campus
Ongoing Construction Projects | 3 | 436 | 267 | 65 | 101 | 33 | 0
Cabinet Approved Projects to be Implemented | 2 | 259 | 10 | 65 | 60 | 80 | 60
| 5 | 695 | 277 | 130 | 161 | 113 | 60
The Open University of Sri Lanka
Ongoing Construction Projects | 8 | 180 | 0 | 0 | 0 | 0 | 0
Pending Cabinet Approval/ NPD Approved | 1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Eastern University of Sri Lanka
Ongoing Construction Projects | 7 | 1425 | 1108.6 | 252 | 99.8 | 0 | 0
Cabinet Approved Projects to be Implemented | 3 | 778 | #REF! | #REF! | #REF! | 290 | #REF!
Pending Cabinet Approval/ NPD Approved | 1 | 4395 | 0 | 0 | 0 | 0 | 0
Pending NPD Approval/UGC Approved | 1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Rajarata University of Sri Lanka
Ongoing Construction Projects | 11 | 2571 | 2052 | 282 | 283.6 | 0 | 0
Cabinet Approved Projects to be Implemented | 4 | 604.5 | #REF! | 86 | 272 | 271.5 | 55
Pending Cabinet Approval/ NPD Approved | 1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Sabaragamuwa University of Sri Lanka
Ongoing Construction Projects | 8 | 1777 | 1347.4 | 160 | 281 | 84 | 0
Cabinet Approved Projects to be Implemented | 7 | 1484.8 | 0 | 87.5 | 376.5 | 534.5 | 416
Pending Cabinet Approval/ NPD Approved | 1 | 80.1 | #REF! | #REF! | #REF! | #REF! | #REF!
| 16 | 3341.9 | #REF! | #REF! | #REF! | #REF! | #REF!
South Eastern University of Sri Lanka
Ongoing Construction Projects | 3 | 600 | 0 | 72 | 0 | 0 | 0
Pending NPD Approval/UGC Approved | 1 | 638.3 | 0 | 0 | 0 | 0 | 0
| 4 | 1238.3 | 0 | 72 | 0 | 0 | 0
Wayamba University of Sri Lanka
Ongoing Construction Projects | 17 | 1892 | 1004 | 332.2 | 552 | 64 | 0
Pending NPD Approval/UGC Approved | 2 | 69.5 | 0 | 0 | 0 | 0 | 20
| 19 | 1961.5 | 1004 | 332.2 | 552 | 64 | 20
University of the Visual Performing Arts
Ongoing Construction Projects | 5 | 1267 | 576 | 0 | 0 | 0 | 0
Cabinet Approved Projects to be Implemented | 2 | #REF! | #REF! | 37 | 570 | 571 | 126
| 7 | #REF! | #REF! | 37 | 570 | 571 | 126
Uwa Wellassa University
Ongoing Construction Projects | 38 | 3738 | 2051 | 25 | 0 | 0 | 0
Pending NPD Approval/UGC Approved | 4 | 100 | 0 | 0 | 0 | 0 | 0
| 42 | 3838 | 2051 | 25 | 0 | 0 | 0
Trincomalee Campus - Eastern University of Sri Lanka
Ongoing Construction Projects | 5 | 1221 | 580 | 0 | 0 | 199 | 0
| 5 | 1221 | 580 | 0 | 0 | 199 | 0
Postgraduate Institute of Medicine (PGIM)
Ongoing Construction Projects | 2 | #REF! | 700 | 0 | #REF! | #REF! | #REF!
| 2 | #REF! | 700 | 0 | #REF! | #REF! | #REF!
Postgraduate Institute of English (PGIE)
Ongoing Construction Projects | 1 | 93 | 66.2 | 0 | 13.4 | 13.4 | 0
| 1 | 93 | 66.2 | 0 | 13.4 | 13.4 | 0
University of Colombo School of Computing (UCSC)
Ongoing Construction Projects | 1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Cabinet Approved Projects to be Implemented | 1 | #REF! | #REF! | #REF! | 73 | 10 | #REF!
| 2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Gampaha Wickramarachchi Ayurveda Institute (GWAI)
Ongoing Construction Projects | 4 | #REF! | 98 | 149 | #REF! | #REF! | #REF!
Cabinet Approved Projects to be Implemented | 1 | #REF! | #REF! | #REF! | 0 | 0 | 0
Pending NPD Approval/UGC Approved | 3 | 691.5 | #REF! | #REF! | 27 | 197.5 | 244
| 8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Institute of Agro Technology and Rural Sciences (IARS)
Cabinet Approved Projects to be Implemented | 1 | #REF! | #REF! | 10 | #REF! | #REF! | #REF!
| 1 | #REF! | #REF! | 10 | #REF! | #REF! | #REF!
Postgraduate Institute of Science (PGIS)
Cabinet Approved Projects to be Implemented | 1 | #REF! | #REF! | 3 | 137.1 | 0 | 0
| 1 | #REF! | #REF! | 3 | 137.1 | 0 | 0
University Grants Commission (UGC)
Ongoing Construction Projects | 1 | 75 | 19.7 | 50 | 5 | 0 | 0
| 1 | 75 | 19.7 | 50 | 5 | 0 | 0
Note on C48: admin: include donation from india

## Sheet3 (hidden)
Head No: 214 - UNIVERSITY GRANTS COMMISSION
Medium Term Projects 2017 - 2020
Rs. Mn
Name of the University /Stage on Approval | No. of Projects | Original / Amended TCE | Allocation 2017 | Cumulative upto 30.09.2016
Major Summary
Ongoing Construction Projects | 182 | #REF! | #REF! | #REF!
Cabinet Approved Projects to be Implemented | 26 | #REF! | 0 | #REF!
Pending Cabinet Approval/ NPD Approved | 22 | #REF! | #REF! | #REF!
Pending NPD Approval/UGC Approved | 17 | #REF! | #REF! | #REF!
Pending UGC Approval | 0 | 0 | 0 | 0
| 247 | #REF! | #REF! | #REF!
University of Peradeniya
Ongoing Construction Projects | 20 | 4582.578 | 0 | 0
Cabinet Approved Projects to be Implemented | 2 | 5342.57 | 0 | 0
Pending Cabinet Approval/ NPD Approved | 10 | 4546.3 | 0 | 0
Pending NPD Approval/ UGC Approved | 4 | 734 | 0 | 0
Pending UGC Approval
| 36 | 15205.448 | 0 | 0
University of Colombo
Ongoing Construction Projects | 4 | 6199.3 | 91 | 346.22
Cabinet Approved Projects to be Implemented | 5 | 4391.61 | #VALUE! | #VALUE!
Pending Cabinet Approval/ NPD Approved | 2 | 721.118 | 0 | 0
Pending NPD Approval/ UGC Approved |  |  | 0
| 11 | 11312.028 | #VALUE! | #VALUE!
University of Sri Jayewardenepura
Ongoing Construction Projects | 6 | 7970.04 | 0 | 0
Cabinet Approved Projects to be Implemented | 4 | 3125.4 | 0 | 0
Pending NPD Approval/ UGC Approved | 0 | 0 | 0 | 0
| 10 | 11095.44 | 0 | 0
University of Kelaniya
Ongoing Construction Projects | 10 | 2079 | 0 | 0
Cabinet Approved Projects to be Implemented | 0 | 0 | 0 | 0
Pending NPD Approval/ UGC Approved | 1 | 1602 | 0 | 0
| 11 | 3681 | 0 | 0
University of Moratuwa
Ongoing Construction Projects | 14 | 1921.77 | 0 | 0
Cabinet Approved Projects to be Implemented | 0 | 0 | 0 | 0
Pending Cabinet Approval/NPD Approved | 2 | 686 | 0 | 0
Pending NPD Approval/ UGC Approved | 2 | 289 | 0 | 0
| 18 | 2896.77 | 0 | 0
University of Ruhuna
Ongoing Construction Projects | 13 | 4593.17 | 0 | 0
Cabinet Approved Projects to be Implemented | 0 | 0 | 0 | 0
Pending Cabinet Approval/NPD Approved | 2 | #REF! | #REF! | #REF!
Pending NPD Approval/ UGC Approved
| 15 | #REF! | #REF! | #REF!
University of Jaffna
Ongoing Construction Projects | 11 | 5194.7 | 0 | 0
Cabinet Approved Projects to be Implemented | 2 | 1365 | 0 | 0
Pending Cabinet Approval/NPD Approved
Pending NPD Approval/UGC Approved | 2 | #REF! | #REF! | #REF!
| 15 | #REF! | #REF! | #REF!
University of Jaffna - Vavuniya Campus
Ongoing Construction Projects | 3 | 589.37 | 0 | 0
Cabinet Approved Projects to be Implemented | 0 | 0 | 0 | 0
| 3 | 589.37 | 0 | 0
The Open University of Sri Lanka
Ongoing Construction Projects | 2 | 245 | 0 | 0
Pending NPD Approval/UGC Approved | 2 | 571.55 | 0 | 0
| 4 | 816.55 | 0 | 0
Eastern University of Sri Lanka
Ongoing Construction Projects | 9 | 2298 | 0 | 0
Cabinet Approved Projects to be Implemented | 0 | 0 | 0 | 0
Pending Cabinet Approval/ NPD Approved | 2 | 4395 | 0 | 0
Pending NPD Approval/UGC Approved
| 11 | 6693 | 0 | 0
Rajarata University of Sri Lanka
Ongoing Construction Projects | 6 | 4395.1 | 0 | 0
Cabinet Approved Projects to be Implemented | 2 | #REF! | #REF! | #REF!
Pending Cabinet Approval/ NPD Approved | 3 | #REF! | #REF! | #REF!
| 11 | #REF! | #REF! | #REF!
Sabaragamuwa University of Sri Lanka
Ongoing Construction Projects | 11 | 3565.7 | 0 | 0
Cabinet Approved Projects to be Implemented | 3 | 1115 | 0 | 0
Pending Cabinet Approval/ NPD Approved | 1 | #REF! | #REF! | #REF!
Pending NPD Approval/UGC Approved
| 15 | #REF! | #REF! | #REF!
South Eastern University of Sri Lanka
Ongoing Construction Projects | 1 | 600 | 0 | 0
Cabinet Approved Projects to be Implemented | 1 | #REF! | #REF! | #REF!
Pending NPD Approval/UGC Approved | 1 | 638.3 | 0 | 0
| 3 | #REF! | #REF! | #REF!
Wayamba University of Sri Lanka
Ongoing Construction Projects | 18 | 5992.79 | 0 | 0
Cabinet Approved Projects to be Implemented | 1 | 2140 | 0 | 0
Pending NPD Approval/UGC Approved | 2 | 69.5 | 0 | 0
| 21 | 8202.29 | 0 | 0
University of the Visual Performing Arts
Ongoing Construction Projects | 5 | 1267 | 0 | 0
Cabinet Approved Projects to be Implemented | 0 | 0 | 0 | 0
| 5 | 1267 | 0 | 0
Uwa Wellassa University
Ongoing Construction Projects | 38 | 3738 | 25 | 0
Cabinet Approved Projects to be Implemented | 1 | #REF! | #REF! | #REF!
Pending NPD Approval/UGC Approved | 1 | 100 | 0 | 0
| 40 | #REF! | #REF! | #REF!
Trincomalee Campus - Eastern University of Sri Lanka
Ongoing Construction Projects | 3 | 1221 | 0 | 0
Cabinet Approved Projects to be Implemented | 3 | 1751.2 | 0 | 0
| 6 | 2972.2 | 0 | 0
Gampaha Wickramarachchi Ayurveda Institute (GWAI)
Ongoing Construction Projects | 3 | #REF! | #REF! | #REF!
Cabinet Approved Projects to be Implemented | 1 | #REF! | #REF! | #REF!
Pending NPD Approval/UGC Approved | 2 | #REF! | #REF! | #REF!
| 6 | #REF! | #REF! | #REF!
University of Colombo School of Computing (UCSC)
Ongoing Construction Projects | 2 | #REF! | #REF! | #REF!
Cabinet Approved Projects to be Implemented
| 2 | #REF! | #REF! | #REF!
Postgraduate Institute of Medicine (PGIM)
Ongoing Construction Projects | 1 | #REF! | #REF! | #REF!
| 1 | #REF! | #REF! | #REF!
Institute of Agro Technology and Rural Sciences (IARS)
Cabinet Approved Projects to be Implemented | 1 | #REF! | #REF! | #REF!
| 1 | #REF! | #REF! | #REF!
Postgraduate Institute of Science (PGIS)
Ongoing Construction Projects | 1 | #REF! | #REF! | #REF!
| 1 | #REF! | #REF! | #REF!
University Grants Commission (UGC)
Ongoing Construction Projects | 1 | 75 | 50 | 25.4819
| 1 | 75 | 50 | 25.4819
5
Note on C50: admin: include donation from india