## FORMAT
PROGRESS REVIEW ON ONGOING CONSTRUCTION PROJECTS
AS AT ……………………………………………
Name of the University / HEI …………………………..
Rs. (Mn)
No | Name of the project | TEC / Revised TEC | Awarded Value (With Tax) | Project Duration |  | Cumulative Progress as at ………………. |  | Financial Progress (………………..) | Allocation (……………) | Outstanding Bills (………….) | Remarks
|  |  |  | Date of Award | End Date/Extended Date | Financial (Rs.Mn) | Physical % *
1
2
3
4
5
Total
Attention :
* Update the Awarded value, Date of Award & extended Date / Expected Date to be complete the project
* If there are projects in the above list, both physically and financialy completed, please, state " Physicaly and Financialy completed" in the Remarks column and update the date of completion.
* Include the projects if any, which are not included in the given list above
Ledgends - Physical Progress
15% - | Foundation Completion (A)
30% - | 50% of concrete structure and walls completion (B)
50% - | 100% of concrete structure and walls and roof completion (C)
70% - | All plastering works, plumbing and Electrical wiring completion (D)
80% - | Doors/Windows and Floor finishes completion (E)
90% - | Painting, installation of plumbing/sanitary/electrical fittings completion (F)
100% - | External work and handed over completion (G)